## Master Information Table
Site No | Dept | Site Name | Address | County | LUG | Facility or Site # | Project # | Site Name | Type | Contaminant | Risk | Redevelop Potential | Recreation? | Overall Status | Est. Closure Date | Closure Type | Comments
1 | MDNR | Roscommon Toxaphene Storage Pit | 1515 E. Robinson Lake Rd. | Roscommon | Roscommon | 72000003 | 500001 | DNR Forest Fire Experiment Sta | Storage Pit | DDT & toxaphene | High | Moderate | No | In Progress | 2022 | NA | Performing RCRA post-closure groundwater monitoring and annual reporting. Pursued option of closure but contaminants persist.
2 | MDNR | Tobico Marsh - Hartley and Hartley | 2301 North 2 Mile Rd. | Bay | Kawkawlin Twp. | 09000015 | 500002 |  | Dump | Radioactive material and organic compounds | High | Moderate | No | Closed | 2005 |  | Separate state funding. Decommissioning approved in 2005.
3 | MDNR | Gaylord Repair Shop | 540 S. Otsego Ave. | Otsego | Gaylord | 69000006 | 500003 | Gaylord Repair Shop | UST | Petroleum products | High | High | No | Closed | 2018 | Due Care | NFA approved site closure ongoing complete in FY 2017 with Post closure Due Care.
4 | MDNR | Grayling Field Office (former fish hatchery) | 4895 West N. Down River Road | Crawford | Grayling | 20000005 | 500004 | DNR Grayling Field Office | UST | Petroleum products | High | High | No | Closed | 2012 | Tier 1 Residential Closure with groundwater use restriction | Tier 1 Residential Closure with groundwater use restriction
5 | MDNR | East Tawas State Dock | 113 Newman St. | Iosco | East Tawas | 35000035 | 500005 | East Tawas State Dock | UST | Petroleum products | High | Moderate | Yes | OM | 2021 |  | Additional soil removal and groundwater sampling may be required. RC to address off-site non DNR issues. RC approval needed by DNR and City. Survey needed for RC.
6 | MDNR | Marquette Fish Hatchery | 488 Cherry Creek Rd. | Marquette | Harvey | 52000030 | 500006 | Marquette Hatchery | UST | Petroleum products | High | None | No | Closed | 2003 | Unrestricted Residential | Unrestricted Tier I Residential Closure.
7 | MDNR | Baraga District Office | North US-41, Box 440 | Baraga | Baraga | 07000009 | 500007 | Baraga District Office | UST | Petroleum products | Moderate | None | No | Closed | 2001 | Restricted Tier I Institutional Controls | Restricted Tier I Closure w/Institutional Controls
8 | MDNR | Naubinway Field Office | P.O.Box 287, US-2 | Mackinac | Naubinway | 49000016 | 500008 | Naubinway Field Office | UST | Petroleum products | High | None | No | Closed | 2013 | Commercial Tier I Closure with Deed Restrictions | Commercial Tier I Closure with Deed Restrictions
9 | MDNR | Lincoln Field Office | 408 Main St. | Alcona | Lincoln | 01000013 | 500009 | DNR Lincoln Field Office | UST | Petroleum products | High | None | No | Closed | 2005 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
10 | MDNR | Calumet Field Office | 26628 Larch Street (M-26) | Houghton | Calumet | 31000010 | 500010 | Calumet Field Office | UST | Petroleum products | Moderate | High | No | Closed | 2011 | Unrestricted Tier I Residential | Unrestricted Tier I Residential Closure
11 | MDNR | Pointe Mouillee Shooting Range | Dixie Highway/US Turnpike | Monroe | Rockwood | 58000126 | 500011 | Point Mouillee Shooting Range | Shooting range | Lead | Moderate | Low | Yes | OM | Unknown |  | Work will resume when funding becomes available.
12 | MDNR | Young State Park | 03246 Boyne City Rd. | Charlevoix | Boyne City | 15000018 | 500012 |  | UST | Petroleum products | Moderate | None | Yes | Closed | 1998 | Deed Restricted Tier II | Tier II closure w/deed restriction. Completed using other state funding.
13 | MDNR | Willard Landfill - Highland Rec Area | 1910 Teeple Lake Rd. | Oakland | Highland | 63000863 | 500013 | Willard LF Highland Rec Area | Dump | Organic compounds | Low | Low | Yes | Not Liable | NA |  | State determined to be not liable.
14 | MDNR | CARGEM | 9264A Old US 27 | Roscommon | Houghton Lake | 72000024 | 500014 | Cargem | Surface spill | Waste oil & metals | Low | Moderate | Yes | Closed | 2003 | Generic Residential | Generic residential closure. Site has been redeveloped.
15 | MDNR | Moo Lee Landfill-Pointe Mouille Dump | Roberts Rd. | Monroe | Rockwood | 58000014 | 500015 | Moo Lee LF | Dump | Organic compounds | Low | Low | Yes | Not Liable | NA |  | State determined to be not liable.
16 | MDNR | Onaway Field Office | R #1, Box 32, M-211 | Presque Isle | Onaway | 71000010 | 500016 |  | UST | Petroleum products | Low | None | No | Closed | 1998 | Unrestricted Tier 1Residential | Unrestricted Tier 1 Residential Closure.
17 | MDNR | Mackinac Island State Park | Mackinac Island | Mackinac | Mackinac Island | 49000042 | 500017 |  | UST | Petroleum products | Low | None | Yes | Closed | 1997 | Unrestricted Tier 1 Residential | Unrestricted Tier 1 Residential Closure.
18 | MDNR | Lime Island | Lime Island | Chippewa | St. Mary's River | 17000010 | 500018 | Lime Island | AST | Petroleum products | Low | Moderate | Yes | No Funding | Unknown 2017 |  | Work will resume when funding is available.
19 | MDNR | Clare Field Office | 8540 S. Clare Ave. | Clare | Clare | 18000037 | 500019 |  | UST | Petroleum products | Unknown | Unknown | No | Closed | 1998 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
20 | MDNR | Bald Mountain Shooting Range | 1350 Greenshield, R#1 | Oakland | Lake Orion | 63005140 | 500020 | Bald Mountain Shooting Range | Shooting range | Lead | Unknown | Low | Yes | No Funding | Unknown |  | Work will resume when funding becomes available.
21 | MDNR | Rose Lake Shooting Range | 8562 E. Stoll Road | Clinton | East Lansing | 19000053 | 500021 | Rose Lake Shooting Range | Shooting range | Lead | Unknown | Low | Yes | Investigation | Unknown |  | Screening level ecological risk assessment (SCLERA) and baseline ecological risk assessment (BERA) competed. Defined furthest extent of contamination into wetland. FS done and alternatives outlined, expensive to meet criteria.
22 | MDNR | Sharonville Shooting Range | Sharon Valley Road | Jackson | Norvell | 38000348 | 500022 | Sharonville Shooting Range | Shooting range | Lead | Unknown | Low | Yes | No Funding | Unknown |  | Work will resume when funding becomes available.
23 | MDNR | Herman Radio Tower | Herman | Baraga | Herman | 07000005 | 500023 |  | UST | Petroleum products | Low | Moderate | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
24 | MDNR | Marquette Warehouse & Repair Shop | 110 Ford Rd. | Marquette | Harvey |  | 500024 |  | UST | Petroleum products | Low | None | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Completed with other state funding.
25 | MDNR | Bald Mountain Rec. Area Dump | 1350 Greenshield, R#1 | Oakland | Lake Orion | 63001138 | 500025 | Bald Mountain Rec. Area | Dump | Unknown | Unknown | Low | Yes | No Funding | Unknown |  | Work will resume when funding becomes available.
26 | MDNR | Dansville State Game Area Dump | Howard Rd. | Ingham | Dansville | 33000581 | 500026 | Dansville State Game Area Dump | Dump | Unknown | Low | Low | Yes | Not Liable |  |  | State determined to be not liable.
27 | MDNR | Waterloo Recreation Area Dump | 16345 McClure Rd., R#1 | Washtenaw | Chelsea | 81000508 | 500027 | Waterloo Recreation Area Dump | Dump | Unknown | Unknown | Low | Yes | No Funding | Unknown |  | Work will resume when funding becomes available.
28 | MDNR | Proud Lake Recreation Area | 3540 Wixom Rd., R#3 | Oakland | Milford | 63000168 | 500028 |  | Surface spill | Petroleum products | Low | None | Yes | Closed | 1998 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
29 | MDNR | Pontiac Lake Recreation Area Dumps | 7800 Gale Rd., R#2 | Oakland | Waterford | 63005165 | 500029 | Pontiac Lake Recreation Area Dumps | Dump | Unknown | Unknown | Low | Yes | No Funding | Unknown |  | Work will resume when funding becomes available.
30 | MDCH | Caro Center, Waste Site #39 | 2000 Chambers Rd., Box A | Tuscola | Caro | 79000040 | 500030 | Caro Regional Center | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier 1 Residential Closure.
31 | MDOC | Coldwater Center for Develop. Disab. & Psych. Hosp. | 620 Marshall Road | Branch | Coldwater | 12000029 | 500031 | Coldwater Regional Mental Health | Surface spill | PCBs | Low | High | No | Closed | 2002 | Unrestricted Tier 1 Residential Closure | Unrestricted Tier 1 Residential Closure. Separate state funding used.
32 | MDCH | Medical Waste Site #62 | Gunn Road Gunn Road | Ingham | Lansing | 33000582 | 500032 |  | Dump | Medical waste | Low | None | No | Closed | 2002 | Unrestricted Commercial 201 | Unrestricted commercial closure.
33 | MDMVA | Camp Grayling - Hanson Hills | Old Lake Rd. | Crawford | Grayling | 20000083 | 500033 | Camp Grayling - Hanson Hills | UST | Petroleum products | Low | Low | Yes | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
34 | MDMVA | Detroit Artillery Armory | 15000 W. Eight Mile Rd. | Oakland | Oak Park | 63000348 | 500034 | Detroit Artillery Armory | Dump | Solid and hazardous wastes | Moderate | High | No | Closed | 2015 |  | Negotiations with property owner.
35 | MDMVA | Dowagiac Armory | 700 West Prairie Ronde St. | Cass | Dowagiac | 14000075 | 500035 |  | UST | Petroleum products | Moderate | None | No | Closed | 2013 | Deed Restricted Commercial Closure | Deed Restricted Commercial Closure
36 | MDMVA | Midland Armory | 2847 E. Airport Rd. | Midland | Midland | 56000132 | 500036 |  | UST | Petroleum products | Low | None | No | Closure Activities | 2015 |  | Closure activities.
37 | MDMVA | Camp Grayling Bulk Fuel Facility | Grayling Army Airfield | Crawford | Grayling | 20000002 | 500037 | Camp Grayling Bulk Fuel Facility | AST | Petroleum products | High | None | No | OM | 2021 |  | Final groundwater monitoring with treatment system off. Submit closure report, remove wells and treatment system.
38 | MDMVA | US Prop. & Fisc. Office/Comb. Supp. Maint. Shop (USPFO/CSMS) | 3155 West St. Joseph St. | Ingham | Lansing | 33000565 | 500038 |  | UST | Petroleum products | Low | None | No | Closure Activities | 2021 |  | Additional field work required by EGLE.
39 | MDMVA | Lansing Headquarters Armory | 2500 S. Washington Ave. | Ingham | Lansing |  | 500039 |  | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Residential Tier 1 closure. Funded by National Guard Bureau.
40 | MDMVA | Detroit Light Guard Armory | 4400 E. Eight Mile Rd. | Oakland | Detroit | 82000435 | 500040 |  | UST | Petroleum products | Low | None | No | Closure Activities | 2015 |  | Closure pending.
41 | MDMVA | Camp Grayling Range 40 | Camp Grayling | Crawford | Grayling | 20000057 | 500041 |  | Shooting range | Metals, VOC, TNT | Low | None | No | Completed | 2020 |  | Completed.
42 | MDMVA | Camp Grayling Range 13 | Camp Grayling | Crawford | Grayling | 20000070 | 500042 | Camp Grayling Range 13 | Shooting range | Lead & 2,-4DNT | Unknown | None | No | Closed | 1999 | Unrestricted Tier I Residential | Unrestricted Tier I Residential Closure.
43 | MDMVA | Camp Grayling/Various Ranges | Camp Grayling | Crawford | Grayling | 20000084 | 500043 | Camp Grayling/Various Ranges | Shooting range | Unknown | Unknown | None | No | Closed | 2021 | Active Range - Due Care Plan | Long term groundwater monitoring.
44 | MDMVA | Camp Grayling/ Misc. sites | Camp Grayling | Crawford | Grayling | 20000084 | 500044 |  | Dump | Petroleum products & metals | Low | None | No | Closure Activities | 2015 |  | Closure pending.
45 | MDMVA | Camp Grayling Building #8 | Camp Grayling | Crawford | Grayling |  | 500045 |  | UST | Petroleum products | Low | None | No | Closed | 2007 | Unrestricted Tier 1 Residential Closure | Unrestricted Tier 1 Residential Closure. Project funded by the National Guard Bureau.
46 | MDMVA | Lansing Artillery Armory | 300 Elvin Court | Ingham | Lansing |  | 500046 |  | UST | Petroleum products | Low | None | No | Closed | 1997 | Unrestricted Residential Tier II | Unrestricted Tier II Residential Closure. Funded by National Guard Bureau.
47 | MDMVA | UST removals, 12 Armories | Various | Various | Various |  | 500047 |  | UST removals | Unknown | Unknown | None | No | Not Eligible | NA |  | Sites may require remediation if found to be contaminated upon UST removal. If remediation is required, sites will become eligible for funding.
48 | MDMVA | Grand Rapids Veteran's Facility | 3000 Monroe Ave. NW | Kent | Grand Rapids | 41000629 | 500048 |  | UST | Petroleum products | Unknown | None | No | Closed | 1998 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
49 | MDMVA | Adrian Armory | 230 W. Maumee | Lenawee | Adrian | 46000123 | 500049 |  | UST | Petroleum products | Low | None | No | Closed | 1996 | Unrestricted Tier 1 Residential Closure | Unrestricted Tier I Residential Closure. Funded by National Guard Bureau.
50 | MDOT | Kalkaska Maintenance Garage | 809 North Birch | Kalkaska | Kalkaska | 40000027 | 500050 | MDOT Kalkaska | Surface spill | TCE | High | None | No | OM | 2021 | No further action closure. | TCE concentrations in May 2020 monitoring analytical were below EGLE cleanup criteria. Quarterly monitoring for NFA closure underway. MDOT funded.
51 | MDOT | Materials and Technology Building | 8885 Ricks Road | Eaton | Windsor Township | 23000016 | 500051 | Materials and Technology Building | UST | TCE | High | None | No | OM | 2030 |  | Treatment system currently operating using MDOT funding.
52 | MDOT | Dobias ROW Property | 712 N. Mission St. | Isabella | Mt. Pleasant | 37000060 | 500052 | MDOT ROW Dobias Property | UST | Petroleum products | High | None | No | OM | 2022 |  | Groundwater monitoring for natural attenuation to achieve clean closure using MDOT funding.
53 | MDOT | Battle Creek Maintenance Garage | 5857 B Drive North | Calhoun | Battle Creek | 13000279 | 500053 | Battle Creek Maintenance Garage | UST | Petroleum products | High | High | No | Closed | 2003 | Restricted Commercial IV Tier II Inst. Controls | Restricted Tier II Commercial Closure.
54 | MDOT | Kalamazoo Maintenance Garage | 5673 W. Main | Kalamazoo | Kalamazoo | 39000024 | 500054 | Kalamazoo Maintenance Garage | UST | Petroleum products | High | None | No | Closed | 2013 | Unrestricted Tier 1 Residential Closure | Unrestricted Tier 1 Residential Closure. MDOT funded.
55 | MDOT | Central Michigan University | 1120 S. Mission | Isabella | Mt. Pleasant | 37000098 | 500055 | CMU/MDOT | UST | Petroleum products | Moderate | High | No | Closed | 2009 | Deed Restricted Tier II Commercial Closure | Deed Restricted Tier II Commercial Closure.
56 | MDOT | Dowagiac Maintenance Garage | 101 Wolf St. | Cass | Dowagiac | 14000050 | 500056 | Dowagiac Maintenance Garage | UST | Petroleum products | High | High | No | Closed | 2014 | Tier I Restricted | Closed with deed restrictions.
57 | MDOT | I-75 Port of Monroe | I-75 | Monroe | Monroe |  | 500057 |  | Dump | Foundry sand | Low | None | No | Not Liable | NA |  | Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activities at this site.
58 | MDOT | Boardman Rail Yard | Lake Avenue | Grand Traverse | Garfield Township |  | 500058 |  | Surface spill | Petroleum products & solvents | Moderate | None | No | Not Liable | NA |  | Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activities at this site.
59 | MDOT | Channing Rail Yard | M-95 | Dickinson | Channing | 22000006 | 500059 |  | Surface spill | Petroleum products & metals | Moderate | None | No | Not Liable | NA |  | MDEQ found the MDOT not liable on 9/29/97. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activities at this site.
60 | MDOT | Engadine Maintenance Garage | M-117 | Mackinac | Engadine |  | 500060 |  | UST | Petroleum products | Low | None | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Completed with other state funding.
61 | MDOT | St. Ignace Maintenance Garage | 500 Ferry Lane | Mackinac | St. Ignace | 49000034 | 500061 | St. Ignace Maintenance Garage | UST | Petroleum products | Moderate | None | No | Closed | 2015 |  | Groundwater monitoring for natural attenuation to achieve a restricted closure.
62 | MDOT | Saginaw East Side Maintenance Garage | 3504 E. Washington | Saginaw | Saginaw | 73000092 | 500062 |  | UST | Petroleum products | Low | None | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Completed with other state funding.
63 | MDOT | Mason Maintenance Garage | 601 Jewett Rd. | Ingham | Mason | 33000286 | 500063 | Mason Maintenance Garage | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
64 | MDOT | Paw Paw Maintenance Garage | Michigan Ave. (Red Arrow Hwy.) | Van Buren | PawPaw | 80000157 | 500064 |  | UST | Petroleum products | Moderate | None | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
65 | MDOT | Jones Maintenance Garage | 61535 M-40 | Cass | Jones | 14000080 | 500065 | Jones Maintenance Garage(MDOT) | UST | Petroleum products | Moderate | None | No | Closed | 2014 | Restricted | Deed restricted closure.
66 | MDOT | Mio Maintenance Garage | 305 West M-72 | Oscoda | Mio | 68000008 | 500066 | Mio Maintenance Garage | UST | Petroleum products | Low | Moderate | No | Closed | 2010 | Deed Restricted Tier I Residential | Deed Restricted Residential Tier I Residential Closure.
67 | MDOT | L'Anse Maintenance Garage | 301 Winter St. | Baraga | L'Anse |  | 500067 |  | UST | Petroleum products | Low | None | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Completed with other state funding.
68 | MDOT | Atlanta Maintenance Garage | 4000 E. M-32 | Montmorency | Atlanta | 60000017 | 500068 | Atlanta Maintenance Garage | UST | Petroleum products | Low | None | No | Closed | 2009 | Deed Restricted Tier II Residential Closure | Deed Restricted Tier II Residential Closure.
69 | MDOT | South Haven Maintenance Garage | 9235 Blue Star Memorial Hwy. | Van Buren | South Haven | 80000158 | 500069 | South Haven Maintenance Garage | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
70 | MDOT | Colon Maintenance Garage | 407 N. Sturgis Rd. | St. Joseph | Colon | 75000090 | 500070 |  | UST | Petroleum products | Low | High | No | Closed | 1999 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
71 | MDOT | Lansing Automotive & Equipment Bldg. | 2522 West Main St. | Ingham | Lansing | 33000584 | 500071 | Lansing Automotive & Equipment Bldg. | UST | Petroleum products | Low | None | No | Closed | 2009 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure
72 | MDOT | Grand Rapids A&E Garage | 1400 Scribner Ave. | Kent | Grand Rapids | 41000420 | 500072 | Grand Rapids A&E Garage | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
73 | MDOT | Marion Maintenance Garage | 2897 Sixteen Mile Rd. | Osceola | Marion | 67000009 | 500073 | Marion Maintenance Garage | UST | Petroleum products | Low | None | No | Closed | 2014 | Restricted
74 | MDOT | Auburn Hills Specialty Crews Complex | 2925 Lapeer Rd. | Oakland | Auburn Hills | 63005163 | 500074 | Auburn Hills Specialty Crews Complex | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
75 | MDOT | Williamston Maintenance Garage | 3737 E. Grand River Ave. | Ingham | Williamston | 33000030 | 500075 | Williamston Maintenance Garage | UST | Petroleum products | Moderate | None | No | Closed | 2003 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
76 | MDOT | Saginaw Specialty Crews Bldg. 201 | 2322 Gallagher St. | Saginaw | Saginaw | 73000488 | 500076 |  | UST | Petroleum products & metals | Low | High | No | Closed | 1997 | Generic Industrial | Generic Industrial Closure. Completed with other state funding.
77 | MDOT | Blue Water Bridge Maintenance Garage | 1410 Elmwood | St. Clair | Port Huron | 74000097 | 500077 |  | UST | Petroleum products | Low | None | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
78 | MDOT | Calhoun's Rib Shack | 200 S. Logan | Ingham | Lansing | 33000583 | 500078 | Calhoun's Rib Shack | UST | Petroleum products | Low | None | No | Not Liable | NA |  | State determined to be not liable.
79 | MDOT | Former Aeronautics Hangar | 16600 W. Airport Service Drive | Ingham | Lansing |  | 500079 |  | UST | Petroleum products | Low | None | No | Closed | 1996 | Unrestricted Residential Tier I | Unrestricted residential closure. Completed with other state funding.
80 | MDOT | Zilwaukee PCB I-75 | Zilwaukee Bridge, Ramps C&G | Saginaw | Zilwaukee | 73000133 | 500080 | MDOT M13 Ramps | Dump | PCBs & Leachate | Moderate | None | No | Not Liable | NA |  | State determined to be not liable.
81 | MDOT | Clare Bulk Fuel Facility | Old US-10 | Clare | Clare |  | 500081 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
82 | MDOT | Iron Mountain E&LS RR |  | Dickinson | Iron Mountain |  | 500082 |  | Unknown | Unknown | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
83 | MDOT | Clare Depot Site | Old US-10 | Clare | Clare |  | 500083 |  | Surface spill | Lead | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
84 | MDOT | Lenawee Co. RR (Adrian Railyard Facility) | 708 E. Michigan | Lenawee | Adrian |  | 500084 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
85 | MDOT | Blissfield RR | US-223 (Adrian St.) | Lenawee | Blissfield |  | 500085 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
86 | MDOT | Ontonagon E&LS RR | Zinc St., 201 Quartz Street | Ontonagon | Ontonagon | 66000009 | 500086 | Ontonagon Railroad Yard | Surface spill | PNAs & metals | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
87 | MDOT | Cadillac Railyard | North Mitchell St. (US-131) | Wexford | Cadillac |  | 500087 |  | Surface spill | PNAs, solvents & metals | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
88 | MDOT | Hillsdale Railyard | Monroe St. | Hillsdale | Hillsdale | 30000197 | 500088 |  | Unknown | PNAs & metals | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
89 | MDOT | Owosso Railyard | S. of Shiawasee River | Shiawassee | Owosso |  | 500089 |  | Surface spill | PNAs & solvents | High | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
90 | MDOT | Vassar Railyard |  | Tuscola | Vassar |  | 500090 |  | Unknown | TCE & lead | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 9/29/97 that it is not liable. Site is a railroad facility which was acquired by DOT pursuant to the State Transportation Act of 1976. The DOT has never conducted any railroad operations or other activity at this site.
91 | MDOT | Ambassador Bridge (Parcel 4002) | 1407 21st St. | Wayne | Detroit | 82000224 | 500091 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ has notified MDOT that it is not liable. Site is one which was encountered along the Right of Way. The DOT has never owned or operated this site.
92 | MDOT | Blacketts | 44840 Van Dyke | Macomb | Utica | 50001017 | 500092 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ has notified MDOT that it is not liable. Site is one which was encountered along the Right of Way. The DOT has never owned or operated this site.
93 | MDOT | Ripley | M-26 | Houghton | Ripley | 31000005 | 500093 |  | Surface spill | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ has notified MDOT that it is not liable. Site is one which was encountered along the Right of Way. The DOT has never owned or operated this site.
94 | MDOT | Parcel 718 Bio Piles | US-27 | Clinton | St. Johns |  | 500094 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ has notified MDOT that it is not liable. Site is one which was encountered along the Right of Way. The DOT has never owned or operated this site.
95 | MDOT | Lake Orion US-24 ROW | M-24 at Atwater | Oakland | Lake Orion |  | 500095 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ has notified MDOT that it is not liable. Site is one which was encountered along the Right of Way. The DOT has never owned or operated this site.
96 | MDOT | Manistique Monitoring Wells | US-2 | Schoolcraft | Manistique |  | 500096 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ notified MDOT 6/98 that it is not liable for this site. Site is a railroad facility which was acquired along a right of way.
97 | MDOT | Port Sanilac | 38 S. Ridge St. | Sanilac | Port Sanilac |  | 500097 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ has notified MDOT that it is not liable. Site is one which was encountered along the Right of Way. The DOT has never owned or operated this site.
98 | MDOT | Naubinway ROW | US 2 | Mackinac | Naubinway |  | 500098 |  | UST | Petroleum products | Low | None | No | Not Liable | NA |  | The MDEQ has notified MDOT that it is not liable. Site is one which was encountered along the Right of Way. The DOT has never owned or operated this site.
99 | MDOC | SPSM-various locations |  | Jackson | Blackman Township | 38000017 | 500099 | State Prison of Southern Mich | Various | Organic compounds | High | None | No | Closure Activities | 2022 |  | Continue monitoring & evaluation for closure.
100 | MDOC | SPSM (asbestos) | 1780 E. Parnall | Jackson | Blackman Township | 38000351 | 500100 | SPSM (asbestos) | Asbestos | Asbestos | Moderate | None | No | Closed | 1998 |  | Asbestos removal completed.
101 | MDOC | Camp Pontiac | 8085 White Lake Rd. | Oakland | Clarkston | 63000948 | 500101 |  | UST | Petroleum products | Low | Moderate | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
102 | MDOC | Camp Tuscola | 2420 Chambers Rd. | Tuscola | Caro | 79000125 | 500102 | Camp Tuscola | UST | Petroleum products | Low | None | No | Closed | 2006 |  | Site delisted as it no longer met criteria in the Part 201 rules.
103 | MDOC | Ionia Reformatory | W. Main St. | Ionia | Ionia | 34000008 | 500103 | Michigan Reformatory | Dump | PNA & lead | Moderate | None | No | Closure Activities | 2023 |  | Draft closure report w/ restriction submitted to EGLE. Waiting on comments from EGLE.
104 | MDHS | Shawono Center | 10 North Howes Lake Rd. | Crawford | Grayling | 20000041 | 500104 | Camp Shawono | UST | Petroleum products | Moderate | None | No | Closure Activities | 2023 |  | EGLE rejected closure and requested VI assessment.
105 | MDTMB | Motor Pool, Capitol Complex | Ottawa and Pine | Ingham | Lansing | 33000586 | 500105 | Motor Pool, Capitol Complex | UST | Petroleum products | Low | None | No | Closure Activities | 2022 2017 |  | Evaluating restrictive closure options.
106 | MDTMB | Surface Storage Dumps | 3369 North Logan St. | Ingham | Lansing | 33000029 | 500106 |  | Dump | Pesticides, heavy metals, organic solvents, phenols and PNAs | Low | None | No | Investigation | Unknown |  | Closed, but evaluating site for additional investigation.
107 | MSP | Alpena State Police Post | 2160 S. State Ave. | Alpena | Alpena | 04000092 | 500107 |  | UST | Petroleum products | Moderate | None | No | Closed | 1998 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
108 | MSP | Wayland State Police Post | 544 N. Main | Allegan | Wayland | 03000117 | 500108 | Wayland State Police Post(MSP) | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
109 | MSP | Bay City State Police Post | 405 N. Euclid Rd. | Bay | Bay City | 09000208 | 500109 | Michigan State Police-Bay City Post | UST | Petroleum products | Low | None | No | Closed | 2004 | Unrestricted Tier II Residential. | Unrestricted Tier II Residential Closure.
110 | MSP | New Buffalo State Police Post | 17651 U.S. 12 | Berrien | New Buffalo | 11000375 | 500110 | New Buffalo State Police Post (MSP) | UST | Petroleum products | Low | High | No | Closed | 2000 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Residential.
111 | MSP | Sault Ste. Marie State Police Post | 3900 I-75 Business Spur | Chippewa | Sault Ste. Marie | 17000103 | 500111 | Michigan State Police Sault Ste. Marie | UST | Petroleum products | Moderate | None | No | In Progress | 2022 |  | Monitoring natural attenuation and closure activities. Triage investigation of groundwater, soil and soil vapor in Oct 2020.
112 | MSP | Gladstone State Police Post | 922 Lake Shore Dr. | Delta | Gladstone | 21000104 | 500112 | Gladstone State Police Post | UST | Petroleum products | Low | None | No | Closed | 1998 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
113 | MSP | State Police Training Academy | 7426 Canal Rd. | Eaton | Lansing | 23000204 | 500113 |  | UST | Petroleum products | Low | None | No | Closure Activities | 2023 |  | Supplemental information with results of quarterly GW monitoring and VI submitted to EGLE.
114 | MSP | Flint State Police Post | G-3478 Corunna Rd. | Genesee | Flint | 25000238 | 500114 | MSP Flint Post | UST | Petroleum products | Low | High | No | In Progress | unknown |  | Site evaluation for abatement/closure. Site transferred to MDOT. On hold.
115 | MSP | Jonesville State Police Post | 476 E. Chicago Rd. | Hillsdale | Jonesville | 30000282 | 500115 | Jonesville State Police Post | UST | Petroleum products | Low | None | No | Closed | 2002 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
116 | MSP | Mt. Pleasant State Police Post | 1011 N. Mission Rd. | Isabella | Mt. Pleasant | 37000064 | 500116 | Michigan State Police Mt.Pleasant | UST | Petroleum products | Low | Moderate | No | Closure Activities | Unknown |  | Closure report submitted to EPA for review/comments. Property sold.
117 | MSP | St. Ignace State Police Post | N430 I-75 | Mackinac | St. Ignace | 49000060 | 500117 |  | UST | Petroleum products | Unknown | None | No | Closure Activities | 2022 |  | Triage investigation of soil, groundwater, and soil gas in Oct. 2020.
118 | MSP | Former Romeo State Police Post | 290 N. Main St. | Macomb | Romeo | 50000065 | 500118 | Former Romeo State Police Post | UST | Petroleum products | Unknown | None | No | OM | 2023 |  | Monitoring. Negotiating with owner restrictive closure. VI investigation was not an issue but additional investigation mybe required.
119 | MSP | Former Warren State Police Post | 30950 Van Dyke Rd. | Macomb | Warren | 50000757 | 500119 | Former Warren State Police Post | UST | Petroleum products | Low | None | No | Closed | 2005 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
120 | MSP | Former Hart State Police Post | 1100 Griswold St. | Oceana | Hart | 64000088 | 500120 | Former Hart State Police Post | UST | Petroleum products | Unknown | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
121 | MSP | Houghton Lake State Police Post | 9011 W. Lake City Rd. | Roscommon | Houghton Lake | 72000060 | 500121 | Houghton Lake State Police | UST | Petroleum products | Low | None | No | Investigation | 2022 |  | Triage investigation of soil, groundwater, and soil gas in Oct. 2020.
122 | MSP | Manistique State Police Post |  | Schoolcraft | Manistique | 77000038 | 500122 |  | UST | Petroleum products | Unknown | None | No | Closed | 1999 | Investigation Showed No Contamination | Investigation showed no contamination.
123 | MSP | Former Owosso State Police Post | 1907 W. Main St. | Shiawassee | Owosso | 78000034 | 500123 | MSP Owosso Post, Former | UST | Petroleum products | High | None | No | Closure Activities | 2022 |  | Additional VI investigation/assessment complete, no risks found.
124 | MSP | Paw Paw State Police Post | 108 W. Michigan | Van Buren | Paw Paw | 80000133 | 500124 |  | UST | Petroleum products | Low | None | No | OM | 2022 |  | Replace damaged MWs. GW monitoring and evaluation of natural attenuation.
125 | MSP | South Haven State Police Post | 720 LaGrange St. | Van Buren | South Haven | 80000151 | 500125 | South Haven State Police Post | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
126 | MSP | Northville State Police Post | 42145 W. Seven Mile Rd. | Wayne | Northville | 82001799 | 500126 |  | UST | Petroleum products | Moderate | None | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
127 | MSP | Pontiac State Police Post | 1295 N. Telegraph Rd. | Oakland | Waterford |  | 500127 |  | UST | Petroleum products | Low | Low | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Residential Tier I closure. Completed with other state funding.
128 | MSP | Ypsilanti State Police Post | 1501 Whittaker Rd. | Washtenaw | Ypsilanti |  | 500128 |  | UST | Petroleum products | Low | None | No | Closed | 1998 | Unrestricted Residential Tier I | Unrestricted Residential Tier I closure. Completed with other state funding.
129 | MDTMB | DMB Plaza Motor Pool | 1200 Sixth St. | Wayne | Detroit | 82001797 | 500129 | DMB Plaza Motor Pool | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Residential Tier I Closure.
130 | MDMVA | Fort Custer |  | Kalamazoo | Augusta | 39000436 | 500130 |  | Shooting range | Unknown | Low | None | No | OM | 2016 | Active Range - Due Care Plan | Active Range - Due Care obligations. Funded by National Guard Bureau.
131 | MDCH | Northville Psychiatric Hospital Asbestos | 41001 Seven Mile Rd. | Wayne | Northville | 82002361 | 500131 |  | Asbestos | Asbestos | Low | None | No | Not Eligible | NA |  | Asbestos Removal Completed. Site owned by Northville Charter Township.
132 | MDTMB | Detroit Plaza State Office Building | 1200 Sixth St. | Wayne | Detroit | 82001797 | 500132 |  | Asbestos | Asbestos | Low | None | No | Not Eligible | NA |  | Demolition activities are not eligible.
133 | Treasury | Denver Township Vacant Land |  | Isabella | Denver Township |  | 500133 |  | Surface spill | Unknown | Low | High | No | Not Eligible | NA |  | Asbestos removal is not eligible.
134 | MDOC | Baraga County Corrections Camp | Rte. 2, Box 720 | Baraga | L'Anse | 07000039 | 500134 | Baraga County Corrections Camp | Various | Petroleum products, dump leachate | Low | None | No | Design | 2023 |  | Site restoration & site evaluation for abatement/closure.
135 | MDOC | Jackson County Landfill | McGill Road | Jackson | Blackman Township | 38000014 | 500135 | Jackson CO LF No 1 | Dump | Dump leachate | High | None | No | OM | Unknown |  | On hold. Cap maintenance and monitoring.
136 | MDOT | Marshall Maintenance Garage | 1242 S. Kalamazoo/ P.O. Box 47 | Calhoun | Marshall | 13000335 | 500136 | Marshall Maintenance Garage(MDOT) | UST | Petroleum products | Moderate | Moderate | No | Closed | 2014 | Tier 1 Restricted | Deed restrictions.
137 | MDNR | Ludington State Park Dump | North M-115, P.O. Box 709 | Mason | Ludington | 53000032 | 500137 | Ludington State Park Dump | Dump | Shop waste | Low | None | Yes | Closed | 1999 | Investigation Revealed No Contamination | Phase II remediaton investigation revealed no contamination that needed addressing.
138 | MDNR | Detour Field Office | P.O. Box 92, M-134 | Mackinac | Detour Village | 17000062 | 500138 | Detour Field Office | UST | Petroleum products | Moderate | None | No | Design | 2020 |  | Prepared and submited NFA with all encompassing RC. NFA rejected by EGLE due to Indoor air concerns. Additional sampling completed to assess indoor air.
139 | MDNR | Onaway State Park | M-211 North, Route 1 | Presque Isle | Onaway | 71000011 | 500139 | Onaway State Park-MDNR | UST | Petroleum products | Low | None | Yes | Closed | 2000 | Unrestricted Residential | Unrestricted Tier I Residential Closure.
140 | MDNR | Proud Lake Recreation Area Dump | 3540 Wixom Road, R#3 | Oakland | Milford | 63005164 | 500140 | Proud Lake Recreation Area Dump | Dump | Domestic/park waste | Low | Low | Yes | No Funding | Unknown |  | Work will resume when funding becomes available.
141 | MDNR | Sleeper State Park Dump | 6573 State Park Rd. | Huron | Caseville | 32000021 | 500141 |  | Dump | Shop and park waste | Unknown | None | Yes | Closed | 1998 | Investigation Revealed No Excess Cont | Site assessment revealed no excess contamination that needed to be addressed.
142 | MDOC | Ryan Regional Correctional Facility | 17600 Ryan Rd., USTs at 5000 Nevada St. | Wayne | Detroit | 82001806 | 500142 | Ryan Regional Correctional Facility | UST | Petroleum products | Unknown | High | No | OM | 2023 |  | Negotiating with the owner of Spartan Metals for access. Sampling and monitoring.
143 | MDMVA | Brodhead Armory | 7600 East Jefferson Ave. | Wayne | Detroit |  | 500143 |  | UST | Petroleum products | Low | None | No | Closed | 2000 | Unrestricted Residential Tier I | Unrestricted Residential Tier I closure. Funded by National Guard Bureau.
144 | MDMVA | Grand Ledge Aviation Support Facility | 16583 S. Wright Rd. | Clinton | Grand Ledge |  | 500144 |  | UST | Petrolem products | Low | None | No | Closed | 1998 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Funded by National Guard Bureau.
145 | MDMVA | Flint Armory | 1101 Cesar Chavez Drive | Genesee | Flint |  | 500145 |  | UST | Petroleum products | Low | None | No | Closed | 2000 | Unrestricted Residential Tier I | Unrestricted Residential Tier 1 closure. Funded by National Guard Bureau.
146 | MDMVA | Montague Armory | 8061 Cook St. | Muskegon | Montague |  | 500146 |  | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Funded by National Guard Bureau.
147 | MDOT | Ivan's Canoe Rental | 11194 US 10 West | Lake | Baldwin | 43000014 | 500147 | Ivan's Canoe Rental | Surface spill | TCE | High | None | No | OM | 2021 |  | TCE concentrations in June 2020 monitoring analytical were below EGLE cleanup criteria. Quarterly monitoring for a No Further Action closure is underway. MDOT funding.
148 | MDOT | Brighton Twp. Facility | 10102 Grand River | Livingston | Brighton Township | 47000127 | 500148 | Brighton Twp. Facility | Surface spill | Unknown | High | None | No | No Funding | Unknown |  | Source of contamination is in dispute. Multiple potential sources.
149 | DCH/DMB | MI Biologic Products Institute | 3500 N. Martin Luther King, Jr. Blvd. | Ingham | Lansing | 33000588 | 500149 | MI Biologic Products Institute | License Decommissioning | Radioactivity | Moderate | High | No | Design | 2016 |  | Excavation of contaminated soils.
150 | MSP | Wakefield State Police Post | 100 Sunday Lake Street | Gogebic | Wakefield | 27000059 | 500150 | Wakefield State Police Post | UST | Petroleum products | Unknown | None | No | Closed | 2015 | Unrestricted Tier I | Unrestricted Tier I Closure
151 | MDCH | Northville Psychiatric Hospital/UST | 41001 Seven Mile Road | Wayne | Northville | 82001807 | 500151 |  | UST | Petroleum products | Low | Low | Yes | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Site owned by Northville Charter Township.
152 | MDCH | Ypsilanti Regional Psychiatric Hospital | 3501 Willis Road | Washtenaw | Ypsilanti | 81000167 | 500152 | Ypsilanti Regional Psychiatric Hospital | UST | Petroleum products | Low | High | No | Closed | 2000 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Toyota Tech Center Redevelopment.
153 | MDMVA | Ironwood Armory | 10333 N. Greenbush St. | Gogebic | Ironwood | 27000040 | 500153 |  | UST | Heating Oil | Low | None | No | Closed | 1999 | Site Delisted | No longer met criteria in rules.
154 | MDMVA | Sault Ste. Marie Armory | 1170 E. Portage Ave. | Chippewa | Sault Ste. Marie |  | 500154 |  | UST | Petroleum products | Low | None | No | Closed | 1994 | Unrestricted Residential Tier I | Unrestricted Residential Tier 1 closure. Funded by National Guard Bureau.
155 | MDMVA | D.J. Jacobetti Home for Veterans | 425 Fisher St. | Marquette | Marquette |  | 500155 |  | UST | Petroleum products | Low | None | No | Closed | 1997 | Unrestricted Residential Tier I | Unrestricted Residential Tier 1 closure. Funded by National Guard Bureau.
156 | MDNR | Ludington State Park UST | M-116 | Mason | Ludington | 53000131 | 500156 |  | UST | Petroleum products | Low | None | Yes | Closed | 1998 | Restricted Tier II Institutional Controls | Tier II residential closure w/deed restrictions limiting groundwater usage. Completed with other state funding.
157 | MDNR | Former DNR Roscommon Field Office | Third and Lake Streets | Roscommon | Roscommon | 72000099 | 500157 | Former DNR Roscommon Field Office | UST | Petroleum products | Low | None | No | Closed | 2001 | Restricted Tier II | Tier II residential closure w/ordinance prohibiting groundwater usage.
158 | MSP | Michigan State Police Aviation Facility | Port Lansing Road | Clinton | Lansing | 19000173 | 500158 | Michigan State Police Aviation Facility | UST | Petroleum products | Moderate | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
159 | MDMVA | Greenville Armory | 319 S. Hillcrest St. | Kent | Greenville |  | 500159 |  | AST | Petroleum products | Low | None | No | Closed | 2000 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Funded by National Guard Bureau.
160 | MDMVA | Camp Grayling-Building 580 |  | Crawford | Camp Grayling |  | 500160 |  | AST | Petroleum products | Low | None | No | Closed | 1999 | Unrestricted Residential Tier I | Unrestricted Residential Tier 1 closure. Funded by National Guard Bureau.
161 | MDTMB | Materials Management Warehouse | 7285 Parsons Drive | Eaton | Lansing | 23000203 | 500161 |  | UST | Petroleum products | Low | Low | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
162 | MDTMB | Newaygo State Police Post | 360 Adams Street | Newaygo | Newaygo | 62000110 | 500162 | Newago State Police Post | UST | Petroleum products | Unknown | None | No | Closed | 2018 |  | Confirmatory sampling. Closure report preparation.
163 | MSP | Bridgeport State Police Post | 2680 Dixie Highway | Saginaw | Bridgeport | 73000556 | 500163 | MSP Bridgeport State Police Post | Surface spill | Petroleum products | Unknown | Low | No | Closure Activities | 2023 |  | Additional investigation/assessment.
164 | MDOC | Ryan Correctional Facility Second UST | 17600 Ryan Road | Wayne | Detroit | 82001800 | 500164 | Ryan Correctional Facility Second UST | UST | Petroleum products | Low | Low | No | No Funding | Unknown |  | Work will resume when funding becomes available.
165 | MDOC | Mound Correctional Facility UST | 17601 Mound Road | Wayne | Detroit | 82001801 | 500165 | Mound Correctional Facility UST | UST | Petroleum products | Low | Low | No | No Funding | Unknown |  | Work will resume when funding becomes available.
166 | MDOC | Cuisino Prison Work Camp | Perry Road | Schoolcraft | Shingleton | 02000056 | 500166 | Cuisino Prison Work Camp | AST | Petroleum products | Moderate | Low | No | OM | 2023 |  | Monitoring of natural attenuation.
167 | MDOC | SPSM Physical Plant-SMR Powerhouse | 4000 Cooper St. | Jackson | Jackson | 38000355 | 500167 | SPSM Physical Plant-SMR Powerhouse | UST | Petroleum products | Low | Low | No | Closed | 2002 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure
168 | MDCH | Northville Psychiatric Hospital/Bldg.15 | 41001 Seven Mile Rd. | Wayne | Northville | 82001793 | 500168 |  | UST | Petroleum products | Low | Low | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Property owned by Northville Charter Township.
169 | MDHS | Adrian Training School | 2300 North Adrian Hwy. | Lenawee | Adrian | 46000179 | 500169 | Adrian Training School | UST | Petroleum products | Moderate | Low | No | Closed | 2014 | Unrestricted Tier 1 Closure | Unrestricted Tier 1 Closure
170 | MDHS | Maxey Training School | 9036 M-36 | Washtenaw | Whitmore Lake | 81000510 | 500170 | Maxey Training School | UST | Petroleum products | Moderate | Low | No | Design | 2023 |  | Free product abatement. Evaluating and addressing the site contamination. Challenge of dealing with the contamination found underneath the building.
171 | MDTMB | Former Mi Liquor Control Warehouse | 2251 Dix Road | Wayne | Lincoln Park | 82001798 | 500171 | Former Mi Liquor Control Warehouse | UST | Petroleum products | Unknown | High | No | Closed | 2002 | Non-Residential Tier I with Deed Restrictions | Closed - Non-Residential Tier I with Deed Restrictions. Delisted. No RC listed in ERNIE.
172 | MDCH | Mt. Pleasant Regional Center | 1400 W. Pickard | Isabella | Mt. Pleasant | 37000134 | 500172 | Mt. Pleasant Regional Center | UST | Petroleum products | Low | Low | No | Closed | 2002 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure. Property owned by City of Mt. Pleasant. Demolition with local, state, and federal funds.
173 | MDCH | Caro Center Power Plant | 2000 Chambers Road | Tuscola | Caro | 79000126 | 500173 | Caro Center Power Plant | UST | Petroleum products | Low | None | No | Design | 2022 |  | Site evaluation for additional excavation/investigative sampling. EGLE issued VI TAPS Review 4/19 recommendation for sampling soil gas/GW.
174 | MDCH | Caro Center Warehouse Bldg. | 2000 Chambers Road | Tuscola | Caro | 79000127 | 500174 | Caro Center Warehouse Bldg. | UST | Petroleum products | Low | None | No | Closed | 2016 |  | Site restoration.
175 | MDTMB | Lansing Energy Center | 7432 Parsons Dr., State Secondary Complex | Eaton | Lansing | 23000188 | 500175 | Energy Center, Lansing | UST | Petroleum products | Low | Low | No | Closed | 2014 | Unrestricted Tier I | Unrestricted Tier I closure.
176 | MDOC | Gilman Technical Rule Violation Center | 8110 E. White Lake Rd. | Oakland | White Lake | 63005867 | 500176 | Gilman TRV | UST | Lead | Low | None | No | Closed | 2015 | Unrestricted Tier I | Unrestricted Tier I Closure.
177 | MDOC | Newberry Correctional Facility | 3001 Newberry Avenue | Luce | Newberry | 48000025 | 500177 | Newberry Correctional Facility | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
178 | MDOC | Camp Pellston | 1500 Robinson and Larks Lake Road | Emmet | Pellston | 24000078 | 500178 | Camp Pellston | UST | Petroleum products | Moderate | Low | No | Closed | 2003 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
179 | MDOC | SPSM Regional Garage | 4000 Cooper Street | Jackson | Jackson | 38000353 | 500179 | SPSM Regional Garage | UST | Petroleum products | Low | None | No | Closed | 2000 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
180 | MDOC | Thumb Correctional Facility | 3225 John Connelly Rd. | Lapeer | Lapeer | 44000271 | 500180 | Thumb Correctional Facility | UST | Petroleum products | Moderate | Low | No | Closed | 2001 | Unrestricted Residential | Unrestricted Tier I Residential Closure.
181 | MDOC | Dale Foltz Training Center Physical Plant | 4000 Cooper Street | Jackson | Jackson | 38000354 | 500181 | Dale Foltz Training Center Physical Plant | UST | Ethylbenzene | Low | None | No | Closed | 2000 | Unrestricted Residential | Unrestricted Tier I Residential Closure.
182 | MDOC | Cassidy Lake SAI |  | Washtenaw | Chelsea | 81000221 | 500182 | Cassidy Lake SAI | UST | Lead | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
183 | MDOC | Camp Branch | 19 4th Street | Branch | Coldwater | 12000092 | 500183 | Camp Branch-Dept of Correction | UST | Petroleum products | Low | None | No | Closed | 2002 | Unrestricted Residential Tier I Residential | Unrestricted Tier I Residential Closure.
184 | MDOC | Camp Waterloo | 6000 Maute Road | Jackson | Grass Lake | 38000352 | 500184 | Camp Waterloo | UST | Lead | Low | None | No | Closed | 2002 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
185 | MDOE | Michigan School for the Deaf and Blind | 715 W. Willow | Ingham | Lansing | 33000585 | 500185 | Michigan School for the Deaf and Blind | UST | Petroleum products | Low | Low | No | Closed | 2003 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
186 | MDOT | Charlotte Maintenance Garage | 905 Paine Drive | Eaton | Charlotte | 23000135 | 500186 | MDOT Charlotte Garage | UST | Petroleum products | Low | None | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
187 | MDOT | Grand Ledge Maintenance Garage | 731 N. Canal Rd. | Eaton | Grand Ledge | 23000136 | 500187 | MDOT Grand Ledge | UST | Petroleum products | Low | None | No | Closed | 2002 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
188 | MDTMB | Clinton Valley Center | 140 Elizabeth Lake Rd. | Oakland | Pontiac | 63005166 | 500188 | Clinton Valley Center | UST | Petroleum products | Low | High | No | Closed | 2001 | Unrestricted Residential Tier I | Unrestricted Tier I Residential Closure.
189 | MDTMB | Former Roosevelt Office Building | SE Corner of Ionia and Seymour | Ingham | Lansing |  | 500189 |  | Other | Lead | Low | High | No | No Funding | Unknown |  | No funding available.
190 | MDCH | Northville Psychiatric Hospital Complex | 41001 7 Mile Road | Wayne | Northville | 82001793 | 500190 |  | Other | Various | Moderate | High | No | Closed | 2008 | Unrestricted Tier I Residential | Unrestricted Tier I Residential Closure. Property owned by Northville Charter Township.
191 | MDMVA | Grand Rapids Veterans Home Pond | 3000 Monroe Ave., NW | Kent | Grand Rapids | 41000629 | 500191 |  | Surface water spill | PNAs | Moderate | None | No | Investigation | 2015 |  | Remedial investigation underway, closure work. Probable ending contract in 2018.
192 | MDCH | Ypsilanti Regional Psychiatric Hospital Oil Spill | 3501 Willis Road | Washtenaw | York Township | 81000167 | 500192 |  | Surface spill | PNAs | Moderate | High | No | No Funding | Unknown |  | No funding available.
193 | DMOC | Western Wayne Correctional Facility | 48401 Five Mile Road | Wayne | Plymouth | 82001486 | 500193 |  | Dump | Arsenic and lead | Low | Low | No | No Funding | Unknown |  | No funding available. Site transferred to Michigan Land Bank for sale.
194 | MDTMB | DMVA Federal Surplus-Combined Support and Maintenance Shop | 3369 North Logan St. | Ingham | Lansing | 33000029 | 500194 | Surface Storage Dump/DMB Federal Surplus | Dump | Inorganics in soils and chlorinated hydrocarbons in groundwater | High | High | No | No Funding | Unknown |  | No funding available.
195 | MDOE | Flint Campus, School for Deaf and Blind | 1667 Miller Road | Genesee | Flint | 972 | 500195 |  | UST | Petroleum products | Unknown | Unknown | No | No Funding | Unknown |  | No funding available.
196 | MDARD | Michigan State Fair Grounds | 1120 W. State Fair | Wayne | Detroit | 82001900 | 500196 |  | UST | Petroleum products | Moderate | Moderate | No | Closed | 2013 | Restricted Tier I Industrial | Restricted Tier I Industrial Closure. Property sold to private development group, no development as of 2/12/2018.
197 | MSP | Ithaca State Police Post | 1876 N. State Road | Gratiot | Ithaca | 29000081 | 500197 |  | UST | Petroleum products | Unknown | Low | No | No Funding | Unknown |  | Site evaluation for abatement/closure.
198 | MDTMB | Bioport | 3500 N. Martin Luther King Blvd. | Ingham | Lansing | 33000588 | 500198 |  | UST | Petroleum products | Unknown | None | No | No Funding | Unknown |  | Being addressed under site #149.
199 | MDCH | Caro Center Grounds Shed | 2000 Chambers | Tuscola | Caro | 79000040 | 500199 |  |  | Petroleum Products | Unknown | None | No | No Funding | Unknown |  | No funding available.
200 | MDOC | Bellamy Creek Correctional Facility | 1727 Bluewater Hwy. | Ionia | Ionia | 91084282 | 500200 |  | Surface Spill | Ethylene Glycol | Medium | None | No | No Funding | Unknown |  | No funding available.
201 | MDMVA | Jackson Armory | 100 Armory Court | Jackson | City of Jackson | 38000108 | 500201 |  | UST | PNAs, arsenic | Low | High | No | Design | 2023 |  | Additional investigation. Evaluating site contamination in deep aquifers. Negotiating with the new owner & EGLE to accept restricted closure.
202 | MDOC | Macomb Correctional Facility | 34625 26 Mile Road | Macomb | Lenox | 35262 | 500202 |  | UST | VOC, PNAs | Medium | Low | No | Closed | 2009 | Unrestricted Tier I Residential | Unrestricted Tier I Residential Closure.
203 | MDOC | Camp Manistique | 401 N Maple St | Schoolcraft | Manistique |  | 500203 |  |  | VOC, PNAs | Medium | High | No | No Funding | Unknown |  | No funding available.
204 | MDMVA | Taylor Armory | 12450 Beech Daly Road | Wayne | Taylor |  | 500204 |  |  |  | Low | Moderate |  | Closed | 2010 | Unrestricted Tier I Residential | Unrestricted Tier I Residential Closure.
205 | MSP | East Lansing State Police Post | 714 S. Harrison Road | Ingham | East Lansing |  | 500205 |  | Leaking Underground Storage Tank |  | Low | Moderate | Low | Closed | 2014 | Unrestricted Tier I | Unrestricted Tier I Closure.
206 | MDOC | Robert Scott Correctional Facility | 47500 Five Mile Road | Wayne | Plymouth Township | 82003202 | 500206 |  |  |  | Low | Unknown |  | Closure Activities | 2022 |  | EGLE rescinded their closure letter dated 3/1/12. Site evaluation for closure.
207 | MDOT | Bergmann Property | I-75 & McNichols Road SW Quadrant, Highland Park | Wayne | Highland Park |  | 500207 |  | Leaking Underground Storage Tank | Polynuclear aromatic hydrocarbons, heavy metals | Low | Unknown | No | Closure Activities | 2014 |  | No funding available.
208 | MSP | Cheboygan State Police Post | 1206 S. Main St. | Cheboygan | Cheboygan | 9477 |  |  | Leaking Underground Storage Tank |  | Low | Low | Low | No Funding | 2023 |  | UST closed in place. Initial assessment report submitted to EGLE.
209 | MSP | Grand Haven State Police Post | 1622 S. Beacon Blvd. | Ottawa | Grand Haven | 9488 |  |  | LUST | Petroleum | Low | Low | Low | No Funding | 2023 |  | Initial Assessment Report filed. UST deregistered.
210 | MSP | Reed City State Police Post | 825 S. Chestnut | Osceola | Reed City |  |  |  | LUST | Petroleum | Low | Low | Low | Closed | 2015 | Unrestricted Tier I | Unrestricted Tier I Closure.
211 | MSP | Rockford State Police Post | 345 Northland Dr., NE | Kent | Rockford |  |  |  | LUST | Petroleum | Low | Low | Low | Closed | 2013 | Unrestricted Tier I | Unrestricted Tier I Closure.
212 | MDOT | Mackinac Bridge Authority | N415 I-75 | Mackinaw | Mackinaw City |  |  |  | LUST | Petroleum | Low | Low | Low | Closed | 2015 | Varied | Release C-1124-85 received a retstricted Tier I Closure on June 15, 2015; Release C-1436-93 received an Unerestricted Type B Residential Closure on April 14, 1994;release C-0087-08 received an Unrestricted Tier II Residential Closure on August 23, 2013
213 | MSP | Bad Axe State Police Post (former) | 675 S. Van Dyke | Huron | Bad Axe | 32000146 |  |  | UST | Petroleum |  | Medium | No | Closed | 2015 |  | Initial Assessment Report submitted to DEQ. UST deregistered.
214 | DTMB | State Secondary Complex Sewers | Lansing Road, Canal Road | Eaton | Lansing | [6 empty] | Low | No | No Funding | 2022 |  | Closed- Evaluate results. Investigate Sediments for mercury contamination.
215 | DMVA | Owosso Armory | 201and 215 North Water Street | Shiawassee | Owosso | 78000159 |  |  | Dump | Metals | Low | High | No | In Progress | 2021 |  | Field work complete, preparing NFA Report.
216 | MDOT | Hack Road Borrow Pit Pond | NW of Hack Rd. and Wolf Road | Saginaw | Saginaw |  |  |  | Barrels | Unknown | Unknown | Low | Low | No Funding | 2017 |  | Seeking funding for drum removal contactor.
217 | DNR | Au Gres State Harbor | 201 S. Water Street, Au Gres | Arenac | Au Gres | 20284 |  |  | LUST | VOCs | Low | Low | High | No Funding | 2022 |  | Preparation of Closure report/Monitoring well abandonment activities.
218 | MDOC | Michigan Reformatory Power Plant | 1342 West Main Street | Ionia | Ionia |  |  |  | LUST | Petroleum | Low | Low | Low | No Funding | 2022 |  | Site evaluation for abatement/closure.
219 | DMVA | Grayling Army Airfield | Old 27 Building 176 | Crawford | Grayling | 20000012 |  | Camp Grayling Army Airfield | Surface Spill/LUST | Petroleum, other |  |  |  | In Progress | 2025 |  | Remedial Investigation phase.
220 | MSP | Lakeview State Police Post | 10300 Edmore Road | Kent | Lakeview | 9496 |  |  |  | Petroleum | Unknown | Unknown | Unknown | No Funding | 2020 |  | Site remediated. Monitoring/Closure activities
221 | MDNR | Black River Marina | 8091 Viau Road | Cheboygan | Cheboygan | 50005916 |  |  |  | Petroleum | Unknown | Unknown | Unknown | No Funding | Unknown |  | Work will begin when funding becomes available.