## overall spend by category
Flint Financial Summary by Outcome Category - UNAUDITED
Cumulative Expenditures through Sept 30, 2016 | Flint Water Appropriations | Flint Specific Appropriation Spent | Flint Specific Encumbrances / Obligations | % of Appropriation Expended & Encumbered/ Obligated | Non-Flint Specific Appropriations Spent | Component Unit Spending | Total Spent / Encumbered / Obligated
Safe Drinking Water | 88279400 | 27368985.61 | 29754268.72 | 64.71% | 15256957 | 39415 | 72419626.33
Food and Nutrition | 19654800 | 1498437.56 | 3021427.22 | 23% | 100289 | 0 | 4620153.78
Social Development and Well-Being | 66937700 | 4614723.3294 | 21368221.69 | 38.82% | 2696217 | 0 | 28679162.0194
Physical Well-Being | 16478100 | 3111547.96 | 6085724.31 | 55.82% | 6410352 | 249 | 15607873.27
Water Bill Credits | 42750000 | 31080157 | 0 | 72.7% | 0 | 0 | 31080157
Economic Development | 0 | 0 | 0 | n/a | 13127544 | 4489536 | 17617080
Totals | 234100000 | 67673851.4594 | 60229641.94 | 54.64% | 37591359 | 4529200 | 170024052.3994
As part of the ongoing effort for full transparency, contents of this report represent the State's attempt to capture all expenditures for the Flint water crisis. This report will be updated every two weeks and will evolve to include more comprehensive data.
Note: Individual amounts may not add to totals due to rounding; Non-Flint specific includes internal transfers and work projects

## overall spend by department
Flint Financial Summary by Department - UNAUDITED
| PA 143 of 2015 | PA 3 of 2016 | PA 24 of 2016 | PA 268 of 2016 | PA 249 of 2016 | Non-Flint Specific Appropriations | Component Unit | Department Total
Agriculture and Rural Development | 0 | 0 | 0 | 0 | 0 | 450834 | 0 | 450834
Attorney General | 0 | 0 | 0 | 1300000 | 0 | 1549765 | 0 | 2849765
Civil Rights | 0 | 0 | 0 | 0 | 0 | 37558 | 0 | 37558
Corrections | 0 | 0 | 0 | 0 | 0 | 1586438 | 0 | 1586438
Education | 0 | 2685000 | 0 | 6639 | 0 | 45289 | 0 | 2736928
Environmental Quality | 7300000 | 4828958 | 0 | 32836322 | 0 | 3426494 | 0 | 48391774
Health and Human Services | 1949129 | 15420056 | 0 | 14760522 | 0 | 9539209 | 0 | 41668916
Insurance and Financial Services | 0 | 0 | 0 | 0 | 0 | 5659 | 0 | 5659
Licensing and Regulatory Affairs | 199606 | 1254709 | 0 | 0 | 0 | 0 | 0 | 1454315
Military and Veterans Affairs | 0 | 2476834 | 0 | 0 | 0 | 65111 | 0 | 2541945
Natural Resources | 0 | 0 | 0 | 250000 | 0 | 1262 | 0 | 251262
School Aid | 0 | 0 | 0 | 0 | 9200000 | 0 | 0 | 9200000
Secretary of State | 0 | 0 | 0 | 0 | 0 | 3131 | 0 | 3131
State Police | 0 | 7043 | 0 | 2297428 | 0 | 1689972 | 0 | 3994443
Talent and Economic Development | 0 | 0 | 0 | 0 | 0 | 13127544 | 4529200 | 17656744
Technology, Management and Budget | 0 | 0 | 0 | 0 | 0 | 3049303 | 0 | 3049303
Transportation | 0 | 0 | 0 | 0 | 0 | 694135 | 0 | 694135
Treasury | 0 | 0 | 30000000 | 1131247 | 0 | 2319655 | 0 | 33450902
Total Resource Utilization per Appropriation | 9448735 | 26672600 | 30000000 | 52582158 | 9200000 | 37591359 | 4529200 | 170024052
Note: Individual amounts may not add to totals due to rounding; Non-Flint specific includes internal transfers and work projects

## spend by department and outcome
Flint Financial Summary by Department and by Outcome Category - UNAUDITED
|  |  | PA 143 of 2015 | PA 3 of 2016 | PA 24 of 2016 | PA 268 of 2016 | PA 249 of 2016 | Non-Flint Specific | Component Unit | Department Total
Safe Drinking Water
|  | Agriculture and Rural Development | [5 empty] | 450834 |  | 450834
|  | Attorney General |  |  |  | 0 |  |  |  | 0
|  | Civil Rights | [5 empty] | 11297 |  | 11297
|  | Corrections | [5 empty] | 1586438 |  | 1586438
|  | Education | [7 empty] | 0
|  | Environmental Quality | 7300000 | 4828958 |  | 32836322 |  | 3426494 |  | 48391774
|  | Health and Human Services | 1000000 | 4612800 |  |  |  | 1959325 |  | 7572125
|  | Insurance and Financial Services | [7 empty] | 0
|  | Licensing and Regulatory Affairs | 199606 | 1254709 | [5 empty] | 1454315
|  | Military and Veterans Affairs |  | 2476834 |  |  |  | 65111 |  | 2541945
|  | Natural Resources |  |  |  | 250000 |  | 1262 |  | 251262
|  | Secretary of State | [5 empty] | 3131 |  | 3131
|  | State Police |  | 7043 |  | 2297428 |  | 1689972 |  | 3994443
|  | Talent and Economic Development | [6 empty] | 39415 | 39415
|  | Technology, Management and Budget | [5 empty] | 3049303 |  | 3049303
|  | Transportation | [5 empty] | 694135 |  | 694135
|  | Treasury |  |  |  | 51090 |  | 2319655 |  | 2370745
Total Spent - Safe Drinking Water | Safe Drinking Water Total |  | 8499606 | 13180344 | 0 | 35434840 | 0 | 15256957 | 39415 | 72411162
Food and Nutrition
|  | Education |  | 140000 |  | 6639 |  | 45289 |  | 191928
|  | Health and Human Services |  | 2641689 |  | 1740000 |  | 55000 |  | 4436689
| Food and Nutrition Total |  | 0 | 2781689 | 0 | 1746639 | 0 | 100289 | 0 | 4628617
Social Development and Well Being
|  | Attorney General |  |  |  | 1300000 |  | 1549765 |  | 2849765
|  | Civil Rights | [5 empty] | 26261 |  | 26261
|  | Education |  | 2225000 | [5 empty] | 2225000
|  | Health and Human Services |  | 4407945 |  | 8850000 |  | 1114532 |  | 14372477
|  | Insurance and Financial Services | [5 empty] | 5659 |  | 5659
|  | School Aid |  |  |  |  | 9200000 |  |  | 9200000
| Social Development and Well-Being Total |  | 0 | 6632945 | 0 | 10150000 | 9200000 | 2696217 | 0 | 28679162
Physical Well Being
|  | Education |  | 320000 | [5 empty] | 320000
|  | Health and Human Services | 949129 | 3757622 |  | 4170522 |  | 6410352 |  | 15287625
|  | Talent and Economic Development | [6 empty] | 249 | 249
| Physical Well-Being Total |  | 949129 | 4077622 | 0 | 4170522 | 0 | 6410352 | 249 | 15607874
Water Bill Credits
|  | Treasury |  |  | 30000000 | 1080157 |  |  |  | 31080157
| Water Bill Credits Total |  | 0 | 0 | 30000000 | 1080157 | 0 | 0 | 0 | 31080157
Economic Development
|  | Talent & Economic Development | [5 empty] | 13127544 | 4489536 | 17617080
| Economic Development Total |  | 0 | 0 | 0 | 0 | 0 | 13127544 | 4489536 | 17617080
Grand Total |  |  | 9448735 | 26672600 | 30000000 | 52582158 | 9200000 | 37591359 | 4529200 | 170024052
Note: Individual amounts may not add to totals due to rounding; Non-Flint specific includes internal transfers and work projects

## Flint Water Exp & Act Track
| Report Name |  |  | Flint Water Emergency - Financial and Activities Tracking and Reporting Document | [6 empty] | Food = Food and Nutrition |  | Water = Safe Drinking Water
| Report Due Date |  |  | 2016-11-28 | [6 empty] | Physical = Physical Well-Being |  | Econ Develop = Economic Development
| Report Post Date |  |  | 2016-11-30 | [6 empty] | Social = Social Development and Well-Being
| Reporting Period |  |  | Cumulative through September 30, 2016
| Spending Authority, Purpose and Description | [5 empty] | Encumbered/Obligated (Gross Only) |  | Expended Through End of Reporting Period |  |  | Appropriated Amount |  | Response Activities
# | Dept | Fiscal Year | Funding Source | Outcome Category | Description of Purchases or Services | Contractor, Grantee or Vendor Name(s) | Obligated | Encumbered | State GF | Gross | Spent/ Encumbered/ Obligated | State GF | Gross | % Spent / Encumbered / Obligated | Output Description | Planned Outputs | Cumulative Outputs | Outcome to Date
1 | MDARD | 2016 | Current Approps | Water | Agency/SEOC support costs |  |  |  | 65068 | 100689 | 100689 |  | 0 |  | Provide administrative support | As needed | Approximately 1,430 hours spent supporting the Flint water emergency effort | 100% of requests met
2 | MDARD | 2016 | Current Approps | Water | Animal Health Programs - Companion Animal Testing and Outreach |  |  |  | 50241 | 50241 | 50241 |  | 0 |  | Facilitate testing animals exposed to City of Flint water for lead toxicity | Respond to citizen requests | 332 animals with completed test results | Of the 332 animals with complete results: 328 animals tested negative (<50 ppb) 3 animals tested exposed/probable (50-399 ppb) 1 animal was retested due to confirmed toxicity at another lab ( >/= 400 ppb)
3 | MDARD | 2016 | Current Approps | Water | Water Inspections at Food Establishments. Nutrition Support and Coordination |  |  |  | 296909 | 299904 | 299904 |  | 0 |  | Conduct assessments to determine compliance with water requirements, conduct enforcement, complete follow up visits for non-compliance due to high lead levels, collect water samples | Conduct assessments of food establishments connected to the Flint water supply | Completed 389 initial assessments, Completed 268 follow up assessments due to non-compliance or high lead levels, 448 water samples collected, 446 samples tested; 2 samples pending | Of the 446 samples tested: 322 were non-detect (<1 ppb) 73 were in the range of 1-3.99 ppb 35 were in the range of 4-16ppb 16 were > 15 ppb
4 | AG | 2016 | Current Approps | Social | Legal Services | Flood Law, PLLC |  |  |  | 991069 | 991069 |  | 0 |  | Comprehensive written report | Comprehensive written report | Investigation is Ongoing | Investigation is Ongoing
5 | AG | 2016 | PA 268 of 2016 | Social | Drinking water declaration of emergency legal services | Flood Law, PLLC |  |  |  | 1300000 | 1300000 | 0 | 1300000 | 100% | Comprehensive written report | Comprehensive written report | Investigation is Ongoing | Investigation is Ongoing
6 | AG | 2016 | Current Approps | Social | Agency Support Costs | AT&T;Cellco Partnership; CMP Distributors; Epoch Hospitality; Grand Traverse Pie Co of Lansing; MI Police Equip; Russell Video Services; The Regents of U-M; West Publishing; William Whitbeck; |  | 130333 | 403504.23 | 428363.23 | 558696.23 |  | 0 |  | Comprehensive written report | Comprehensive written report | Investigation is Ongoing | Investigation is Ongoing
7 | MDCR | 2016 | Current Approps | Water | Agency/SEOC Support costs |  |  |  | 11296.5 | 11296.5 | 11296.5 |  | 0 |  | Provide administrative support | As needed |  | 100% of requests met
8 | MDCR | 2016 | Current Approps | Social | Communications with non English speakers to ensure they have appropriate health information; hearing & meetings related to housing problems due to water situation & potential gaps in services. |  |  |  | 26260.95 | 26260.95 | 26260.95 |  | 0 |  | Provide administrative & organizational support | As needed |  | 100% of requests met
9 | DOC | 2016 | Current Approps | Water | Agency/SEOC Support Costs | Penske Truck / Michigan State Industries |  | 0 | 1536618 | 1586438 | 1586438 |  | 0 |  | Provide Labor and Administrative Support | As needed | Approximately 48745 hours spent supporting the Flint water emergency effort | 100% of requests met
10 | DOC | 2016 | DECF | Water | Reimbursement from DECF |  |  |  | -755148.73 | -755148.73 | -755148.73 |  | 0
11 | MDE | 2016 | PA 3 of 2016 | Food | Fruits, vegetables, low-fat dairy | Genesee Intermediate School District (GISD) | 0.22 |  | 139999.78 | 139999.78 | 140000 | 140000 | 140000 | 100% | Provide fruits/vegetables to children exposed to lead | Establish 19 sites to distribute fruits and vegetables | Daily snacks made available to approximately 8,319 students each day the school was in operation | Provide children exposed to lead with the fruits/vegetables known to absorb lead
12 | MDE | 2016 | PA 3 of 2016 | Physical | Flint school district nurses - 9 positions | Flint Schools | 46425.81 |  | 273574.19 | 273574.19 | 320000 | 320000 | 320000 | 100% | Provide additional nurses in Flint Schools | Contract with 9 nurses | Contracted with 9 nurses | Provide nurses in the Flint Schools to address medical concerns related to lead exposure
13 | MDE | 2016 | PA 3 of 2016 | Social | Grant to GISD to provide Early On Services to children ages 0-3 exposed to lead. | Genesee Intermediate School District (GISD) | 651273.69 |  | 1573726.31 | 1573726.31 | 2225000 | 2225000 | 2225000 | 100% | Provide Early On services to children in the affected area | Hire 2 Early On consultants to provide evaluation services | Hired 2 consultants | Provide Early On Services to children ages 0-3 exposed to lead
14 | MDE | 2016 | Current Approps | Food | USDA Expanded Fresh Fruit/Vegetable Funding to Flint Schools | G | 0 | 0 | 0 | 45289 | 45289 |  | 0 |  | # of children served | Snacks made Available to all students each day of service | 1197 | Made 1,197 snacks to students (cumulative for four schools). See "FFVP" tab for more information
15 | MDE | 2016 | PA 268 of 2016 | Food | Nutrition Assistance for Children of Flint | Will add info in subsequent reports | 0 |  | 6639.04 | 6639.04 | 6639.04 | 6000000 | 9500000 | 0.06988% | Will add info in subsequent reports | Will add info in subsequent reports | 4,748 meals served | 4,748 meals served
16 | MDE | 2016 | PA 268 of 2016 | Social | Child care assistance for Flint children (0-3) | Will add info in subsequent reports | 0 |  | 0 | 0 | 0 |  | 8100000 | 0% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
17 | MDE | 2016 | PA 268 of 2016 | Social | CCDF reserve for Flint day care needs | Will add info in subsequent reports | 0 |  | 0 | 0 | 0 |  | 8000000 | 0% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
18 | MDE | 2016 | DECF | Food | Reimbursement from DECF | NA |  |  | -8463.5 | -8463.5 | -8463.5 |  | 0
19 | MDE | 2017 | PA 268 of 2016 | Social | Child care assistance for Flint children (0-3) | Will add info in subsequent reports | 0 |  | 0 | 0 | 0 |  | 8050100 | 0% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
20 | DEQ | 2016 | PA 143 of 2015 | Water | Re-connection to Great Lakes Water Authority System (1/2 costs for 9 months beginning October 2015 through June 2016) | City of Flint |  |  | 5000000 | 6000000 | 6000000 | 5000000 | 6000000 | 100% | Re-connect to Great Lakes Water Authority System | Re-connect to Great Lakes Water Authority System | Re-connect to Great Lakes Water Authority System | City of Flint remained on the Great Lakes Water Authority System
21 | DEQ | 2016 | PA 143 of 2015 | Water | Water Sample Testing | NA |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 100% | Provide Testing of Water Samples | Provide About 38,400 Water Sample Tests | Over 25,300 Water Samples Have Been Analyzed, Expenditures Are Those That Have Been Billed to Date | Sampling Results for Sentinel Sites & Residential: 92% of Samples Below Action Level of 15 PPB 8% of Samples Above Action Level of 15 PPB
22 | DEQ | 2016 | PA 143 of 2015 | Water | Technical Assistance and Coordination | NA |  |  | 300000 | 300000 | 300000 | 300000 | 300000 | 100% | Provide Technical Assistance and Coordination for Response Efforts | Provide Assistance Through End of FY16 | Provided Technical Assistance and Coordination for Response Efforts through September 2016 | Technical Assistance and Coordination for Response Efforts to City of Flint in Coordination with EPA
23 | DEQ | 2016 | PA 3 of 2016 | Water | Water System Needs and Plumbing Assessments | NA |  | 153087 | 1779132 | 1779132 | 1932219 | 2553000 | 2553000 | 75.68% | Assist with Water System Needs and Plumbing Assessments within City of Flint Homes for Line Material Determination (ex. Lead) | Complete Plumbing Assessments; Assist With Replacement of 33 Lines | Approximately 2,410 plumbing assessments completed; 33 lines have been replaced | 118 Lead Lines Have Been Identified
24 | DEQ | 2016 | PA 3 of 2016 | Water | Water System Needs - KWA Back Up Pipe | NA | 2000000 |  |  | 0 | 2000000 | 2000000 | 2000000 | 100% | Support the Construction of a 36 Inch Back Up Pipe | 36 Inch Back Up Pipe Will Be Constructed
25 | DEQ | 2016 | PA 3 of 2016 | Water | Infrastructure Integrity Study Using Outside Experts | NA |  | 201510 | 220950 | 220950 | 422460 | 423000 | 423000 | 99.87% | Complete an Infrastructure Integrity Study Using External Experts | Complete an Infrastructure Integrity Study to Evaluate System | A draft report for the infrastructure integrity study has been completed | A draft report for the infrastructure integrity study has been completed
26 | DEQ | 2016 | PA 3 of 2016 | Water | Lab and Testing Costs | NA |  |  | 474279 | 474279 | 474279 | 774000 | 774000 | 61.28% | Provide Additional Residential Water Sample Testing | Provide about 35,100 Water Sample Tests | Over 25,300 Water Samples Have Been Analyzed, Expenditures Are Those That Have Been Billed to Date | Sampling Results for Sentinel Sites & Residential: 92% of Samples Below Action Level of 15 PPB 8% of Samples Above Action Level of 15 PPB
27 | DEQ | 2016 | PA 3 of 2016 | Water | Assistance to the City of Flint on Corrosion Control |  |  |  |  | 0 | 0 | 36500 | 36500 | 0% | Assistance to the City of Flint on Corrosion Control | Provide Assistance to the City of Flint on Corrosion Control
28 | DEQ | 2016 | Current Approps | Water | Technical Expertise for Testing, Sampling, Administration, Evaluation | NA |  |  | 792365 | 3426494 | 3426494 |  | 0 |  | Provide Technical Expertise for Testing, Sampling, Administration, Evaluation | Assistance Will Continue | Provided Technical Expertise for Testing, Sampling, Administration, Evaluation for 49,376 Hours | 100% of Request Met to Date for Technical Expertise in Testing, Sampling, Administration, Evaluation
29 | DEQ | 2016 | DECF | Water | Reimbursement from DECF | NA |  |  | -132490.41 | -792870.41 | -792870.41 |  | 0 |  | Reimbursement from the Disaster Emergency Contingency Fund | Reimbursement from the Disaster Emergency Contingency Fund | Reimbursement from the Disaster Emergency Contingency Fund | Reimbursement from the Disaster Emergency Contingency Fund
30 | DEQ | 2016 | PA 268 of 2016 | Water | Re-connection to Great Lakes Water Authority System (July 2016 - September 2016) | Great Lakes Water Authority |  |  | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 100% | Maintain Connection to Great Lakes Water Authority System July 2016 to September 2016 | Maintain Connection to Great Lakes Water Authority System July 2016 to September 2016 | City of Flint remained on the Great Lakes Water Authority System | City of Flint remained on the Great Lakes Water Authority System
31 | DEQ | 2016 | PA 268 of 2016 | Water | Drinking Water Emergency Response Team | NA |  |  | 1736322 | 1736322 | 1736322 | 2250000 | 2250000 | 77.17% | Provide Technical Expertise for the Response Efforts | Technical Expertise Will Be Provided for the Response Efforts | Technical Expertise Was Provided Through the Emergency Declaration | Technical Expertise Was Provided Through the Emergency Declaration
32 | DEQ | 2016 | PA 268 of 2016 | Water | Replacement of lead service lines for high risk, high hazard homes in Flint |  | 25000000 |  |  | 0 | 25000000 | 25000000 | 25000000 | 100% | Support the Replacement of 5,000 Lines | Estimated 5,000 Lines Will be Replaced
33 | DEQ | 2016 | PA 268 of 2016 | Water | Water system needs |  | 2200000 |  |  | 0 | 2200000 | 2200000 | 2200000 | 100% | Support the Construction of a 36 Inch Back Up Pipe | 36 Inch Back Up Pipe Will Be Constructed
34 | DEQ | 2017 | PA 268 of 2016 | Water | Re-connection to Great Lakes Water Authority System (October 2016 - December 2016) |  |  |  |  | 0 | 0 | 3900000 | 3900000 | 0% | Maintain Connection to Great Lakes Water Authority System October 2016 to December 2016 | Maintain Connection to Great Lakes Water Authority System October 2016 to December 2016
35 | DEQ | 2017 | PA 268 of 2016 | Water | Drinking Water Emergency Response Team |  |  |  |  | 0 | 0 | 1500000 | 1500100 | 0% | Provide Technical Expertise for Response Efforts | Technical Expertise Will Be Provided for the Response Efforts
36 | DHHS | 2016 | PA 3 of 2016 | Food | Genesee County food safety inspections | Genesee County Health Department | 0 |  | 200000 | 200000 | 200000 | 200000 | 200000 | 100% | Conduct assessments to determine compliance with water requirements, conduct enforcement, complete follow up visits for non-compliance due to high lead levels, collect water samples | 212 Food Service Establishments for continued compliance checks | Completed 276 assessments to verify continued compliance, 0 water samples collected | 276 establishments were found in compliance
37 | DHHS | 2016 | PA 3 of 2016 | Food | Nutrition Education | Genesee County Health Department |  | 0 | 0 | 67509.24 | 67509.24 |  | 120000 | 56.26% | Provide health education and outreach initiatives | Number of health education and outreach initiatives | The health educator currently attends at least 5 meetings/events per week and is responsible for the dissemination of health education materials. | Health Educator and Clerical positions filled and started in mid-May
38 | DHHS | 2016 | PA 3 of 2016 | Food | Food Bank Resources | Food Bank of Michigan | 0 |  | 1037200 | 1037200 | 1037200 | 1037200 | 1037200 | 100% | Deliver fresh produce, eggs or dairy products to affected locations | Deliver healthy lead mitigating foods to all residents in Flint regardless of income | 2,176,175 million pounds of food delivered | Deliveries made to 32,324 families through Oct 2016.
39 | DHHS | 2016 | PA 3 of 2016 | Food | Nutritional Education | Michigan Department of Education | 872000 |  | 0 | 0 | 872000 |  | 872000 | 100% | Provide nutrition education to 5-10 year olds | Number of 5-10 year olds provided with nutrition education |  | Interagency Agreement has been finalized to transfer funds from DHHS to MDE. MDE is working to finalize contracts with YMCA and Food Bank of Eastern Michigan to provide additional fresh fruits and vegetables at snacks in the at risk after school program in conjunction with nutrition education for the children and families. The Food Bank will also enhance their weekend backpack program for children affected by the water crisis.
40 | DHHS | 2016 | PA 3 of 2016 | Food | Lactation Consultant | Genesee County Health Department | 78471 |  | 6509 | 6509 | 84980 | 30000 | 85000 | 99.98% | Provide counseling on breastfeeding | Number of women who breastfeed | A health educator was hired to expand training and outreach | Activities will expand to include education and training to health care professionals and clinics, working with local breastfeeding coalitions, and providing linkages to community resources.
41 | DHHS | 2016 | PA 3 of 2016 | Physical | Children's Healthcare Access Project (CHAP) | Greater Flint Health Coalition |  |  | 315914.07 | 315914.07 | 315914.07 | 200000 | 200000 | 158% | Assist children with establishing primary care medical home | 700 children assisted with establishing primary care medical home | There were 344 children served in Sept and 345 in Oct. Total children served from May-Oct is 2,065 | Funding has facilitated over a 400% increase in monthly volume
42 | DHHS | 2016 | PA 3 of 2016 | Physical | Child and Adolescent Health Centers | Michigan Primary Care Association | 636149 |  | 13851.26 | 13851.26 | 650000.26 | 650000 | 650000 | 100% | Establish CAHC satellite locations in elementary schools | Three CAHC satellite locations established in elementary schools | 1.) Richfield (K-6th Grade), agreement between U of M and Richfield signed, renovations underway; some staff have been hired, 2.) Kearsley High School, agreement between U of M and Kearsley in process, renovations starting | 3. Carman-Ainsworth are currently under discussion with UM to start CAHCs. Northwestern High School had an existing center that is currently undergoing renovations and updates
43 | DHHS | 2016 | PA 3 of 2016 | Social | Pathways to Potential Expansion | N/A |  |  | 217944.85 | 217944.85 | 217944.85 | 720000 | 720000 | 30.27% | Place additional Pathways to Potential workers in Flint schools | Six Pathways to Potential workers hired and placed in Flint schools | Six Pathways to Potential workers hired and placed in Flint schools | Six Pathways to Potential workers began work on May 2, 2016. 3 workers are located in Flint Northwestern High School and 3 at Southwestern High School.
44 | DHHS | 2016 | PA 3 of 2016 | Social | Crisis Counseling | Genesee Health System |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 100% | Provide psychological first aid and crisis counseling to individuals or families | Number of individuals or families provided psychological first aid and crisis counseling | 1,516 contacts were made in Sept and 1,973 were made in Oct. 5,060 contacts have been made in total | Crisis counseling/outreach is being delivered in community outreach locations by professional and para-professional staff trained in models such as mental health first aid and psychological first aid. Additionally, educational support is provided as needed, regarding community resources, including referrals to TCM< and assistance with Medicaid applications. These contacts are unscheduled, done in the community, are outreach in nature, and no identification of the served individual is required. These contacts can be completely anonymous.
45 | DHHS | 2016 | PA 3 of 2016 | Social | Case Management, Care Coordination, Crisis Services, Behavioral Health and Developmental Services | Genesee Health System | 3290000 |  |  | 0 | 3290000 | 755000 | 3290000 | 100% | Provide Case Management, Care Coordination, Crisis Services, Behavioral Health and Developmental Services to individuals and families | Number of individuals or families served/treated | 60 individuals were provided targeted case management services in Sept and 72 were provided targeted case management in Oct | Coverage of Targeted Case Management Services for Medicaid Beneficiaries who were served by the Flint water system began May 9, 2016.
46 | DHHS | 2016 | PA 3 of 2016 | Social | Michigan Child Care Collaborative (MC3) | University of Michigan | 146743 |  | 253257.41 | 253257.41 | 400000.41 | 200000 | 200000 | 200% | Provide support to primary care providers and pediatric offices and clinical services to children and families in Genesee County | Number of Primary Care Physician and pediatric offices supported for emotional and behavioral health services for children and families | 42 Primary Care providers have been enrolled in MC3 in Flint. Meetings to plan for enrollment of providers at Mott Children's Health Center and at Hurley Children's Center have been held. Meetings continue with local stakeholders (CHAP, Greater Flint Health Coalition). Phone consultation and group consultation to primary care providers has begun as well as telepsychiatric assessment of children. | Funds have been received by the University of Michigan and program is underway. MC3 has provided behavioral health consultation to 6 primary care providers as well as a telepsychiatric assessment and 2 provider group consultations as of October 31, 2016.
47 | DHHS | 2015 | AY15 Work Project | Water | Purchase water resources | Home Depot |  |  | 1137055 | 1137055 | 1137055 |  | 0 |  | Provide and distribute water filters, faucet mounts, replacement cartridges, and bottled water | Number of water filters, faucet mounts, replacement cartridges, and bottled water distributed | 51,727 filter systems and 1,600 replacement filters provided | Completed Water filters, faucet mounts, replacement cartridges and bottles have been delivered and are being distributed from warehouses. The Federal Emergency Management Agency has taken over coordination and purchasing of water resources
48 | DHHS | 2016 | PA 143 of 2015 | Water | Purchase water resources | Home Depot |  |  |  | 1000000 | 1000000 |  | 1000000 | 100% | Provide and distribute water filters, faucet mounts, replacement cartridges, and bottled water | Number of water filters, faucet mounts, replacement cartridges, and bottled water distributed | 127,680 cases of water, 22,000 filter systems, and 375 replacement filters provided | Completed Water filters, faucet mounts, replacement cartridges and bottles have been delivered and are being distributed from warehouses. The Federal Emergency Management Agency has taken over coordination and purchasing of water resources
49 | DHHS | 2016 | PA 3 of 2016 | Water | Purchase water resources | Home Depot |  |  | 4612800 | 4612800 | 4612800 | 4612800 | 4612800 | 100% | Provide and distribute water filters, faucet mounts, replacement cartridges, and bottled water distributed | Number of water filters, faucet mounts, replacement cartridges, and bottled water distributed | 186,691 filter systems and 248,390 replacement filters provided | Completed Water filters, faucet mounts, replacement cartridges and bottles have been delivered and are being distributed from warehouses. The Federal Emergency Management Agency has taken over coordination and purchasing of water resources
50 | DHHS | 2016 | PA 3 of 2016 | Physical | Lead Abatement | Southeastern Michigan Health Association | 771126 | 247783 |  | 491091 | 1510000 |  | 1510000 | 100% | Provide for home abatement | Number of homes that have begun abatement process (Enrolled) | 56 | 19 Flint homes are currently in the lead abatement process. 37 Flint homes have been abated and cleared for re-entry.
51 | DHHS | 2016 | PA 143 of 2015 | Physical | Environmental Blood Lead Investigations | ETC, Inc. | 110000 | 16111.5 | 148888.5 | 148888.5 | 275000 | 275000 | 275000 | 100% | Perform elevated blood level investigations for sources of lead-based paint in children less than age 6 and pregnant females with confirmed EBL levels and adults with confirmed EBL levels | Number of homes investigated/ tested | 161 | Public Health Service nurses are being trained by MDHHS staff in EBL Environmental Investigation (EI) Protocol. The overall cancellation rate is approximately 30%.
52 | DHHS | 2016 | PA 3 of 2016 | Physical | Environmental Blood Lead Investigations | ETC, Inc. |  | 90000 | 200000 | 200000 | 290000 |  | 90000 | 322.2% | Perform elevated blood level investigations for sources of lead-based paint in children less than age 6 and pregnant females with confirmed EBL levels and adults with confirmed EBL levels | Number of homes investigated/ tested |  | Contract amendment to add funding has been executed
53 | DHHS | 2016 | PA 3 of 2016 | Physical | Medical Team to Assess Linkages to Legionnaire's | Wayne State University | 16408 |  | 258591.96 | 258591.96 | 274999.96 | 275000 | 275000 | 100% | Conduct linkage assessments | Number of linkage assessments conducted |  | Phase 1 has been completed. Phase 2 of the contract started on June 1, 2016. Phase 1 was completed and approved on 8/11/16.
54 | DHHS | 2016 | PA 3 of 2016 | Physical | Epidemiologists services | Michigan Public Health Institute | 22571 |  |  | 105636.48 | 128207.48 |  | 126500 | 101.3% | Conduct blood level analyses | Number of requests for blood level analyses | 168 data requests and 14 Data Use Agreements have been processed. | Contractors have been hired and working with MDHHS staff. Two new positions have been filled. Eight (8) weekly data reports are being generated (ongoing). Since February 1, 2016, 168 data requests, 23 information requests, and 14 Data Use Agreements have been processed.
55 | DHHS | 2016 | PA 3 of 2016 | Physical | Adult Blood Lead Epidemiology and Surveillance (ABLES) | MSU |  |  |  | 18500 | 18500 |  | 18500 | 100% | Conduct interviews with individuals with blood lead levels at or above 5 in the City of Flint. Surveillance database will be modified to reflect data collection. Ongoing epidemiologic analyses of the data will be completed | # of interviews conducted | 44 | 44 interviews have been completed. 17 homes referred for environmental investigation.
56 | DHHS | 2016 | PA 143 of 2015 | Physical | Epidemiologists services and Epidemiology Administration and toxicologists | Michigan Public Health Institute and state staff |  |  | 249128.7 | 249128.7 | 249128.7 | 150000 | 150000 | 166.1% | Provide technical expertise for environmental investigations and health education. | Number of reports and health education products. | 32 | Completed For ongoing updates please see line 72 The Cumulative Output number is a reports or health education materials that Toxicology and Response provided technical expertise for either health education or toxicology. Contract has been executed and staff have been hired
57 | DHHS | 2016 | PA 143 of 2015 | Physical | Nurse Case Management | Genesee County Health Department | 28485 |  | 219430 | 219430 | 247915 | 247915 | 247915 | 100% | Provide nurse case management to children identified with elevated blood levels | Number of children served/accepted the offer of services | All legacy cases opened under the Genesee County Health Department have been analyzed and transitioned to CHAP for appropriate next steps. | Completed. For ongoing updates please refer to line 57.
58 | DHHS | 2016 | PA 143 of 2015 | Physical | Nurse Case Management | Greater Flint Health Coalition | 42660 |  | 134425.02 | 134425.02 | 177085.02 | 177085 | 177085 | 100% | Provide nurse case management to children identified with elevated blood levels | Number of children served/accepted the offer of services | Data on new cases sent to CHAP between 5/1/16 and 10/28/16: 114 new cases; 32 received case management; 44 closed without case management; 38 in process of obtaining consent for case management. In total: 439 children up to age 17 in Flint 7 zip codes with EBL;154 received case management;237 closed without case management, 48 in process of obtaining consent for case management. | The nurse case management work was transitioned to the Greater Flint Health Coalition/CHAP as of 5/2/16.
59 | DHHS | 2016 | PA 3 of 2016 | Physical | Nurse Case Management | Greater Flint Health Coalition | 70000 |  |  | 0 | 70000 |  | 70000 | 100% | Provide nurse case management to children identified with elevated blood levels | Number of children served/accepted the offer of services |  | The nurse case management work was transitioned to the Greater Flint Health Coalition/CHAP as of 5/2/16.
60 | DHHS | 2016 | PA 3 of 2016 | Physical | Nurse Family Partnership | Hurley Medical Center |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 100% | Provide NFP specialized home visiting services to low income, first time mothers enrolled before 3rd trimester | Number of women served | 30 women currently being served | Hurley has hired three nurses. The first two nurses have caseloads of 16 and 14 pregnant women. A third nurse completed her training Nov. 14-18th in Denver. She will be slowing working towards building caseload capacity. There are interviews scheduled Nov 28 and Dec. 1 to fill the final position.
61 | DHHS | 2016 | Current Approps | Water | Agency/SEOC support costs | Various |  |  | 20639.93 | 25772.08 | 25772.08 |  | 0 |  | Provide administrative support | As needed |  | 100% of requests met
62 | DHHS | 2016 | Current Approps | Social | Temporary Staff to Support Foster Care and Child Protective Services Programs | Kelly Services |  |  | 3591 | 8550 | 8550 |  | 0 |  | Provide administrative support | As needed |  | 100% of requests met
63 | DHHS | 2016 | Current Approps | Food | Diet Education and Exercise | YMCA of Metropolitan Lansing |  |  | 55000 | 55000 | 55000 |  | 0 |  | Increase healthy foods for the Year-round Healthy Out Of School Time (HOST) Program | Number of children served | 6 sites are now open with approximately 441 children being served | Contract has been executed allowing project to start
64 | DHHS | 2016 | Current Approps | Water | Lead Testing Kits |  |  | 0 |  | 0 | 0 |  | 0 |  | Supplies for lead testing of Flint residents | Number of residents tested |  | Approximately 80% of the test kits and supplies have been used
65 | DHHS | 2016 | Current Approps | Social | Design test, produce, place and conduct advertising and tracking surveys | Brogan and Partners |  |  | 42590.78 | 189981.65 | 189981.65 |  | 0
66 | DHHS | 2016 | Current Approps | Physical | Provide access to fluoride prevention measures through a school-based fluoride mouth rinse program and expansion of a fluoride varnish program for children ages 1-6 | Mott's Children Health Center |  |  |  | 23190.79 | 23190.79 |  | 0
67 | DHHS | 2016 | Current Approps | Social | Low Income Home Emergency Assistance Program |  |  |  |  | 500000 | 500000 |  | 0
68 | DHHS | 2016 | PA 3 of 2016 | Food | Double Up Food Bucks Flint Expansion Project | Michigan Department of Agriculture and Rural Development |  | 330956 | 49044 | 49044 | 380000 | 380000 | 380000 | 100% | Increase consumption of fresh produce by Flint residents | Number of incentives provided for fresh produce consumption | As of Oct 2016 there are 4,661 Supplemental Nutrition Assistance Program (SNAP) customers enrolled in DUFB. This is a 125% increase compared to the same time period last year | An Interagency Agreement with the Michigan Department of Agriculture and Rural Development is in place. Agriculture will contract with the Fair Food Network.
69 | DHHS | 2016 | PA 268 of 2016 | Food | Mobile Food Bank and additional food bank resources | Food Bank of Michigan | 440000 |  |  | 0 | 440000 | 440000 | 440000 | 100% | Deliver fresh produce, eggs or dairy products to affected locations | Deliver healthy lead mitigating foods to all residents in Flint regardless of income
70 | DHHS | 2016 | PA 268 of 2016 | Food | Nutrition Programs | MSU Extension | 1300000 |  |  | 0 | 1300000 | 1300000 | 1300000 | 100% | Improve delivery of nutrition education, expand cooking classes, implement healthy food guidelines in retail locations around the city, provide incentives to food retailers to source food locally | Number of classes held, outreach materials handed out, and stores enrolled in Healthy food retail program |  | Contract started 9/1/16; Media Plan meeting with MDHHS Communications Office; IRB application submitted; Evaluation assessment instrument and evaluation checklist developed; Conference call took place with Chronic Disease (MDHHS) and MSU Ext staff on 11/2/2016 to discuss contract monitoring.
71 | DHHS | 2016 | PA 268 of 2016 | Physical | Contract with Wayne State University to assess linkage between Legionella and water | Wayne State University |  | 2900000 | 50000 | 50000 | 2950000 | 2950000 | 2950000 | 100% |  |  |  | Phase 2 of the contract started on June 1, 2016.
72 | DHHS | 2016 | PA 268 of 2016 | Physical | Childhood lead poisoning prevention program (statewide) | Michigan Public Health Institute and state staff | 1088005 |  | 132517.18 | 132517.18 | 1220522.18 | 1250000 | 1250000 | 97.64% | Provide for home abatement | Number of homes that have begun abatement process (Enrolled)
73 | DHHS | 2016 | PA 268 of 2016 | Social | Community Mental Health services |  | 1490000 |  |  | 0 | 1490000 | 1490000 | 1490000 | 100%
74 | DHHS | 2016 | PA 268 of 2016 | Social | Parents as Teachers evidence-based home visiting program | Genesee County ISD | 260000 |  |  | 0 | 260000 | 260000 | 260000 | 100% | Provide families with training on understanding child development, perform developmental screenings for early detection of potential problems, and connect families with a network of resources | Number of families served |  | The contract with Genesee ISD has been executed. The administrative staff are in the process of being trained on the appropriate data and screening protocols. Further training needs to occur. New home visitors are in the process of being hired and should be on board before the end of November.
75 | DHHS | 2016 | PA 268 of 2016 | Social | Reserve federal TANF future needs for Flint families and children |  | 6100000 |  |  | 0 | 6100000 | 0 | 6100000 | 100% |  |  |  | Working with Workforce Development on putting this funding towards community ventures for TANF recipients in Genesee County
76 | DHHS | 2016 | PA 268 of 2016 | Social | Child and adolescent health center funding | Michigan Primary Care Association | 500000 |  |  | 0 | 500000 | 500000 | 500000 | 100% | Establish CAHC satellite locations in elementary schools | Three CAHC satellite locations established in elementary schools |  | Contract starts 10/1/16
77 | DHHS | 2016 | PA 268 of 2016 | Social | Interpretation services for dead, hard of hearing, and bilingual support |  | 499872 |  | 128.36 | 128.36 | 500000.36 | 500000 | 500000 | 100%
78 | DHHS | 2017 | PA 268 of 2016 | Food | Nutrition Assistance for Children of Flint |  |  |  |  | 0 | 0 | 0 | 3500000 | 0%
79 | DHHS | 2017 | PA 268 of 2016 | Food | Mobile Food Bank, additional food bank resources and food safety inspections | Food Bank of Michigan |  |  |  | 0 | 0 | 1006000 | 1006000 | 0% | Deliver fresh produce, eggs or dairy products to affected locations | Deliver healthy lead mitigating foods to all residents in Flint regardless of income
80 | DHHS | 2017 | PA 268 of 2016 | Food | Nutrition Services 5-10 year olds | Michigan Department of Education |  |  |  | 0 | 0 | 229400 | 257100 | 0% |  |  |  | Interagency Agreement has been finalized to transfer funds from DHHS to MDE. MDE will contract with YMCA and Food Bank of Eastern Michigan to provide additional fresh fruits and vegetables at snacks in the at risk after school program in conjunction with nutrition education for the children and families. The Food Bank will also enhance their weekend backpack program for children affected by the water crisis.
81 | DHHS | 2017 | PA 268 of 2016 | Physical | Adult Blood Lead Epidemiology and Surveillance (ABLES) | MSU |  |  |  | 0 | 0 | 44400 | 44400 | 0% | Conduct interviews with individuals with blood lead levels at or above 5 in the City of Flint. Surveillance database will be modified to reflect data collection. Ongoing epidemiologic analyses of the data will be completed | # of interviews conducted
82 | DHHS | 2017 | PA 268 of 2016 | Physical | Child/Adolescent health centers | Michigan Primary Care Association |  |  |  | 0 | 0 | 472500 | 472500 | 0% | Establish CAHC satellite locations in elementary schools | Three CAHC satellite locations established in elementary schools |  | FY17 Contract starts 10/1/16
83 | DHHS | 2017 | PA 268 of 2016 | Physical | Lead programming for children/homes/outreach | Southeastern Michigan Health Association |  |  |  | 0 | 0 | 831000 | 1304800 | 0% | Provide for home abatement | Number of homes that have begun abatement process (Enrolled)
84 | DHHS | 2017 | PA 268 of 2016 | Physical | Epidemiologists services | Michigan Public Health Institute |  |  |  | 0 | 0 | 212000 | 212000 | 0% | Conduct blood level analyses | Number of requests for blood level analyses |  | Continuation of 2 contractors hired in FY16.
85 | DHHS | 2017 | PA 268 of 2016 | Physical | Nurse case management and public health assessments | Greater Flint Health Coalition |  |  |  | 0 | 0 | 471300 | 471300 | 0% | Provide nurse case management to children identified with elevated blood levels | Number of children served/accepted the offer of services |  | FY17 Contract Starts 10/1/16
86 | DHHS | 2017 | PA 268 of 2016 | Social | Community Education with Genesee County Health Department | Genesee County Health Department |  |  |  | 0 | 0 | 120000 | 120000 | 0% | Provide health education and outreach initiatives | Number of health education and outreach initiatives
87 | DHHS | 2017 | PA 268 of 2016 | Social | Community Mental Health services |  |  |  |  | 0 | 0 | 4245600 | 6135000 | 0%
88 | DHHS | 2017 | PA 268 of 2016 | Social | Parents as Teachers evidence-based home visiting program | Genesee County ISD |  |  |  | 0 | 0 | 260000 | 260000 | 0% | Provide families with training on understanding child development, perform developmental screenings for early detection of potential problems, and connect families with a network of resources | Number of families served
89 | DHHS | 2016 | DECF | Water | Reimbursement from DECF |  |  |  |  | -2487746.83 | -2487746.83 |  | 0
90 | DHHS | 2016 | Internal transfer | Physical | Medicaid coverage for children up to age 21 and pregnant women | Various |  |  | 4470600 | 4470600 | 4470600 | 4470600 | 4470600 | 100% | Provide short- and long-term health support to Flint residents served by the Flint water system | 15,000 residents newly enrolled for Medicaid Coverage and an additional 15,000 currently on Medicaid enrolled to receive case management services | 1,808 new Medicaid enrollees and 22,368 with current coverage enrolled for case management services as of Sept 20, 2016 | Medicaid waiver enrollment began May 9, 2016. There is a slight decrease in the overall waiver enrollment this month compared to last month, which is consistent with overall Medicaid caseload trends & the impacts of redeterminations that are seen at the beginning of each month.
91 | DHHS | 2016 | Current Approps | Physical | DIT Costs Related Flint Waiver |  |  |  | 471745.07 | 1886980.24 | 1886980.24 |  | 0
92 | DHHS | 2016 | Current Approps | Social | Flint Water Serg | Genesee CMH |  |  |  | 85000 | 85000 |  | 0
93 | DHHS | 2016 | Current Approps | Water | DCDS Time Tracking |  |  |  | 796498.38 | 796498.38 | 796498.38 |  | 0
94 | DHHS | 2016 | Current Approps | Social | Lump Sum Payment to Private Child welfare agencies for increased level of required care and supervision mandated by DHHS | Multiple |  |  | 321000 | 321000 | 321000 |  | 0 |  | Provide special payments to PAFC by 7/30/16 |  |  | 100% of payments to date
95 | DHHS | 2016 | Current Approps | Social | 211 Outreach Efforts | United Way of Genesee County |  |  | 5000 | 10000 | 10000 |  | 0
96 | DHHS | 2017 | PA 268 of 2016 | Food | Double Up Food Bucks Flint Expansion Project | Michigan Department of Agriculture and Rural Development |  |  |  | 0 | 0 | 380000 | 380000 | 0% | Increase consumption of fresh produce by Flint residents | Number of incentives provided for fresh produce consumption |  | An Interagency Agreement with the Michigan Department of Agriculture and Rural Development is in place. Agriculture will contract with the Fair Food Network.
97 | DHHS | 2017 | PA 268 of 2016 | Food | Genesee County food safety inspections | Genesee County Health Department |  |  |  | 0 | 0 | 300000 | 300000 | 0% | Conduct assessments to determine compliance with water requirements, conduct enforcement, complete follow up visits for non-compliance due to high lead levels, collect water samples | 212 Food Service Establishments for continued compliance checks |  | FY17 Contract starts 10/1/16
98 | DHHS | 2017 | PA 268 of 2016 | Social | Pathways to Potential Expansion | N/A |  |  |  | 0 | 0 | 147000 | 300000 | 0% | Place additional Pathways to Potential workers in Flint schools | Six Pathways to Potential workers hired and placed in Flint schools |  | Continuation of 6 pathways workers in Flint schools
99 | DHHS | 2017 | PA 268 of 2016 | Physical | Children's Healthcare Access Project (CHAP) | Greater Flint Health Coalition |  |  |  | 0 | 0 | 375000 | 375000 | 0% | Assist children with establishing primary care medical home | 700 children assisted with establishing primary care medical home |  | FY17 Contract starts 10/1/16
100 | DHHS | 2016 | Current Approps | Physical | Flint Water Flush Public Education Campaign | Martin Waymire |  |  | 29580.57 | 29580.57 | 29580.57 |  | 0
101 | DIFS | 2016 | Current Approps | Social | Agency/SEOC support costs |  |  |  |  | 5658.5694 | 5658.5694 |  | 0 |  | Participation in the SEOC, outreach to Flint and gathering information for DIFS in response to request from Governor’s office for all FW related documents | Monitor activity to identify anything that relates to DIFS and follow-up as needed. | 72.5 staff hours participating in: SEOC conference calls; outreach to Flint; gathering information for Governor's office. | Participation in SEOC conference calls; attended 2 JIC outreach events in Flint; responded to 3 requests for information from the various staff at the SEOC; conducted a data call of 1169 authorized P&C insurers to provide data to the SEOC; responded to 1 consumer telephone call; 1 written consumer complaint/inquiry, and 1 response to a state agency question on health insurance coverage.
102 | LARA | 2016 | PA 143 of 2015 | Water | Plumbing inspections of Schools, Child Day Care Centers, Adult Foster Care, and Health Facilities |  |  |  |  | 199606.32 | 199606.32 |  | 200000 | 99.8% | Site Mapping of Plumbing Infrastructure Translation Services; Agency/SEOC Support Costs | Site Mapping of Plumbing Infrastructure: 12 Adult Foster Care 37 Child Day Care 36 Schools 2 Health Care Facilities Foreign Language Translations: 203 requested American Sign Language: 49 | Adult Foster Care (AFC) - 12 of 12; Child Day Care (CDC) - 37 of 37; Schools - 36 of 36; Health Care Fac. - 2 of 2; TOTAL Completed: 100% Foreign language translations: Requested 223 (56 documents into approximately 4 different languages); 181 completed and on website; 20 received, not needed/pulled from website; 18 requested/or received but not yet on website. American Sign Language: 56 translations requested, 25 completed/on website; 14 Not Sent/Not Required; 2 pulled from website. 13 requested/or received but not yet on website. | Substantially Complete
103 | LARA | 2016 | DECF | Water | Reimbursement from DECF |  |  |  | -23584.38 | -23584.38 | -23584.38 |  | 0
104 | LARA | 2016 | PA 3 of 2016 | Water | Fixture replacements (Schools, daycares, adult foster care, nursing homes, dialysis centers, surgery centers) | Home Depot (641P6600569): Johnson & Wood (641N6600060): Etna Supply (641P6600608); Ferguson Enterprises (N6600063) |  | 136874.87 | 1117834.46 | 1117834.46 | 1254709.33 | 2000000 | 2000000 | 62.74% | Supplies, Plumbing Install Contract, Agency/SEOC Support Costs | Map and install 1,360 plumbing fixtures. (2 sites (14 fixtures) are not to be replaced) At the request of DEQ we have installed 41 filters as of 7/8 | Contractors have installed 1,360 of 1,360 mapped fixtures as of 5/1; 100 % completed | Initial Installs Completed
105 | DMVA | 2016 | PA 3 of 2016 | Water | Agency/SEOC Support Costs | See attached | 0 | 0 | 2476834 | 2476834 | 2476834 | 2000000 | 2000000 | 123.8% | Deliver cases of water, faucet kits and filters to affected locations | Distribute as many supplies as possible daily | 578,482 cases, 19,091 faucet kits, 39,081 filters | Distributed Water Cases, Faucet Kits, Filters to affected locations
106 | DMVA | 2016 | Current Approps | Water | Admin Support - Estimate Agency/SEOC Support Costs | See attached | 0 | 0 | 65111.17 | 65111.17 | 65111.17 | 0 | 0 |  | Provide Admin Support | As needed | Approx 1002 hours to support Flint Water Emergency Effort | 100% of Request met
107 | DNR | 2016 | Current Approps | Water | Assist DEQ in responding to Flint Water emergency | Various |  |  | 70.24 | 1262.01 | 1262.01 |  | 0 |  | Provide support to DEQ in responding to Flint emergency | As needed | Approximately 15,000 hours spent supporting the Flint water emergency effort | 100% of requests met
108 | DNR | 2016 | PA 268 of 2016 | Water | Summer Youth program to help with aid to Flint | Genesee Area Focus Fund |  |  | 249999.98 | 249999.98 | 249999.98 | 250000 | 250000 | 100% | Provide youth in Flint with employment opportunities | As needed | Grant Awarded to grantee and fully spent by grantee | Grant Awarded to grantee and fully spent by grantee
109 | School Aid | 2016 | PA 249 of 2016 | Social | Early on funding (April - September) for all 0-4 year olds in the city; funded from GF transfer to School Aid Fund | Will add info in subsequent reports | 8300000 | 0 | 900000 | 900000 | 9200000 | 9200000 | 9200000 | 100% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
110 | School Aid | 2017 | PA 249 of 2016 | Food | Genesee ISD fresh fruit/vegetables for K-5; funded from GF transfer to School Aid Fund | Will add info in subsequent reports | 0 | 0 | 0 | 0 | 0 | 137500 | 137500 | 0% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
111 | School Aid | 2017 | PA 249 of 2016 | Physical | School Nurses for Flint Public Schools; funded from GF transfer to School Aid Fund | Will add info in subsequent reports | 0 | 0 | 0 | 0 | 0 | 317500 | 317500 | 0% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
112 | School Aid | 2017 | PA 249 of 2016 | Social | Early on services 0-3 funding; funded from GF transfer to School Aid Fund | Will add info in subsequent reports | 0 | 0 | 0 | 0 | 0 | 6400000 | 6400100 | 0% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
113 | School Aid | 2017 | PA 249 of 2016 | Social | Grant to Genesee Intermediate School Districts to serve school aged children; funded from GF transfer to School Aid Fund | Will add info in subsequent reports | 0 | 0 | 0 | 0 | 0 | 812500 | 812500 | 0% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
114 | School Aid | 2017 | PA 249 of 2016 | Social | School Social Workers for Flint Public Schools; funded from GF transfer to School Aid Fund | Will add info in subsequent reports | 0 | 0 | 0 | 0 | 0 | 975000 | 975000 | 0% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
115 | School Aid | 2017 | PA 249 of 2016 | Social | Great Start Readiness; funded from GF transfer to School Aid Fund | Will add info in subsequent reports | 0 | 0 | 0 | 0 | 0 | 1500000 | 1500000 | 0% | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports | Will add info in subsequent reports
116 | MDOS | 2016 | Current Approps | Water | Emergency Management Coordinator Conference Call Participation / Assistance at the Flint Information Center |  |  |  |  | 3131 | 3131 |  | 0 |  | Provide support for the Flint water emergency | As needed | Approximately 45 hours spent supporting the Flint water emergency effort | 100% of requests met
117 | MSP | 2016 | PA 3 of 2016 | Water | Operational funding for Flint Water Interagency Coordinating Committee |  |  |  | 7042.7 | 7042.7 | 7042.7 | 100000 | 100000 | 7.043% | Operational funds for Flint Water Interagency Coordination Committee | Hold meetings as needed to make recommendations to the Governor | Provide recommendations as requested
118 | MSP | 2016 | Current Approps | Water | SEOC support costs. State & Local EOC duties. Providing security & support for delivering water/water related items. |  |  |  |  | 988462.51 | 988462.51 |  | 0 |  | Safe and successful handling of Flint Water response. Safe delivery of water and water related items. | As needed | 13,935 hours - Spent supporting the SEOC and the safe & successful delivering of Flint Water response. | Safe and successful handling of Flint Water response. Safe delivery of water and water related items
119 | MSP | 2016 | Current Approps | Water | SEOC, Joint Information Center and Warehouse operations | Various |  |  |  | 701509.42 | 701509.42 |  | 0 |  | SEOC, Joint Information Center and Warehouse Operations | As needed | Continuous operations of the SEOC, Joint Information Center and Warehouse | Have provided overall coordination and distribution of water and filters
120 | MSP | 2016 | PA 268 of 2016 | Water | Water and filter cartridges |  |  | 5359 | 2292069 | 2292069 | 2297428 | 6000000 | 6000000 | 38.29% | Bottled Water | Provide water as needed
121 | MSP | 2016 | DECF | Water | Reimburse DE from DECF |  |  |  |  | 8463.5 | 8463.5 |  | 0
122 | MSP | 2016 | DECF | Water | Reimburse DEQ from DECF |  |  |  |  | 792870.41 | 792870.41 |  | 0
123 | MSP | 2016 | DECF | Water | Reimburse DHHS from DECF |  |  |  |  | 2487746.83 | 2487746.83 |  | 0
124 | MSP | 2016 | DECF | Water | Reimburse DOC from DECF |  |  |  |  | 755148.73 | 755148.73 |  | 0
125 | MSP | 2016 | DECF | Water | Reimburse DOT from DECF |  |  |  |  | 694095.99 | 694095.99 |  | 0
126 | MSP | 2016 | DECF | Water | Reimburse DTMB from DECF |  |  |  |  | 3049302.81 | 3049302.81 |  | 0
127 | MSP | 2016 | DECF | Water | Reimburse LARA from DECF |  |  |  |  | 23584.38 | 23584.38 |  | 0
128 | TED | 2016 | Current Approps | Econ Develop | Public Outreach/Communications |  |  |  | 127543.56 | 127543.56 | 127543.56 |  | 0 |  | Public Outreach/ Communications | Public Outreach/ Communications | Completes tasks as assigned | Completes tasks as assigned
129 | TED | 2016 | Current Approps | Econ Develop | The project’s primary goals will be to: 1) develop temporary jobs that benefit the residents of Flint affected by the Flint Water Crisis by employing workers on projects that provide emergency water, water filters, lead testing kits and replacement cartridges, 2) provide support services to the persons placed into the temporary job, 3) provide support for temporary jobs through warehousing water and other commodities, and recycling the bottles and filters as needed during the crisis. | GST Michigan Works! Governing Board and State of Michigan Employees | 4127759 |  |  | 3372241.03 | 7500000.03 |  | 0 |  | Providing work experience program to place program participants into work experience jobs (managing bottled water inventory and distributing bottled water to Flint Residents). Providing job skills training and supportive services to transition participants into long term employment with the goal toward career self-sufficiency. | The project plans to serve 400 Dislocated Workers and Long Term Unemployed (those who have been out of work more than 20 nonconsecutive weeks in the past five years) who reside in Flint. Temporary jobs will allow an individual to be hired under this project for a period of no more than 12 months and will not exceed 2080 hours. | To date, approximately 267 participants have been placed into temporary employment and 204 into subsidized employment. The number of hours worked is currently not available. Work experience jobs have been created in areas such as career counselors, truck drivers, water distribution hub managers, and water distribution workers. Subsidized employment, work-experience positions have been created in a number of charitable and community organizations such as Mission of Hope, the Food Bank, and the Flint Housing Commission. To date, over 1.3 million cases of water, 27,000 faucet filters, 49,000 replacement filters, and 9,000 water test kits have been distributed through this project. | Activity is on going
130 | MSF | 2016 | Current Approps | Econ Develop | Capitol Theatre Project |  |  |  | 5500000 | 5500000 | 5500000 |  | 0 |  | Support for Capitol Theatre renovation | Creation of 82 jobs |  | Funding allocated
131 | MEDC | 2016 | Component Unit | Econ Develop | Market studies for grocery store in City of Flint. | Flint Genesee Chamber of Commerce |  |  |  | 70000 | 70000 |  | 0 |  | Market analyses that drive the strategic establishment of viable grocery store(s) in key locations within the City of Flint | Consultant to complete a market study report | Request for Proposal let by Flint Genesee Chamber of Commerce, vendor selected, grant paperwork being started in MEDC
132 | MSF | 2016 | Component Unit | Econ Develop | iSource Worldwide and SkyPoint Ventures - business development performance loan and grant | iSource Worldwide and SkyPoint Ventures |  | 1500000 |  | 2750000 | 4250000 |  | 0 |  | Performance based loan and grant to support venture located in Flint | Creation of 100 jobs |  | MSF Board approved project. First payment was made in August.
133 | MSHDA | 2016 | Component Unit | Econ Develop | Grant funds provided to hire 50 local residents for installation of water filters, test and record lead levels in the water | Orchard's Children Services | 25000 |  |  | 25440 | 50440 |  | 0 |  | 50 individuals hired and trained to test water in Flint, in conjunction with Flint YMCA's Safe Places Program | Individuals hired, trained, and on payroll for this purpose | Provision of job opportunities for Flint residents as part of a larger job training and employment support effort | Half of Funding spent hiring has begun.
134 | MSHDA | 2016 | Component Unit | Water | Water sample testing, install water filters |  |  |  |  | 39415 | 39415 |  | 0 |  | 1) Organize testing procedures for MSHDA funded developments. 2) Deliver and install water filters and follow up to ensure filters installed correctly | 1) Provide 500 water testing kits 2) Ongoing outreach to Tenant Based Voucher holders | 1) Approximately 220 testing kits have been analyzed for lead content | 1) Sampling results show 4.1 % of sampling pool beyond 15 PPB for lead and 0.9% tested high for copper. 2) Reached roughly 600 voucher holders through door to door or mailers.
135 | MSHDA | 2016 | Component Unit | Econ Develop | Study potential infrastructure improvements |  |  |  |  | 7365 | 7365 |  | 0 |  | Study available resources to assist in Governor's 75 point plan | Secure Funding in order to accomplish objectives | Organizing efforts regarding Help For Hardest Hit Funds, Multifamily Housing, Homeowner Mortgage Program | Efforts ongoing
136 | MSHDA | 2016 | Component Unit | Econ Develop | Attract New Business to Flint |  |  |  |  | 10570 | 10570 |  | 0 |  | Work to attract a grocery store to Flint | Fresh fruits & vegetables to help mitigate high levels of lead |  | Efforts ongoing
137 | MSF | 2016 | Component Unit | Econ Develop | Technical assistance and training to businesses affected by water crisis | Flint Genesee Chamber of Commerce |  | 100000 |  | 0 | 100000 |  | 0 |  | Technical assistance and training to businesses for federal, state, and local contracting |  |  | Funding allocated
138 | MSHDA | 2016 | Component Unit | Econ Develop | Prepare/Review RFP pertaining to homeowner rehab due to lead contamination |  |  |  |  | 1161 | 1161 |  | 0 |  | Review RFP for $1 million of HOME funding | Grant funding to nonprofit agency to perform homeowner rehab | Award announcement should be made in the month of August | Efforts ongoing
139 | MSHDA | 2016 | Component Unit | Physical | Provide outreach services Flint residents |  |  |  |  | 249 | 249 |  | 0 |  | Provide outreach to Flint residents regarding physical well being | Provide information on blood testing, expanded Medicaid Services, Nutrition, and other information |  | Efforts ongoing
140 | DTMB | 2016 | Current Approps | Water | SEOC Support | U-Haul, Star Truck Rental, Penske, Hallwood Plaza, Bell Warehousing, Consumers Energy, DTMB Print and Graphics, Grainger, Amazon, Republic Services, UPS, Walmart, Apple, Best Buy, Cellco, Verizon |  | 0 |  | 3049302.81 | 3049302.81 |  | 0 |  | Provide requested technology, equipment and Facilities | All requested resources have been provided | requests are completed as they come from the SEOC | request fulfilled
141 | DTMB | 2016 | PA 268 of 2016 | Water | Drinking water declaration of emergency reserve fund |  |  |  |  | 0 | 0 | 18900000 | 18900000 | 0%
142 | DTMB | 2016 | DECF | Water | Reimbursement from DECF |  |  |  |  | -3049302.81 | -3049302.81 |  | 0
143 | MDOT | 2016 | Current Approps | Water | Support water distribution: snow removal, traffic control devices, & staff support | MDOT, Quality Temporary Services |  | 0 |  | 694135.23 | 694135.23 |  | 0 |  | Respond to resource requests to support water distribution | As Needed | Approximately 76 employees spent 9,656 hours supporting water distribution; Contract for temporary staffing in place to continue to meet resource requested CDL drivers. | 100% of Requests Met
144 | MDOT | 2016 | DECF | Water | Reimbursement from DECF |  |  |  |  | -694095.99 | -694095.99 |  | 0
145 | Treasury | 2016 | Current Approps | Water | Reconnect to Detroit Water System | City of Flint |  |  |  | 2000000 | 2000000 |  | 0 |  | Reconnect to Detroit Water System | Reconnect to Detroit Water System |  | City of Flint remains on the Detroit Water System
146 | Treasury | 2016 | AY13 Work Project | Water | Reimburse the City for a portion of its cost for performing a search for a new DPW director | Michigan Municipal League | 10000 |  |  | 0 | 10000 |  | 0 |  | # of well qualified candidates | Hire a qualified DPW Director |  | Interviews completed, selection process ongoing, no applicant selected at this time.
147 | Treasury | 2016 | PA 24 of 2016 | Water Bill Credits | To provide relief for the residents by funding a credit on water/sewer bills (April 15-Dec 31, 2016) | City of Flint |  |  | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 100% | # of credits issued and total amount of credits | Apply credits to residents water and sewer bills |  | $29,020,837 sent to the City for water credits. Remaining balance will be wired after the next series of credits.
148 | Treasury | 2016 | PA 268 of 2016 | Water | Mission Flint program management office (June-Dec, 2016) | City of Flint |  |  | 51090.33 | 51090.33 | 51090.33 | 1380000 | 1380000 | 3.702% | Staffing and support for Mission Flint | Assist Flint during water crisis |  | No appropriation spent to date
149 | Treasury | 2016 | PA 268 of 2016 | Water Bill Credits | To provide relief for the residents by funding a credit on water/sewer bills (April 15-Dec 31, 2016) | City of Flint |  |  | 1080157 | 1080157 | 1080157 | 12750000 | 12750000 | 8.472% | # of credits issued and total amount of credits | Apply credits to residents water and sewer bills |  | No appropriation spent to date
150 | Treasury | 2016 | AY13 Work Project | Water | Reimburse the City for legal costs related to Congressional testimony | Reed Smith LLP |  |  | 90794.95 | 90794.95 | 90794.95 |  | 0 |  | Provide legal research for testimony related to Flint water issues | Reimburse the City for legal research |  | City of Flint has been reimbursed for the legal research during congressional hearings
151 | Treasury | 2016 | AY13 Work Project | Water | Reimburse the City for assistance in the water bill relief credit program | Great Lakes Treasury Services |  |  | 5053.08 | 5053.08 | 5053.08 |  | 0 |  | Assist Flint in providing a water bill relief credit program | To provide water bill relief credits to the Flint residents |  | Project ongoing, City is able to provide appropriate credits
152 | Treasury | 2016 | AY13 Work Project | Water | Reimburse the City for assistance in developing the software need to apply water credits | BS&A Software |  |  | 29800 | 29800 | 29800 |  | 0 |  | Customize Flint's water and sewer billing system | To accommodate the water bill relief credit program |  | Project ongoing, City is able to provide appropriate credits
153 | Treasury | 2016 | AY13 Work Project | Water | To provide legal assistance with the Flint water investigation | Dykema Gossett |  | 28762.64 | 21237.36 | 21237.36 | 50000 |  | 0 |  | Assist Flint in providing legal counsel for parties involved in the water crisis | To ensure that representation is properly provided |  | Investigation is ongoing, additional work is expected
154 | Treasury | 2016 | AY13 Work Project | Water | To reimburse the City of Flint for administrative costs related to the water credit program | City of Flint |  |  | 21818.03 | 21818.03 | 21818.03 |  | 0 |  | City of Flint employees provided overtime assistance with water credit program | To accommodate the water bill relief credit program |  | Project ongoing, City is able to provide appropriate credits
155 | Treasury | 2016 | AY13 Work Project | Water | To reimburse the City of Flint for assistance to ensure the accuracy and completeness of the water credit program | YEO & YEO |  |  | 28648 | 28648 | 28648 |  | 0 |  | Review of the accuracy and completeness of the application of the water credits | To accommodate the water bill relief credit program |  | Project ongoing, City is able to provide appropriate credits
156 | Treasury | 2016 | AY13 Work Project | Water | To provide a benchmarking study on the City's water rates | Raftelis |  | 18675.21 | 61324.79 | 61324.79 | 80000 |  | 0 |  | Provide water rate analysis on Flint resident's water bills | Develop a five year water revenue and expenditure projection |  | Initial water rate analysis complete, additional work possible
157 | MGCB | 2016 | Current Approps | Water | Agency/SEOC support costs |  |  |  |  | 3541 | 3541 |  | 0 |  | Provide administrative support | As Needed |  | 100% of Requests Met
[7 empty] | 60122948.72 | 5859452.22 | 79246557.67 | 104041651.0494 | 170024051.9894 | 185408800 | 234100000
[7 empty] | Agency | Appropriated | Spent to Date | Encumbered/ Obligated | Total
[7 empty] | MDARD | 0 | 450834 | 0 | 450834
[7 empty] | Att General | 1300000 | 2719432.23 | 130333 | 2849765.23
[7 empty] | Civil Rights | 0 | 37557.45 | 0 | 37557.45
[7 empty] | Corrections | 0 | 831289.27 | 0 | 831289.27
[7 empty] | Education | 36335100 | 2030764.82 | 697699.72 | 2728464.54
[7 empty] | DEQ | 51836600 | 18044306.59 | 29554597 | 47598903.59
[7 empty] | DHHS | 51705700 | 17833828.91 | 21347340.5 | 39181169.41
[7 empty] | DIFS | 0 | 5658.5694 | 0 | 5658.5694
[7 empty] | LARA | 2200000 | 1293856.4 | 136874.87 | 1430731.27
[7 empty] | DMVA | 2000000 | 2541945.17 | 0 | 2541945.17
[7 empty] | DNR | 250000 | 251261.99 | 0 | 251261.99
[7 empty] | School Aid | 19342600 | 900000 | 8300000 | 9200000
[7 empty] | State | 0 | 3131 | 0 | 3131
[7 empty] | MSP | 6100000 | 11800296.28 | 5359 | 11805655.28
[7 empty] | TED | 0 | 3499784.59 | 4127759 | 7627543.59
[7 empty] | MSF | 0 | 8250000 | 1600000 | 9850000
[7 empty] | MEDC | 0 | 70000 | 0 | 70000
[7 empty] | MSHDA | 0 | 84200 | 25000 | 109200
[7 empty] | DTMB | 18900000 | 0 | 0 | 0
[7 empty] | MDOT | 0 | 39.24 | 0 | 39.24
[7 empty] | Treasury | 44130000 | 33389923.54 | 57437.85 | 33447361.39
[7 empty] | Gaming | 0 | 3541 | 0 | 3541
[7 empty] | Total | 234100000 | 104041651.0494 | 65982400.94 | 170024051.9894
[7 empty] | Category | Appropriated | Spent to Date | Encumbered/ Obligated | Total
[7 empty] | Econ Develop | 0 | 11864320.59 | 5752759 | 17617079.59
[7 empty] | Food | 19654800 | 1598726.56 | 3021427.22 | 4620153.78
[7 empty] | Physical | 16478100 | 9522148.96 | 6085724.31 | 15607873.27
[7 empty] | Social | 66937700 | 7310940.3294 | 21368221.69 | 28679162.0194
[7 empty] | Water | 88279400 | 42665357.61 | 29754268.72 | 72419626.33
[7 empty] | Water Bill Credits | 42750000 | 31080157 | 0 | 31080157
[7 empty] | Total | 234100000 | 104041651.0494 | 65982400.94 | 170024051.9894
[7 empty] | Public Act | Appropriated | Spent | Encumbered/ Obligated | Total
[7 empty] | PA 143 of 2015 | 9350000 | 9251478.54 | 197256.5 | 9448735.04
[7 empty] | PA 3 of 2016 | 28028500 | 16911221.71 | 9761378.59 | 26672600.3
[7 empty] | PA 24 of 2016 | 30000000 | 30000000 | 0 | 30000000
[7 empty] | PA 268 of 2016 | 142908300 | 10798922.89 | 41783236 | 52582158.89
[7 empty] | PA 249 of 2016 | 19342600 | 900000 | 8300000 | 9200000
[7 empty] | Internal transfer | 4470600 | 4470600 | 0 | 4470600
[7 empty] | AY 15 work project | 0 | 1137055 | 0 | 1137055
[7 empty] | AY 13 work project | 0 | 258676.21 | 57437.85 | 316114.06
[7 empty] | Current Approps | 0 | 27409496.6994 | 4258092 | 31667588.6994
[7 empty] | Component Unit | 0 | 2904200 | 1625000 | 4529200
[7 empty] | Total | 234100000 | 104041651.0494 | 65982400.94 | 170024051.9894
UNAUDITED
UNAUDITED