## Slide 1
[Guidance Slide-Information Only, Delete]
There is guidance within slides on what to include and items to be pulled from the Team Charter. Please be sure to remove this guidance (text colored in red) once information is included.
Feel free to add graphics, charts, screen shots of pertinent tools, and pictures throughout to make the presentation engaging and easily understood by the intended audience. Use bullets to limit the amount of narrative on slides, too much text on PPT slides can be overwhelming.
It is highly recommended that you have someone outside of your QI team review the Story Board from the audience perspective.
Use the notes section below the slide to capture additional information that you would share verbally during the presentation, notable things that are not able to be captured in the slides due to space limitation.

## Slide 2: QI Project Title Team Name Local Implementing Agency FY16 Storyboard
[Insert Program/ Organization Logo or Graphic]

## Slide 3: Our QI TEAM
[Insert team member names, agency position they are representing on the team, and role on QI team (pull from Team Charter) – a table has been included below for you to display this information]
[This is a great spot to include a picture of your team!]
Team Member Name | Agency Position | Role on CQI Team

## Slide 4: PLAN Stage Identify an Opportunity and plan for Improvement
Getting Started
Assemble the Team
Examine the Current Approach
Identify Potential Solutions
Develop an Improvement Theory

## Slide 5: PLAN Stage identify an opportunity And Plan for Improvement
Problem Statement
[Insert Problem Statement from your Team Charter]
Aim Statement
[Insert final Aim Statement from your Team Charter]

## Slide 6: PLAN Stage identify an opportunity And Plan for Improvement
Examine the Current Approach: Process Map
[Insert the process map the team developed of the current process (prior to improvement) or a description (it’s a good idea to use bullets to break up the text) of the current process selected for improvement.]

## Slide 7: PLAN Stage identify an opportunity And Plan for Improvement
Examine the Current Approach: Key Lessons from Process Map
[Examine Current Approach: Look to the process improvement area on the Team Charter for key information about the process and gaps noted by the team in review of the process map. What did the team learn from your process map that informed the PDSA cycle undertaken? You can summarize in bullets.]

## Slide 8: PLAN Stage identify an opportunity And Plan for Improvement
Examine the Current Approach: Baseline Data
[Include baseline data that supports the problem identified, the measure in your Aim Statement, and the process being targeted for improvement. This is a good spot to insert a chart (pie, bar, run, etc.) with your data displayed visually. Keep in mind, the team will want to display comparison data in the Study section of the story board.]

## Slide 9: PLAN Stage identify an opportunity And Plan for Improvement
Examine the Current Approach: Determine Root Cause
[Insert the QI tool (Fishbone Diagram, Tree Diagram, Force Field Analysis, Interrelationship Diagraph etc.) used to examine root causes.]

## Slide 10: PLAN Stage identify an opportunity AND Plan for Improvement
Examine the Current Approach: Key Lessons from Root Cause Analysis
[Determining Root Cause: What did the team learn from the QI tool used to examine root cause? How did the team decide what root cause to tackle? You can summarize in bullets.]

## Slide 11: PLAN Stage identify an opportunity AND Plan for Improvement
Identify Potential Solutions
[Insert Affinity Diagram or other QI tool used to brainstorm potential solutions to the root cause.]

## Slide 12: PLAN Stage identify an opportunity And Plan for Improvement
Identify Potential Solutions: Key Lessons from Affinity Diagram
[What did the team learn from identifying potential solutions based on the root cause? Were model or best practices reviewed to identify potential changes that could be tested? What solution did the team pick and why? You can summarize in bullets.]

## Slide 13: PLAN Stage identify an opportunity And Plan for Improvement
Improvement Theory (If/Then Statement)
[Insert Improvement Theory/Theories from your Team Charter]

## Slide 14: DO Stage Test the theory for Improvement
Test the Theory for Improvement

## Slide 15: Do Stage Test the theory for Improvement
Test the Theory
Major Action Steps | Date Completed
[Note the major action steps and dates your team took to test the improvement theory (complete the Do stage). This includes tasks that were completed in order to prepare for the test as well as testing the theory.]
Notes: [How was the test carried out? Did the team carry the test out on a small scale? How did the team determine the effectiveness of the test? What problems, unexpected observations, and/or unintended side effects occurred? Feel free to insert images of tools developed for your test here (i.e. survey, tracking document, etc.)]

## Slide 16: Do Stage Test the theory for Improvement
[Use this space to insert images of tools developed for your test (i.e. survey, tracking document, checklist, etc.)]

## Slide 17: STUDY Stage Use data to Study the Results of the Test
Study the Results

## Slide 18: Study Stage Use Data to Study The Results
How did the test go?
[Was the test successful? Did the results match the team’s theory? Was there an improvement? You can summarize in bullets.]
[Insert a chart or table with your data (be sure to include your baseline and comparison data). Feel free to include the data chart(s) on a separate slide, if needed.]

## Slide 19: Study Stage Use Data to Study The Results
What did the team learn?
[Note what the team learned through the test here. Did the team experience any unintended side effects or events that impacted results? Did the team need to test the improvement under other conditions? Were there any “aha” moments during the test? You can summarize in bullets.]

## Slide 20: AcT Stage Act on the Results and Establish Future Plans
Standardize the Improvement Theory or Develop a New Theory
Establish Future Plans

## Slide 21: ACT STAGE Act on the results and Establish Future Plans
  Based on the results, the team decided to: Adapt, Adopt, or Abandon the improvement theory
    [Why?]
  The team celebrated the successes of this cycle by:
    [Note what the team did to celebrate – feel free to include a picture of your celebration.]
  Plans for the next PDSA cycle:
    [What are the team’s plans for your next PDSA cycle?]