# Michigan Department of Health and Human Services

# Behavioral Health and Developmental Disabilities Administration

Behavioral Health Home and Opioid Health Home Updates

April 2020

| Topic | Behavioral Health Home Updates | Opioid Health Home Updates |
| --- | --- | --- |
| State Plan Amendment (SPA) work with the federal Centers for Medicare & Medicaid Services (CMS) | - Met with CMS to discuss draft concept paper in February, they are going to review further and contact us if they have any questions or comments - Required Public Notice and Tribal Notice are complete - We are aiming for a late spring/early summer SPA submission date - We are on track for the October 1, 2020 start date | - Met with CMS to discuss draft concept paper in February, they are going to review further and contact us if they have any questions or comments - Required Public Notice and Tribal Notice are complete - We are aiming for an early summer SPA submission date to CMS - We are on track for the October 1, 2020 start date |
| Medicaid Policy Promulgation | - Public comment is out until April 14th; once that concludes the policy will move to final - You can view the proposed policy here: https://www.michigan.gov/mdhhs/0,5885,7-339-71551_2945_42542_42543_42546_42553-87511--,00.html - We are on track for the October 1, 2020 start date | - Public comments are due by April 16th; once that concludes the policy will move to final - You can view the proposed policy here: https://www.michigan.gov/mdhhs/0,5885,7-339-71551_2945_42542_42543_42546_42553-87511--,00.html - We are on track for the October 1, 2020 start date |
| IT Systems Work (e.g., reimbursement, enrollment) | - Projects to support the systems accommodations needed in CHAMPS (for reimbursement and benefit plan assignment) and the Waiver Support Application (for enrollment) will soon commence - A draft BHH webpage has been created and will be shared once approved. - We are on track for an October 1, 2020 start date | - Projects to support the systems accommodations needed in CHAMPS (for reimbursement and benefit plan assignment) and the Waiver Support Application (for enrollment) will soon commence - We are on track for an October 1, 2020 start date |
| Provider Development with the Lead Entities (LEs) and Health Home Partners (HHPs) | - MDHHS met with all Lead Entities to discuss implementation progress. Recommended activities to focus on: - Identify HHPs - Develop contracts - Submit the Health Home Provider Application - You can locate the application on the OHH website under provider resources: - https://www.michigan.gov/mdhhs/0,5885,7-339-71547_4860-475091--,00.html - Develop payment methodology for HHP - Identify staff | - MDHHS met with all Lead Entities to discuss implementation progress. Recommended activities to focus on: - Identify HHPs - Develop contracts - Submit the Health Home Provider Application - You can locate the application on the OHH website under provider resources: - https://www.michigan.gov/mdhhs/0,5885,7-339-71547_4860-475091--,00.html - Develop payment methodology for HHP - Identify staff |