The Liberty Consulting Group

Schedule B - Pricing

Request For Proposal No. 230000001370

Utility Distribution System Audit

- The Contractor must provide a pricing schedule for the proposed Contract Activities using  Microsoft Word or Excel; however, you may also submit an additional pricing schedule in a non-modifiable format (e.g., PDF). Failure to complete the pricing schedule as requested may result in disqualification of your proposal.

- Price proposals must include all costs, including but not limited to, any one-time or set-up charges, fees, and potential costs that Contractor may charge the State.

- The Contractor is encouraged to offer quick payment terms. The number of days must not include processing time for payment to be received by the Contractor's financial institution.

Quick payment terms: n/a% discount off invoice if paid within n/a days after receipt of invoice.

- By submitting its proposal, the Contractor certifies that the prices were arrived at independently, and without consultation, communication, or agreement with any other Contractor.

|  | Utility Distribution System Audit – Part 1 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Schedule B.1 – Pricing Worksheet |  |  |  |  |
|  | CATEGORY – Key Personnel |  |  |  |  |
| Name | Position Title | Personnel Salary | Hourly Rate | Estimated Number of Hours | Total |
| John Antonuk | Project Manager | Confidential |  |  |  |
| Christine Kozlosky | Lead Auditor | Confidential |  |  |  |
| Lauen Gaunt, P.E. | Senior Consultant | Confidential |  |  |  |
| Dan Kowalewski | Senior Consultant | Confidential |  |  |  |
| Mark Lautenschlager | Senior Consultant | Confidential |  |  |  |
| Michael Antonuk | Consultant | Confidential |  |  |  |
| Ed Kram* | Senior Consultant (contingent) | Confidential |  |  |  |
| Michael Sedlak* | Senior Consultant (contingent) | Confidential |  |  |  |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
| Category Total |  |  |  | 2340 | $732,200 |
|  | CATEGORY – Non-Key Personnel and Other / Administrative Personnel |  |  |  |  |
| Name | Position Title | Personnel Salary | Hourly Rate | Estimated Number of Hours | Total |
| Dr. Alan Salzberg | Statistics Lead | Confidential |  |  |  |
| Corey West | Statistics Support | Confidential |  |  |  |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
| Category Total |  |  |  | 320 | $84,960 |
| GRAND TOTAL |  |  |  | 2660 | $817,160 |

*Mr. Kram and Mr. Sedlak are not at present budgeted to spend any hours, but if final system sampling program imposes significant time or other constraints, we can allocate time from the other Senior Consultants without increasing total hours required, with their addition and any changes to other budgets subject to prior MPSC Staff approval

|  | Utility Distribution System Audit – Part 2 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Schedule B.2 – Pricing Worksheet |  |  |  |  |
|  | CATEGORY – Key Personnel |  |  |  |  |
| Name | Position Title | Personnel Salary | Hourly Rate | Estimated Number of Hours | Total |
| John Antonuk | Project Manager | Confidential |  |  |  |
| Brian Daschbach | Lead Auditor | Confidential |  |  |  |
| Mike Beck, P.E. | Lead Auditor | Confidential |  |  |  |
| Dan Kowalewski | Senior Consultant | Confidential |  |  |  |
| Mark Lautenschlager | Senior Consultant | Confidential |  |  |  |
| Lauen Gaunt, P.E. | Senior Consultant | Confidential |  |  |  |
| Christine Kozlosky | Senior Consultant | Confidential |  |  |  |
| Michael Antonuk | Consultant | Confidential |  |  |  |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  | Category Total |  |  | 2780 | $939,000 |
|  | CATEGORY – Non-Key Personnel and Other / Administrative Personnel |  |  |  |  |
| Name | Position Title | Personnel Salary | Hourly Rate | Estimated Number of Hours | Total |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  |  |  | $ |  | $ |
|  | Category Total |  |  | 0 | $0 |
|  | GRAND TOTAL |  |  | 2780 | $939,000 |

Explanation of Hours Budgeted for Stratified Statistical Sampling

The preceding tables assume a total of 1,200 hours (400 each for Mr. Lautenschlager, Mr. Kowalewski, and Mr. Gaunt) for the stratified statistical sampling work activities of Part 1. This section explains the interaction of those budgeted hours with other Part 1 and with Part 2 activities.

Stratified sampling as contemplated by the RFP appears useful in two related but distinct ways in examining and assessing the distribution infrastructure of the two Michigan utilities:

Providing visibility to the Commission, Staff, and stakeholders about several classes of attributes that define the systems and drive their operation

  - Essentially objective attributes (e.g., physical nature, components, and configuration)

  - Mixed objective and subjective attributes (e.g., conformity with standards and code and other external requirements, condition, health, and fitness for intended use)

  - Relating those attributes to performance levels (e.g., as measured by reliability metrics)

  - Identifying, using attribute identification through categorization of attributes (e.g., by sub-region, community) field based locational differences that relate to other areas of issues of interest or concern (e.g., equity in ensuring service reliability, safety, hardness, resiliency, etc.)

Informing our Part 2 work, which will need the information to identify specific needs, issues, and primary areas of focus in addressing historical, current, and projected reliability, safety, hardness, resiliency, and other performance factors in identifying contributors to any issues of concern and on crafting recommendations for cost effectively securing improvements for the future.

The attribute data and information we will report through Part 1 efforts also will provide important background for Commission, Staff, and stakeholder readers of the report on Part 2 findings, conclusions, and recommendations. These Part 1 results will permit them to form their own views about the significance, priorities, cost/benefit relationships and other factors necessary for consideration in using report results to drive future programs, plans, and initiatives. Generally, our examinations of electric utility system planning, engineering and design, configurations, technology use, installation, management and operations, reliability, safety, hardness, and resiliency have had as a primary focus the identification of potential cost-effective improvements.

A hallmark of our reporting is the creation and expression in final reports of a reasonably complete and sound factual foundation that explains why and how we reached conclusions and formulated recommendations. Our reports have always (subject only to a handful of client requests over three decades for more brevity in reporting) sought as well to offer readers enough information to draw their own conclusions, or at least to question the sufficiency of ours and to identify further inquiries they consider appropriate).

We find the two-part audit structure the RFP consistent with our general approach. We have used sampling (sometimes designed under formal statistical guidelines and protocols and sometimes using judgment to determine how much information we need, based on our team’s more than a century of combined experience. The benefits of a statistical approach must always be balanced against the “value” the results produce, particularly when competitive pricing is a factor in our selection to perform work. We clearly understand the independence, transparency and other value that the RFP seeks to achieve from Part 1’s statistical sampling. Similarly, we understand the value in the findings, conclusions, and recommendations that Part 2 must produce.

However, as our budget proposal recognizes, sampling here can lead to Part 1 costs that begin to approach or even exceed the resources required to perform the remainder of the engagement. The RFP has created a process that engages MPSC Staff and the companies in work to determine a suitable stratified sampling program. We read that process as recognizing the uncertainties that now surround that determination. They include numbers of components at issue, how to categorize and stratify populations, determination of the desired resulting confidence interval(s), and what comprises and acceptable results error rate. In turn, those uncertainties will drive the hours required to execute the stratified sampling process we design with consideration of the participation of Commission Staff and the companies in discussions about that design.

Accordingly, we have budgeted hours for sampling based on the rough “value” proposition that Part 1 hours and thus costs could approach, but should not exceed other Part 1 and Part 2 work efforts combined. We say “rough” because we understand that Commission Staff may address value differently as the uncertainties above become resolved sufficiently to design a program that provides a reasonably firm basis for estimating the resource requirements for executing it. Many factors drive the hours required to execute the field examinations that will comprise a major component of Part 1 costs. They have the potential for reducing visitable locations per day to single digits depending in major part on distances involved. Those distances will provide significant given the size and dispersion of company facilities across much of the state.

The factors involved include:

Pre-identification of locations involved and creation of daily transportation routing between them

Accommodation of company requirements and support-person availability for addressing access and assuring selection of proper locations (e.g., specific pole numbers or spans)

Travel time to vicinity of day’s first location

Reconnaissance time to find exact locations after exit from highway arteries

Time to visually inspect each location, enter attribute data into provided templates specifically designed for each component and configuration at issue

Time to create a photographic record of site circumstances and conditions

Return from day’s last visited location

Validation of completeness and proper entry of attribute template data and photographic materials

Periodic calibration discussions among inspection team members validate consistent application of criteria for making specific attribute entries, to capture lessons learned by others (particularly from photographic materials

Travel and reconnaissance time for each remaining.

We too are likely to see value differently as alternative sampling program designs can emerge. However, the point, as we read the RFP is not to impose our judgment, but to engage MPSC Staff and the companies in doing so. We see our role as offering designs that we consider reasonable alternatives, providing the hours and costs for executing them, and adjusting them based on sampling program design changes produced by the discussions contemplated.

That categorization, stratification, confidence intervals, error rates and other determinants finally accepted may not have originated with us is not material. Of course, the need for our work to be independent requires that we find the plan ultimately accepted sufficient in terms of execution completeness, objectivity and integrity and with respect to full and candid results reporting. Beyond these factors, we also need the ability to assign final hours to the ultimately approved sampling program.

Budgeted hours, and thus costs, for stratified sampling activities may rise or fall from those budgeted based upon the final plan adopted, which must follow work with the MPSC Staff and the companies. If an offer that requires firm total pricing (as opposed to unchanged hourly rates applicable throughout the duration of the contract) is not required, we agree that we will perform any finally approved sampling program in accord with an approved hours and cost estimate for so doing.

If an offer must provide firm total pricing through the duration of the contract, understand that we are offering a firm price of $1,756,160. Should the final approved sampling plan call for a scope, and thus hours and costs, beyond those (1,200 hours at $396,000) assigned to stratified sampling in the preceding tables, we agree as follows:

We will design and execute after working with MPSC Staff and the companies, an agreed-upon final sampling program that; (a) is achievable for the 1,200 hours, and (b) balances categorization, stratification, confidence intervals, error rates and other determinants according to a prioritization of them

Finding agreed upon means for reducing other Part 1 and Part 2 work activities (and any accompanying change in results able to be produced) by the amounts necessary to account for required hours beyond 1,200.

Final sample program design also may, once uncertainties are reduced through first Part 1 efforts, produce a reduction in sampling program hours from the 1,200 shown above. In that event, we will identify that reduction and reduce firm pricing, and at the election of MPSC Staff either:

- Reduce firm pricing accordingly

- If MPSC Staff makes any request for any other, additional, sampling, other Part 1, or Part 2 work, we will propose, specifically responsive detailed plans and budgets. We will undertake those plans only if and as approved by the authority designated by the Commission.

In summary, we agree to the firm pricing set forth in the tables above, subject to adjustment as described above.