EQuIS™ Implementation Approach

Prepared for: State of Michigan,

Department of Technology, Management and Budget

25 September 2023

Dan Alexander

Vice President

dalexander@earthsoft.com

Table of Contents

EQuIS Implementation Proposal	4

Executive Summary	4

Summary of Estimated Costs*	5

TRACK 1: ROUTINE IMPLEMENTATION SERVICES	5

Task 1: EQuIS Implementation Project Initiation	5

Task 2: EQuIS Configuration	6

Task 3: EQuIS Training	7

On-Site Option	7

Task 4: Data Management Plan	8

Task 5: EQuIS Workflow Documentation	9

TRACK 2: Historical Data Migration Evaluation and Data Transformation/Migration	10

Task 1: Historical Data Migration Evaluation	10

Task 2: Data Transformation/Migration (Design and Implementation)	11

Conditions and Schedule to Complete Proposed Services	14

Terms of Service	14

Payment Terms	14

Acceptance and Authorization Signature	14

Appendix A:  Draft EQuIS Implementation Plan	15

Task 1: Project Initiation	15

Task 2: EQuIS Installation, Configuration and Customization	15

Task 3: Training and Ongoing Support	16

Task 4: Data Management Plan Documentation	16

Task 5: Data Reporting and Collection Workflow Definitions	17

Appendix B: Data Migration Assumptions & Scope	18

Phase 1 – Evaluation – Client Data Inventory	20

Task 1.1 – Data Inventory	20

Phase 2 – Design –Inventory Mapping	20

Task 2.1 – Data Table Mapping	21

Task 2.2 - Reference Values	21

Task 2.3 - Data Review	21

Phase 2 Completion	22

Phase 3 – Implementation – EDD Testing, Creation and Loading	22

Task 3.1 – Format Development	22

Task 3.2 – Data Migration	22

Task 3.3 - Data Migration Correctness and Completeness Checks	23

Task 3.4 - Data Deliverable	23

Project Management	23

Appendix C:  EarthSoft Services Hourly Rate Schedule	24

Appendix D: Client Billing Address and Other Information	25

# EQuIS Implementation Proposal

## Executive Summary

EarthSoft is pleased to submit this estimated proposal for EQuIS Implementation services to the State of Michigan, Department of Technology, Management and Budget. Based on each client’s specific requirements, the overall implementation process may include three separate tracks. The tasks outlined for each track are typical steps in an EQuIS Implementation, and the level of effort estimated represents an average for each track and related task(s).

The EQuIS implementation project will begin as specified in the final Statement of Work (SOW) delivered after the Project Initiation step (in Track 1) and will consist of the following component(s):

TRACK 1 – Routine implementation services

  - Valid value review and loading

  - Workflow requirements gathering

  - Applications configured (Field forms, task management, dashboard views, report setup)

  - Training

  - User acceptance testing

  - Go live

TRACK 2 – Historical Data Migration Evaluation and Data Transformation/Migration

Historical Data Migration Evaluation

  - Determine current data status

  - Plan database mapping

  - Mid-stream assessment

  - Confirm time/effort costs

Data Transformation/Migration

  - Review of the schema and valid values

  - Begin to convert client databases into an EQuIS format for migration to the new EQuIS system

  - Use the EQuIS Link data transformation tool to map and convert client databases

If the proposed implementation fits this average, the costs estimated should cover completion of that task. If, however, further review reveals complexities or other unanticipated obstacles, EarthSoft will summarize the status of the track/task and provide an updated cost estimate based upon the knowledge and state of the implementation at that time.  The EQuIS Implementation Project Initiation task will tailor the suggested scope, schedule, and budget to the organization’s specific needs and refine the task list appropriately. A refined cost estimate will be provided after all requirements are defined.

# TRACK 1: ROUTINE IMPLEMENTATION SERVICES

## Task 1: EQuIS Implementation Project Initiation

To commence the EQuIS Implementation as effectively as possible, the EarthSoft implementation team will conduct several meetings with the client to evaluate current-state environmental data workflows (including field forms and reporting requirements), identify future-state EQuIS workflows, and discuss project plans and schedules. The Implementation will be broken down into tasks, and roles and responsibilities for all Implementation team members will be reviewed. Data management workflow(s) to meet client requirements will be finalized. Sources and locations of key data sets needed to configure the EQuIS reference tables will be identified. Milestones, key dates, and task assignments will be determined. Post-kickoff meeting, the EarthSoft project team will complete the project initiation by generating refined cost estimates and authoring the revised Scope of Work (SOW).

The following project areas will be discussed during the series of Kickoff Meetings to inform the revised SOW:

- Project Contacts

  - EarthSoft contacts, client contacts, internal stakeholders, laboratory contacts, subject matter experts (SMEs)

- IT/Security

  - Discuss cloud hosting requirements, desired Azure region, number/type of user, required levels of access

- Current & Future State Workflow

  - Map out current and future state workflow and desired improvements

- Reporting & Visualization

  - Identify required internal and external reports, discuss appropriate level of automation, define integration points with other systems (e.g., Power BI, ArcGIS Pro, etc.)

- Historical Data Migration

  - Identify existing data sources, discuss cost vs. value of historical data, identify legacy data required for “field-to-field” migration, review reference values and naming conventions, discuss plan to migrate gap data

- Field Data Collection

  - Discuss current field forms, review out-of-the-box EQuIS Collect forms, identify field devices/equipment desired for integration

- Sample Planning

  - Identify sample plans to be configured in EQuIS SPM, discuss pre-population of field forms vs. ad-hoc data collection

- Electronic Data Deliverable (EDD) Formats

  - Identify current Electronic Data Deliverable (EDD) formats provided by laboratories and contractors, review out-of-the-box EQuIS EDD formats for historical and ongoing data import

- Data Qualification

  - Discuss data qualification requirements, identify data review routines fit for automation in EQuIS DQM

- Training

  - Determine training frequency and format (e.g., regional, site-by-site, etc.)

- User Acceptance Testing (UAT)

  - Determine process and staff for UAT, discuss functional requirements to be tested, define “completeness”

Refinement of the cost for this task will be adjusted and provided prior to the meeting series once the EarthSoft team is formed and location of the meeting is determined and scheduled.

## Task 2: EQuIS Configuration

EQuIS Configuration is the stage that applies the definitions, requirements, and procedures defined during the Project Initiation task and included in the Data Management Plan. Specifically, this may include:

EQuIS Software will be deployed

Facilities will be created in the EQuIS database as defined during project initiation

Locations and coordinates will be reviewed and loaded

Reference values for matrices, location types, analytical methods, fractions, and test types will be reviewed and loaded

Other reference value sets, as required and appropriate, will be reviewed and loaded

Groups (location, facility, and others as needed) will be defined and configured

Method Analyte Groups (MAGs) will be reviewed and loaded

Action Levels will be reviewed and loaded

User roles/types will be defined, and members identified

Field forms (within scope) will be produced for Collect

Reports will be configured

Dashboard views will be created as prescribed within the scope

User Acceptance Testing (UAT) will be defined

Because of the magnitude and complexity of this effort, individual tasks will be prioritized and may be phased. The result of EQuIS Configuration is that EQuIS will be operational as specified in the revised Scope of Work. Data will be loadable, viewable, and reportable.

## Task 3: EQuIS Training

## On-Site Option

Throughout the EQuIS implementation, EarthSoft will conduct EQuIS training sessions for the project team including data managers, users, and consultants. These training sessions will be organized around the specific needs and user types, and they will cover the use of EQuIS.  Training will be tailored to topics such as the client Data Management Program or project-specific data management SOPs.

While the training will be arranged to best fit the schedule and needs of those attending, the recommendation is to have an initial three-day session soon after the configuration of the reference values and the loading of locations into EQuIS. This provides an opportunity to review and discuss the setup and structure of the configured EQuIS data. However, as a populated example database already exists, this session could be held as soon as practical within the scheduling constraints of both EarthSoft and the client.

During the EQuIS Configuration task (Task 2), online, focused Product Training on specific EQuIS applications is recommended to provide details around how particular applications (such EQuIS SPM or EQuIS DQM) may be configured.  Each session will be 2-3 hours at most and will be conducted by an EQuIS Trainer or a Subject Matter Expert, depending on availability and application.

Approximately 3 to 4 months into the project and following the first sessions, a second three-day session would be conducted to train new staff would be conducted to train new staff, reinforce, and clarify concepts already discussed, and explore other facets of EQuIS use not previously covered.

For consultants and laboratories, one 2-hour session of virtual (or in-person) training per organization is appropriate.  Prior to the kickoff and requirements gathering, an assumption is made of four (4) organizations (for example, two laboratories and two consultants) requiring training.

One day of setup and preparation prior to each session ($2,000) and three days of training for up to 10 people is estimated at $3,000/day. (For 10 or more people, a second trainer is required at additional cost.) Consultant and Laboratory Training is taught consecutively with Follow-Up Training, if in-person.

## Task 4: Data Management Plan

The Data Management Plan (DMP) is the overall guidance document for managing data using EQuIS. This task involves research and inquiry into current data management procedures to identify where activities can or should be modified to best fit a new, optimized data management process. The DMP will be based on client-specific requirements relative to the collection, management, and reporting of both field and analytical data.

The DMP will include a detailed description of tasks including steps to be followed that will comply with the data management process. The document will also include any identified specifications or standard operating procedures (SOPs), which may include:

Sample planning

Field data collection

Chain of Custody (COC) preparation and submission of data to the laboratories

Laboratory reporting

Data checking and loading

Reporting

Data validation

- The DMP will complement, and is not meant to supplant, existing EarthSoft online documentation and general Training exercises. It will focus on client-specific procedures and is meant to be a living document to which the client may continue making changes and revisions in the future, post-implementation.

## Task 5: EQuIS Workflow Documentation

The client will use EQuIS as the corporate data management system to manage field and analytical data. EQuIS consists of the EQuIS Professional and EQuIS Enterprise applications, the relational database model (Schema) itself, and several modules supporting the data workflow, including the EQuIS Data Processor (EDP), EQuIS Live for real-time data logger data, EQuIS Geotech for geotechnical data, Sample Planning Module (SPM), and EQuIS Collect. Optional modules include EQuIS Alive for biological/ecological data and EQuIS Risk3T for environmental risk assessment.

The purpose of the Workflow Documentation is to provide a visual representation of how each piece of the EQuIS software will be implemented and integrated. The workflow documentation may identify client staff or groups responsible for operating and maintaining EQuIS.

The client’s workflow will be mapped out and documented appropriately. This documentation is incorporated into the Data Management Plan. Detailed workflows may also be generated to illustrate individual sections of the EQuIS implementation, and to provide more accurate detail and understanding of the EQuIS data management process.

# TRACK 2: Historical Data Migration Evaluation and Data Transformation/Migration

## Task 1: Historical Data Migration Evaluation

In many cases, historical data must be migrated into EQuIS from legacy systems or other data repositories. Data migrations are frequently the largest source of effort uncertainty in an EQuIS Implementation and often the largest overall task in terms of level of effort and time required for completion. For this reason, it is impossible to predict how much effort will be required to ‘complete’ the data migration. Generally, data migrations include up to 80% of the legacy data being migrated. EarthSoft separates data migration projects into three phases:  Evaluation, Design, and Implementation.

EarthSoft has extensive experience with data migrations from PDF, spreadsheets, commercial off-the-shelf (COTS) systems, Microsoft Access, and other historical data formats. We have scripts written for most standard formats and experience developing new ones if needed.  Costs provided for this Track are estimated probable costs and are based on representations made rather than the product of the detailed Mapping outcome of the Design phase.

The level of effort estimate represents a budget estimate average based on experience with similar projects. These numbers do not reflect the simplest or most complex Data Migrations. If the proposed migration fits this average, the costs estimated should cover completion of this task.  EarthSoft will provide an updated estimate for each phase of the migration based upon the knowledge and state of the migration at the end of the Evaluation and Design phases.

EarthSoft separates Data Migrations projects into three phases: Evaluation, Design, and Implementation.  This approach has been developed based on years of experience in performing data migrations.  EarthSoft starts each data migration effort with imperfect knowledge of the source data and specifics on how this source data will map into the EQuIS data structure.  EarthSoft can often estimate the effort for the first phase, Evaluation, accurately based on representations from the client.  The level of effort for Design and Implementation, by contrast, is unknown until we complete Evaluation.

During the Evaluation phase, the EarthSoft team will work with the client to review the current state of the historical data, discuss concerns regarding the data, and consider recommendations.  If an inventory is provided, each element will be assessed for data complexity and volume.  If no inventory is available, this phase will establish one.  The data migration objectives will be weighed against the total budgeted allowance of Track 2 and if gross discrepancies exist, a change in scope or in budget will be discussed to complete the other Data Migration Phases.

The EarthSoft team will work with the client to answer the following questions during the evaluation:

- How many databases, Excel spreadsheets or other source data?

- Determine data volume and complexity

  - How unique and / or variable are the databases, Excel spreadsheets or other source data? (Two different databases can be twice the work of two databases that are identical.)

- What is the current state of the data to be migrated?

  - SQL Server database that is highly normalized? Data dictionary is not available, making mapping more difficult?

- How are the data accessed—on a server, individual hard drives, CD, paper?

- How many records are to be migrated? How will the data be divided into manageably sized Electronic Data Deliverables (EDDs)? Will Enterprise EDP be implemented?

## Task 2: Data Transformation/Migration (Design and Implementation)

Once the Evaluation phase of a Historical Data Migration is complete, the migration itself will be completed in two additional phases: Design and Implementation. We will estimate a separate level of effort / cost for Design (inventory / mapping) and for Implementation (queries and tools / data loading), which allows the client to consider the value of migrating the data based on EarthSoft’s design mapping.

The second phase of historical data migration, Design, uses the Client provided or developed Inventory of data, creates a preliminary mapping from the source client data structure to the EQuIS data structure, reviews reference values, as well as checks for referential integrity and data anomalies.  There are several checkpoints in this phase where level of effort is analyzed.  These checkpoints address the representations made on the data for the price quotation versus the reality of what is received, the complexity of understanding and mapping that data, and presentation to the Client of logical subsets for processing and related costs.

EarthSoft will coordinate with the Client to finalize the scope of the Implementation phase based on Client choices from this estimate.  EarthSoft recognizes that not all data has future value.  The Design provides the Client tools to make decisions regarding the costs and benefits of migrating subsets of the source data.  The final step of the Design phase is for the Client to make selections from the Inventory of data to migrate and EarthSoft to refine the estimate for the Implementation phase based on those selections.

The third phase, Implementation, entails effort to process the selected source client data into Electronic Data Deliverable (EDD) files based on the Design.  It is not possible to provide an accurate estimate for this phase until Design is complete.  EarthSoft is providing a budget or allocation value that will likely be modified at the completion of the Design phase.  This phase, upon Client approval for the refined budget, will process source data into EDDs, load into a test EQuIS environment, assess for correctness and completeness based on the specifications of the client, and provide access for Client acceptance.

The process followed during the Design and Implementation phases of a historical data migration includes:

- Plan database mapping.

  - Create a spreadsheet with the EQuIS and client database mapping.

  - Discuss, review, revise and update mappings, and obtain client approval.

  - Edit or customize EQEDD format for data migration. This will not necessarily be the final client format. The format may only be used for data migration.

- Mid-stream assessment.

  - Reassess at the midway point to confirm validity of the preliminary assessment and assumptions.

  - If necessary, adjust the process and reassess the level of effort.

- Adjust the Time and Effort costs. EarthSoft will provide the client with revised costs for approval before proceeding.

- Complete the mapping and data loading.

Deliverables from the completed Data Migration will include:

- Assumptions Document – to be reviewed and accepted by the client; includes scripts, queries and assumptions made during the migration.

- Mapping Document – Excel spreadsheets containing the mapping from the original data source to EQuIS.

- Reference Value EDDs – for import to the client database.

- Modified EQEDD (or similar) format – typical migrations require that some of the conditional checks are removed or modified.

- Data migration EDDs consistent with the modified EDD format for archival.

The tasks described are intended to be a one-time activity. However, the migration EDDs will be provided in case a re-migration is ever necessary.  Once EarthSoft receives the source data and the migration is started, the client may not enter any new data into the source database(s).

Gap Data

At the outset of the data migration project, the Client and EarthSoft will define a bright line for what data will be included in this project.  There should be a clear plan to handle ‘gap’ data – data that is added to the Client’s legacy data system after the source data for the migration has been delivered to EarthSoft.  The Inventory and Mapping document detail what data are in scope.  All data not included in these documents are out of scope.

Considerations for how to handle the gap data technically will be included but actual effort to migrate that data is not.  Once the initial defined inventory migration is complete, better details on the Gap Data will be available for addressing the required level of effort.

The Data Migration is a collaborative and iterative process between the client and the EarthSoft team, and we work closely with a client representative(s) who are knowledgeable and can make decisions regarding the data.

Assumptions

The provided totals for the data migration evaluation and transformation/migration are based upon assumptions regarding the data sources. EarthSoft has assumed there are no more than thirty (30) fields in each of the tables (132 tables) of the historical databases (2 historical databases, Wellogic and GCTS) with no more than 21,250,109 rows between the databases. EarthSoft follows a proven, repeatable approach to historical data migration ensuring defensibility, auditability, and traceability of the migration. Based on our review of the limited information provided in the RFP regarding historical data, we recommend allocating $346,140 toward this task. This recommendation assumes collaboration between the EarthSoft data migration team and EGLE's Subject Matter Experts (SMEs) to align the scope of the task with the proposed allocation. We understand EGLE may utilize commercial laboratories that are capable of producing EQuIS formatted EDDs. We recommend EGLE request historical data from those laboratories in the EQuIS EQEDD format as a cost saving measure to reduce the above allocation. Additionally, EarthSoft will provide EGLE with EQuIS compatible formats and training on EQuIS Link (data migration tool) to streamline the collaborative migration effort. EarthSoft's assumptions are based on 25+ years of experience with environmental data migration. If the above assumptions are incorrect, EarthSoft will work with EGLE to revise the scope and schedule of the migration task based on the budget allocation.

## Conditions and Schedule to Complete Proposed Services

The client will provide EarthSoft with all relevant information pertaining to the specific objectives and priorities and will generally assist us in accurately and efficiently completing the requested services. EarthSoft will complete the above described deliverable(s) to the client according to a project plan schedule proposed separately. The client is responsible for final testing and will have 15 business days after EarthSoft provides the final deliverable(s) to complete acceptance testing. The budget and time estimate are predicated upon up to two review/feedback cycles. Modifications or changes to scope will require a signed Change Order.

## Terms of Service

These Terms of Service constitute a legal agreement between Client and EarthSoft; therefore, please review these terms of service carefully. By referring to this Price Quotation when placing a Purchase Order (PO), you contractually agree to these Terms of Service as the first order of precedence.

EarthSoft hereby agrees to provide for Client the above EarthSoft services at our standard hourly rates for the actual effort used to perform these services, and not to exceed the Total Budget Amount as stated above (exclusive of travel expenses) without further written authorization.   EarthSoft retains all rights of authorship, ownership, and use of all Intellectual Property created, developed or derived by EarthSoft during the performance of EQuIS support services. Additional EarthSoft services are available to Client at EarthSoft’s current prices.

## Payment Terms

EQuIS Software, Support, and Services fees are quoted to Licensee net to EarthSoft, Inc., 125 S. Alcaniz St., Suite 2, Pensacola, FL 32502, and are exclusive of any and all taxes and fees of every sort. Licensee is solely responsible for all sales tax, use tax, value-added tax, property tax, withholding tax, duties, customs, tariffs, shipping, handling and every other charge that may be lawfully assessed on this transaction at this time or anytime hereafter.

Payment is due within 30 calendar days of the date of each Progress Invoice. All fees are payable in US currency; currency conversions are calculated on the day the EarthSoft Invoice is prepared. A four-percent convenience fee will be added to credit card payments. For proper billing, please see, complete, and return Appendix D Client Billing Address and Other Information with your signed quote and purchase order.

The prices listed may change at any time after expiration of price quotation in 30 calendar days.

## Acceptance and Authorization Signature

| Services Group Manager Signature |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Services Group Manager Name/Title |  |  |  | Signature |  |
| October 4, 2023 |  |  |  | Printed Name/Title |  |
|  |  |  |  | Date |  |
| EARTHSOFT, INC. |  |  |  | State of Michigan, Department of Technology, Management and Budget |  |

# Appendix A:  Draft EQuIS Implementation Plan

EarthSoft has significant experience implementing EQuIS systems. The Plan is for the hypothetical new, typical, large EQuIS implementation. The Project Initiation task will tailor this suggested scope, schedule, and budget to your organization’s specific needs and refine the task list appropriately.

TRACK 1

## Task 1: Project Initiation

- Information Gathering Spreadsheet

- Initial Meetings (Scope, Schedule, Budget Checkpoint)

  - Refine Statement of Work

- Revised Scope, Schedule, and Budget (Scope, Schedule, Budget Checkpoint)

  - Revised Price Quotation for Software

  - Revised Price Quotation for Configuration

  - Client Price Quotation Acceptance and Notice to Proceed

## Task 2: EQuIS Installation and Configuration

- Software Setup According to Configuration Purchased

  - EQuIS Enterprise Deployment

    - Review Client Acceptance of Prerequisites

    - Schedule Deployment Services

    - Set-up TEST Instance of EQuIS Enterprise

      - Install EQuIS Enterprise on Application Server

      - Create or Update EQuIS Database

      - Configure Application Database Service Account

      - Apply EQuIS Licenses

      - Configure Application Logging

      - Configure/Test LDAP/Windows Authorization for Web Application

      - Deploy Standard Dashboards and Widget Types

      - Set-up ALS Roles

      - Set-up Email Functionality

      - Configure Enterprise EDP

      - Setup the Esri ArcGIS API for Use in the Map Widget

      - Test Enterprise EIA Reporting Functionality

  - EQuIS Professional Deployment

    - Set-up TEST Instance of EQuIS Professional

      - Create Enterprise User Accounts

      - Load Reference Values and Action Level EDDs

      - Configure Reports and Exports

      - Test Data Loading

        - Enterprise Data Loading

        - Professional Data Loading

        - Testing Checkpoint

      - Test Reports and Exports

      - Configure EIAs

  - Collect and SPM Deployment

    - Set-up Test Instance of SPM and Collect

      - Test Electronic Forms Data Collection Process

      - Test Enterprise Field Data Loading

      - Test COC, Sample Label Barcoding, and Pertinent Functionality

  - Install other software, as per purchased configuration

  - EQuIS Professional Configuration – PRODUCTION Instance

  - Distribution License – Setup

    - Build Distribution Download Page

    - Build Distribution Registration Page

  - EQuIS Enterprise, PRODUCTION Instance

- Optional – Configure Reports/ Exports, Forms and EDD Formats

  - Develop/Configure Reports and Exports

    - Install on Test Server

  - Develop/Configure EQuIS Enterprise Agents, Reports/Exports

    - Install and Test on Test Server

  - Develop/Configure EDP EDD Format

    - Test Formats and Data Collections

    - Install on Test Server

    - EDP Distribution to Laboratories

  - Develop/Configure Collect Forms, Reports and EDD

    - Test Forms, Reports, Formats and Data Collections

    - Install on Test Server

  - Develop/Configure SPM EDD Formats

    - Test Formats and Data Collections

    - Install on Test Server

## Task 3: Training and Ongoing Support

- Initial Training

- Web Trainings

- Post Implementation Review and Support

  - Meeting to Review EQuIS Data Management Plan

    - Services Contract for Operations

    - Additional Work or Next Phase

  - Regular Account Reviews

  - Review Product Support Options

## Task 4: Data Management Plan Documentation

- Start Data Management Plan

- Review Workflows (Current State vs. Future State)

- Draft Project Plan

- Assign Resources

- Draft Data Management Plan

## Task 5: Data Reporting and Collection Workflow Definitions

- Define Data Reporting Workflows

  - Graphics, or GIS/CAD

  - Reports / Spreadsheets

  - Statistics, Risk Assessment, and Other Exports

  - Other Database or EDD Exports

  - Map All Data Requirements for All Reports

    - Define Valid Values

      - New Valid Values

      - Synonyms and Mappings

  - Prioritize Development of Reports and Exports

  - Prioritize Reports

  - Define Notifications/Triggers (EIAs) for Reporting Automation

  - Define Third-party Software and License Requirements (if needed)

  - Create Reporting Workflow Diagrams

- Define Data Collection Workflows

  - Collect and Refine Data Requirements

  - SPM EDD Formats

    - Map All Data Requirements for All Reports

      - Define Valid Values

        - Handling of New Valid Values

        - Establish Synonyms and Mappings

    - Prioritize Development of Reports and EDDs

  - Collect EDD Formats

    - Map All Data Requirements for Reports and Forms

      - Define Valid Values

        - Handling of New Valid Values

        - Establish Synonyms and Mappings

    - Prioritize Development of Forms, Reports and EDDs

  - EDP EDD Formats

    - Map All Data Requirements for Reports

      - Define Valid Values

        - Handling of New Valid Values

        - Establish Synonyms and Mappings

    - Development of EDD Formats

  - Document Data Collection Workflows

  - Document SOPs for New Contractors for Data Collection Workflows

## Appendix B: Data Migration Assumptions & Scope

Data Migration projects are successful when:

- EarthSoft engages with client representatives who are knowledgeable regarding the subject client data

- EarthSoft checks the Client provided Inventory against the source client data

- EarthSoft Maps the source Client data into the EQuIS data structure and provides the documented Mapping of the data to the client for review

- EarthSoft assists the client in making decisions about both technical and level of effort impacts for migrating specific identified data with inconsistencies, errors, or duplicates from the inventory

  - Data that do not pass quality checks will not be migrated

- The needs of the data migration are carefully balanced against the timeframe and budget

- There is a clear plan to handle ‘gap’ data – data that is added to the Client’s legacy data system after the source data for the migration has been delivered to EarthSoft.

- Consideration is given to how the migrated data is balanced against the future data collection and reporting requirements

- EarthSoft revises the data migration scope and budget as needed based on the client’s decisions.

- EarthSoft processes the data within the Mapping specification of the revised data migration scope

- EarthSoft documents and confirms completeness and correctness of the data migration performed per the data migration scope

- Scope creep is diligently guarded against

It is critical for the client to understand data migration challenges.  There can be many challenges but not all are applicable to every client or each data source.  “Good data” will be migrated while “bad data” may not be.  Challenges around “bad data” may include:

- Source Data Format not structured

  - A structured database defines each field or column, and data are stored consistently in each field.  Structured data typically requires less effort to migrate than unstructured data such as spreadsheets.

- Variability in Source Data Formats

  - Are several or many different legacy formats involved?

  - Are there inconsistencies between source data formats in terms of field and/or parameter nomenclature?

- Source data referential integrity

  - Is the data internally consistent?

  - Does the source data have primary keys that can be translated easily to EQuIS?

- Source data duplications

  - Are there duplications within the data?

- Source data correctness

  - Is the data correct within the data set?  EarthSoft does not correct data as a part of this scope.

  - EarthSoft will recommend transformations for elements such as reference values.

- Source data completeness

  - Is the data complete?  EarthSoft cannot ascertain the completeness of the source data. If new data are discovered during the migration, they will not be considered in scope.

- Variability in Reference values in the Source Data

  - EarthSoft will propose mapping (transformation) of reference values for client approval.

  - Does the client data have duplicate location names or analyte names? How will these be resolved?

    - Is EarthSoft expected to edit or change these?

- Laboratory Quality Control data can consume a disproportionate effort in the migration effort.

  - Is there value in migrating this data now or should it be set aside for future evaluation?

EarthSoft will communicate all data issues discovered in the performance of this task.

Assumptions:

- EarthSoft will make every effort to migrate data based upon the agreed upon Design. The Client will review any problem data and advise EarthSoft on its migration status and priority. Only data that the client explicitly agrees to in the Mapping document will be included in this migration effort.

- EarthSoft guarantees the completeness and correctness of the migrated data under this Service Order.  The source and target data will match in quantity and type with the exceptions of the agreed upon transformations.  EarthSoft shall correct any data errors or omissions that are a result of the data migration as described below. Any data errors and/or omissions resulting from the data migration described in this scope of work and identified during the milestone review period by the client will be corrected by EarthSoft prior to client acceptance.

- Correction of source data deficiencies are not within the scope of these services. Typical source data deficiencies include but are not limited to:

  - incorrect data values,

  - incorrect data-type formatting,

  - duplicated data,

  - typographical errors,

  - referential data integrity issues.

- This Draft Data Migration Price Quotation includes a one-time migration for a fixed point in time. Data acquired by the Client after this date, known as Gap data, are not included in the scope of this document.  Gap data approaches will be discussed during the Design phase and any cost impacts detailed in a revised scope.

- The Data Migration will be a collaborative and iterative process between the client and EarthSoft, where EarthSoft works closely with a client representative who understands the data.

# Phase 1 – Evaluation – Client Data Inventory

The first phase, Evaluation, uses or creates the Client provided Inventory or data, and reviews actual received data to update or create an Inventory for use in all subsequent phases.  The Inventory will be used to assess data complexity and volume and compare to pre-engagement representations used in assembling budgets for the migration activity.  The

## Task 1.1 – Data Inventory

This task aims to agree on a single documented and defined list (the Inventory) of all client-provided data sources and obtain a migrate-yes/no agreement on each item.

- Discuss, review, revise and update Inventory and obtain ongoing client approval for individual subsets of the Inventory

  - All further tasks and associated level of effort are dependent upon the completion of this Inventory.

- Discuss and obtain client agreement on the handling of gap data

- Conference calls: EarthSoft recommends conference calls to review and resolve questions quickly, when appropriate.

Data Inventory Milestone – This milestone is considered complete upon client acceptance of the EarthSoft developed Migration Inventory.  A review of the level of effort anticipated for the agreed upon data inventory will be performed.  This may result in a refined estimate.  

Client will be responsible for:

- Reviewing the Migration Inventory and providing decisions on whether each Inventory item is to be migrated.

- Providing a final acceptance signature on the Migration Inventory document

- Approving any budget changes

# Phase 2 – Design –Inventory Mapping

The second phase, Design, uses the Client provided Inventory of data, creates a preliminary mapping from the source client data structure to the EQuIS data structure, reviews reference values, as well as checks for referential integrity and data anomalies.  There are several checkpoints in this phase where level of effort is analyzed.  These checkpoints address the representations made on the data for the price quotation versus the reality of what is received, the complexity of understanding and mapping that data, and presentation to the Client of logical subsets for processing and related costs.

EarthSoft will coordinate with the Client to finalize the scope of the Implementation phase based on Client choices from this estimate.  EarthSoft recognizes that not all data has future value.  The Design provides the Client tools to make decisions regarding the costs and benefits of migrating subsets of the source data. The final step of the Design phase is to refine the estimate for the Implementation phase.

## Task 2.1 – Data Table Mapping

This task creates the Mapping document to map each field, in each table, in the source data, where the Inventory indicates migration is desired, to the EQuIS schema field, and will include the following:

- Using an Excel spreadsheet, with the table-by-table, field-by-field mapping, EarthSoft will

  - Discuss, review, revise, update mappings, and obtain client approval.

    - EarthSoft requests conference calls to review and resolve questions quickly, when appropriate.

  - Edit or customize Migration formats for data loading.

Data Table Mapping Milestone – This milestone is considered complete upon client acceptance of the EarthSoft Mapping document.  A review of the level of effort anticipated for the agreed upon Mapping document will be performed.  This may result in a refined estimate.  

Client will be responsible for:

- Reviewing the draft Mapping document.

- Provide a final acceptance signature on the Mapping document.

  - Provide approval to continue with the migration

- Approving any budget changes

## Task 2.2 - Reference Values

This task uses the Data Mapping to determine which fields contain Reference Values and match these values to EQuIS Reference Value fields.  Reference values are also sometimes referred to as Valid Values or Lookup tables.

- Review source data Reference Values and compare to EQuIS RVF fields.

- Best judgment assessment to match the migrated reference values to existing EQuIS Reference Values.

- Create and deliver the combined Reference Value spreadsheet.

- Discuss, review, revise and update Reference Value mappings and obtain client approval

- Upon client approval, import the reference values into the Test database and deliver the refvals EDD to client.

Reference Values Milestone – This milestone is considered complete upon client acceptance of the EarthSoft developed Reference Values EDD and Remap document.

The client will be responsible for:

  - Providing personnel to review and discuss the reference values

  - Review, edit and sign off on the combined Reference Value EDD

  - Provide approval to continue with the migration

  - Import data into their EQuIS database if appropriate.

## Task 2.3 - Data Review

Once the mapping has been completed, EarthSoft will undertake a detailed review of the data to examine referential integrity and look for data anomalies. EarthSoft will update the client with the findings of this investigation via edits to the mapping document and description of any data format inconsistencies.  Findings may drive changes to the scope and cost estimate.

## Phase 2 Completion

At the end of Phase 2, EarthSoft will deliver an updated level of effort estimate to the client to complete Phase 3 – Implementation.

The client will be responsible for:

  - approval to any proposed changes in the delivery schedule, including prioritization of data.

  - approval to continue the migration based on the updated cost estimate.

# Phase 3 – Implementation – EDD Testing, Creation and Loading

The third phase, Implementation, represents the effort to process the source data into EDDs, based on the specifications of the client agreed upon Design, and to load into a test EQuIS database.  A test EQuIS database will be used to review this data for correctness and completeness.

## Task 3.1 – Format Development

EarthSoft will use the information gained from the EQuIS mapping to create a modified version of the Migration EDD format definition for migration from the identified Client source data only. Until the mapping is complete, the exact nature of these modifications cannot be confirmed.

Format Milestone – This milestone is complete when EarthSoft delivers the Migration format.

The client will be responsible for:

  - If EQuIS Professional is used to process data

    - Storing the format definition file locally so that data may be imported into the Client EQuIS database.

  - If EQuIS Enterprise is used to process data

    - On-premises clients

      - Uploading the format definition file to the EQuIS Enterprise site, so that the data may be imported.

      - Importing data into the EQuIS database.

    - EOL clients

      - EarthSoft will upload the format definition file and reference values.

## Task 3.2 – Data Migration

The initial level of effort estimates for Phase 2 - Implementation, represents an average for that phase. These numbers do not reflect the simplest or most complex Data Migrations and are provided for illustration only. Experience tells us that a full understanding of the data mapping is required before we can fully assess this level of effort, and strongly depends on the complexity, variability, and referential integrity of the source data set. The steps for this phase include:

- Updates to the Mapping document, including the data mapping tables. Any data gaps and/or default values will be identified within

- Development of scripts used for converting the source data into EDDs compatible with the Migration format

- Importing the data into the Test EQuIS database.

- One-time migration of the data contained in the source data. Any new data received after the backup date will be imported to EQuIS separately and is not part of this scope of work.

- Delivery of a login to the Test db to allow the client to review and comment upon the migrated data within a 15-day review period.

- Conference calls: EarthSoft recommends periodic conference calls to review and resolve questions quickly, when appropriate.

Migration of Data Migration Milestone – This milestone is considered complete when EarthSoft delivers the EDD’s and final Mapping document.

Client will be responsible for:

- Reviewing the data in the Test EQuIS Database and signing off on the final Mapping document.

## Task 3.3 - Data Migration Correctness and Completeness Checks

Throughout the migration, EarthSoft will undertake Migration Correctness and Complete Checks. Often these can be the most time-consuming aspect of the migration. EarthSoft will undertake the following checks on the migration:

- Mapping Checks – has the data been migrated to the correct field?

  - Check the physical mapping against the approved Mapping document

  - Check the special case mapping e.g., data transformation using conditional mapping.

- Row count checks – is all the data accounted for?

- Checksum – aggregating and verifying data values.

## Task 3.4 - Data Deliverable

Once the data in the Test EQuIS Environment has been approved by the Client, EarthSoft will deliver the final EDDs to the Client for loading to their production EQuIS environment.

Optional Task:  EarthSoft is available to assist in uploading the EDDs to the clients Production EQuIS Database.  A separate cost will be provided if this service is desired.

# Project Management

Project Management includes regular meetings to discuss project goals, planning, schedules, deliverables, and administration. EarthSoft will provide a monthly Task Status Report detailing the spend on the project to date and the remaining budget.

# Appendix D: Client Billing Address and Other Information

| Purchase Order Required: Yes / No | Purchase Order Number: |
| --- | --- |
| Special Billing Instructions: |  |
| Billing Address: | Accounts Payable Point of Contact: |
| Billing Telephone Number: | Billing Email Address: |
| Billing Fax Number: | Federal W-9 Required: Yes / No |