## v4 (hidden)
|  |  | 2020 | [51 empty] | 2021
Task # | Category | Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 53 | Week 54 | Week 55 | Week 56 | Week 57 | Week 58 | Week 59 | Week 60 | Week 61 | Week 62 | Week 63 | Week 64 | Week 65 | Week 66 | Week 67 | Week 68 | Week 69 | Week 70 | Week 71 | Week 72 | Week 73 | Week 74 | Week 75 | Week 76 | Week 77 | Week 78 | Estimated Effort | Rate | Estimated Cost | weeks
| EQuIS Implementation Kickoff Meeting |  | 2020 Week 1: 48; 2020 Week 2: 10; 2020 Week 3: 10; 2020 Week 4: 10; 2020 Week 5: 10; 2020 Week 6: 10; 2020 Week 7: 10 | 108 | 180 | 19440
| Data Management Plan/EQuIS Workflow Documentation | [7 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 280 | 180 | 50400
| EQuIS Configuration |  |  |  |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 |  |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 2555 | 180 | 459900
| Historical Data Migration Allowance |  |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [27 empty] | 240 | 180 | 43200
| Training |  | 2020 Week 21: 60; 2020 Week 33: 60; 2020 Week 45: 60; 2021 Week 57: 60; 2021 Week 70: 60 | 300 | 180 | 54000
| Project Management |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 750 | 180 | 135000
|  | Weekly Estimate | 48 | 20 | 20 | 60 | 60 | 60 | 64 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 114 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 114 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 114 | 54 | 54 | 54 | 54 | 54 | 54 | 0 | 0 | 49 | 49 | 49 | 109 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 109 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 49 | 4233 |  | 761940

## OLD Schedule (hidden)
Task # | Category | Task Name | Start Date | Finish Date | Duration (weeks) | Predecessors | Hours per week | Rate | Line Extension | Total hours
1 | Conception | EQuIS Implementation Kickoff |  |  | 2 |  | 20 | 180 | 7200 | 40
2 | Conception | SOW (scope), Schedule, Budget |  |  | 4 | 1 | 20 | 180 | 14400 | 80
3 | Conception | Requirements Definition |  |  | 8 | 1 | 20 | 180 | 28800 | 160
4 | Design/Build | Design Document |  |  | 4 | 3 | 20 | 180 | 14400 | 80
5 | Design/Build | Technical Specifications |  |  | 6 | 4 | 20 | 180 | 21600 | 120
6 | Design/Build | Functional Specifications |  |  | 6 | 4 | 20 | 180 | 21600 | 120
7 | Design/Build | Data Management Plan |  |  | 8 | 3 | 20 | 180 | 28800 | 160
8 | Design/Build | EQuIS Workflow Documentation |  |  | 6 | 7 | 20 | 180 | 21600 | 120
9 | Design/Build | Language configuration |  |  | 6 |  | 20 | 180 | 21600 | 120
10 | Design/Build | Test Environment setup, client access |  |  | 2 | 3 | 20 | 180 | 7200 | 40
11 | Design/Build | EQuIS Customization & Configuration |  |  | 16 | 6, 10 | 20 | 180 | 57600 | 320
12 | Design/Build | Document Management system |  |  | 10 | 6, 10 | 20 | 180 | 36000 | 200
13 | Design/Build | Map/GIS Interface |  |  | 20 | 6, 10 | 20 | 180 | 72000 | 400
14 | Implementation | Historical Data Migration - Phased |  |  | 40 | 7 | 20 | 180 | 144000 | 800
15 | Implementation | Training Plan |  |  | 4 | 8 | 20 | 180 | 14400 | 80
16 | Implementation | Technical Testing |  |  | 4 | 11,12,13 | 20 | 180 | 14400 | 80
17 | Implementation | User Acceptance Testing |  |  | 6 | 15,16 | 20 | 180 | 21600 | 120
18 | Implementation | Change management and training |  |  | 8 | 15 | 20 | 180 | 28800 | 160
19 | Implementation | Transfer to maintenance | [5 empty] | 180 | 0 | 0
20 | Implementation | Deployment Phases |  |  | 24 | 17 | 20 | 180 | 86400 | 480
21 | PM | Project Management |  |  | 72 |  | 10 | 180 | 129600 | 720
| TBD | User & Admin Documentation | [5 empty] | 180
| TBD | PROD Environment setup, client access | [5 empty] | 180
| TBD | Roll Out - Go Live | [5 empty] | 180
| TBD | Phased Deployment plan | [5 empty] | 180
| TBD | Project Governance | [5 empty] | 180
[5 empty] | 72 |  |  |  | 792000 | 4400
Note on C2: Include prep
Note on C4: Conduct design workshops to fine-tune the functional specification of TOTAL Group's expectations
Note on C6: Work product: Technical Specifications document
Note on C7: Work product: Functional Specifications document
Note on C12: not including Doc Mgt and Map/GIS interface
Note on C15: 160 facilities, 25% in legacy system, 5-8 terabytes of data
Note on F15: probably not enough
Note on C21: Regional?, by business (5)?
Note on C22: include Project governance

## v5
ESTIMATE | [80 empty] | *USD to EUR estimated exchange rate on 25 Sept 2019 per www.x-rates.com: | [6 empty] | 0.91354
Task # | Category | Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52 | Week 53 | Week 54 | Week 55 | Week 56 | Week 57 | Week 58 | Week 59 | Week 60 | Week 61 | Week 62 | Week 63 | Week 64 | Week 65 | Week 66 | Week 67 | Week 68 | Week 69 | Week 70 | Week 71 | Week 72 | Week 73 | Week 74 | Week 75 | Week 76 | Week 77 | Week 78 | Estimated Effort (Hrs.) | Estimated Effort (Days) | Rate (Hrs.) | Rate (Days) | Estimated Cost (USD) | Estimated Cost (EUR) | Weeks
1 | Conception | EQuIS Implementation Kickoff | Week 2: 48 | 48 | 6 | 180 | 1440 | 8640 | 7892.951 | 1
2 | Conception | SOW (scope), Schedule, Budget | Week 3: 20; Week 4: 20; Week 5: 20; Week 6: 20 | 80 | 10 | 180 | 1440 | 14400 | 13154.9184 | 4
3 | Conception | Requirements Definition | Week 5: 20; Week 6: 20; Week 7: 20; Week 8: 20; Week 9: 20; Week 10: 20 | 120 | 15 | 180 | 1440 | 21600 | 19732.3776 | 6
4 | Design/Build | Design Document | Week 9: 20; Week 10: 20; Week 11: 20; Week 12: 20 | 80 | 10 | 180 | 1440 | 14400 | 13154.9184 | 4
5 | Design/Build | Technical Specifications | Week 12: 20; Week 13: 20; Week 14: 20; Week 15: 20; Week 16: 20; Week 17: 20 | 120 | 15 | 180 | 1440 | 21600 | 19732.3776 | 6
6 | Design/Build | Functional Specifications | Week 15: 20; Week 16: 20; Week 17: 20; Week 18: 20; Week 19: 20; Week 20: 20 | 120 | 15 | 180 | 1440 | 21600 | 19732.3776 | 6
7 | Design/Build | Data Management Plan | Week 11: 5; Week 12: 5; Week 13: 5; Week 14: 5; Week 15: 5; Week 16: 5; Week 17: 5; Week 18: 5; Week 19: 5; Week 20: 5; Week 21: 5; Week 22: 5; Week 23: 5; Week 24: 5; Week 25: 5; Week 26: 5; Week 27: 5; Week 28: 5; Week 29: 5; Week 30: 5; Week 31: 5; Week 32: 5; Week 33: 5; Week 34: 5; Week 35: 5 | 125 | 15.625 | 180 | 1440 | 22500 | 20554.56 | 25
8 | Design/Build | EQuIS Workflow Documentation | [78 empty] | 80 | 10 | 180 | 1440 | 14400 | 13154.9184 | 0
9 | Design/Build | Test Environment setup, client access | Week 15: 20; Week 16: 20 | 40 | 5 | 180 | 1440 | 7200 | 6577.4592 | 2
10 | Design/Build | EQuIS Customization & Configuration | [78 empty] | 0 | 0 | 180 | 1440 | 0 | 0 | 0
11 | Design/Build | Document Management system (Configuration of Microsoft Azure Files and Microsoft Azure Search) | Week 17: 10; Week 18: 10; Week 19: 10; Week 20: 10; Week 21: 10; Week 22: 10; Week 23: 10; Week 24: 10; Week 25: 10; Week 26: 10; Week 27: 10; Week 28: 10; Week 29: 10; Week 30: 10; Week 31: 10; Week 32: 10; Week 33: 10; Week 34: 5 | 175 | 21.875 | 180 | 1440 | 31500 | 28776.384 | 18
12 | Design/Build | Webmap Interface (Configuration of ArcGIS Online and Esri Javascript API) | Week 15: 10; Week 16: 10; Week 17: 15; Week 18: 15; Week 19: 15; Week 20: 15; Week 21: 15; Week 22: 15; Week 23: 15; Week 24: 15; Week 25: 15; Week 26: 15; Week 27: 15; Week 28: 15; Week 29: 15; Week 30: 15; Week 31: 15; Week 32: 15; Week 33: 15; Week 34: 15; Week 35: 15; Week 36: 15; Week 37: 10; Week 38: 10; Week 39: 10 | 350 | 43.75 | 180 | 1440 | 63000 | 57552.768 | 25
13 | Design/Build | Language configuration | Week 34: 20; Week 35: 20; Week 36: 20; Week 37: 20; Week 38: 20; Week 39: 20 | 120 | 15 | 180 | 1440 | 21600 | 19732.3776 | 6
14 | Implementation | Historical Data Migration Evaluation | Week 8: 20; Week 9: 20; Week 10: 20; Week 11: 20; Week 12: 20; Week 13: 20; Week 14: 20; Week 15: 20; Week 16: 20; Week 17: 20 | 200 | 25 | 180 | 1440 | 36000 | 32887.296 | 10
15 | Implementation | Training Plan | Week 36: 20; Week 37: 20; Week 38: 20; Week 39: 20 |  | 15 |  | 2000 | 30000 | 27406.08 | 4
16 | Implementation | Technical Testing | [78 empty] | 0 | 0 | 180 | 1440 | 0 | 0 | 0
17 | Implementation | User & Admin Documentation | Week 38: 20; Week 39: 20; Week 40: 20; Week 41: 20; Week 42: 20; Week 43: 20; Week 44: 20; Week 45: 20 | 160 | 20 | 180 | 1440 | 28800 | 26309.8368 | 8
18 | Implementation | Phased Deployment plan | [78 empty] | 0 | 0 | 180 | 1440 | 0 | 0 | 0
19 | Implementation | User Acceptance Testing | [9 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | [7 empty] | 305 | 38.125 | 180 | 1440 | 54900 | 50153.1264 | 61
20 | Implementation | Change management and training | Week 42: 20; Week 43: 20; Week 44: 20; Week 45: 20; Week 46: 10; Week 47: 10; Week 48: 10; Week 49: 10; Week 50: 10; Week 51: 10; Week 53: 10; Week 54: 10; Week 55: 10 | 170 | 21.25 | 180 | 1440 | 30600 | 27954.2016 | 13
21 | Implementation | PROD Environment setup, client access | [78 empty] | 0 | 0 | 180 | 1440 | 0 | 0 | 0
22 | Implementation | Deployment Phases | [12 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  |  |  | 1220 | 152.5 | 180 | 1440 | 219600 | 200612.5056 | 61
23 | PM | Project Management |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  |  |  | 576 | 72 | 180 | 1440 | 103680 | 94715.4125 | 72
[81 empty] | 0 | 0 | 180 | 1440 | 0 | 0 | 0
| Milestones | UAT sign off | [78 empty] | 0 | 0 | 180 | 1440 | 0 | 0 | 0
| Milestones | Roll Out - Go Live | [78 empty] | 0 | 0 | 180 | 1440 | 0 | 0 | 0
[81 empty] | 0 | 0 | 180 | 1440 | 0 | 0 | 0
| TBD | Project Governance | [78 empty] | 4089 |  |  |  | 766020 | 699786.8467