## SCHEDULE B - PRICING

Price proposals must include all costs for the licensing, support, implementation, and training for the Solution.

1. Licensing Fees.  If Contractor is proposing a perpetual license, Contractor shall include the one-time cost of the license, which shall cover all intended users of the Solution (please refer to the estimated number and type of users identified in the User Type and Capacity Section of Schedule A - Statement of Work).  If Contractor is proposing a term-based license, Bidder shall include annual costs for the term-based license for, which shall cover all intended users of the Solution (please refer to the estimated number and type of users identified in the User Type and Capacity Section of Schedule A - Statement of Work).  While the State is looking for precise pricing based on the estimated number of users, Contractor is encouraged to also provide a separate, tiered pricing structure to afford the State discounted pricing based on potential increases in volume in the future.  If Bidder offers an enterprise pricing model (e.g. unlimited number of users), it is encouraged to separately provide that pricing option as well.

It is important to note that Slalom recommends the State directly contract with Salesforce via Carahsoft for the most cost-advantageous licensing agreements.  Slalom is not a reseller of software licenses.

If Contractor is proposing a subscription License Model, only Table A must be completed. If Contractor is proposing a Perpetual License Model, License costs must be included in Table B.

2. Support Service Fees.  The Contractor must identify any monthly costs for ongoing support of the Solution (the “Support Service Fees”) to meet the requirements of Schedule D to the Contract Terms - Service Level Agreement. Separate Support Service fees must be documented in Table B below.

3. Hosting Fees.   If Contractor is proposing a perpetual license with a separate hosting cost (direct or through a subcontractor), Contractor must provide the monthly hosting cost in Table B below. Contractor shall include the hosting costs to accommodate all intended users of the Solution (please refer to the estimated number and type of users identified in the User Type and Capacity Section of Schedule A - Statement of Work). Contractor must also provide tiered pricing for hosting to accommodate future growth or reductions.

Table A - Subscription License Model

Assumption 1: It’s rare that an organization would need more than a handful of admin licenses. For this proposal, we’ve assumed 10 users would have admin access.

Assumption 2: Considering the number of employees and approved third party vendors we estimate EGLE to have, we thought it was unrealistic that 5,000 users would be needed for both user types. Based on what we typically see, we assumed that the max number concurrent users (100), was roughly 20% of the total user numbers and therefore assumed that more realistic number of users is 500 for employees and 500 for approved third party.

All costs below are for budgetary purposes only; real licensing cost will need to be further negotiated at time of signature.

| Subscription Based - Product Name | Annual License Subscription Fee (Price per user) | Annual Cost |
| --- | --- | --- |
| Salesforce Government Cloud Plus | ~$1,218 | $609,000 |
| Salesforce Maps | ~$360 | $180,000 |
| Tableau | ~$588 | $294,000 |
| Mulesoft |  | $143,188 |

As stated in “Slalom Response – EGLE Groundwater Data Management”, Slalom is not a reseller of any of the products and licenses mentioned above. All prices included above are considered to be estimates based on assumptions around license quantities and anticipated discounting from Carahsoft and Salesforce. Upon selection Slalom is happy to provide additional analysis to determine the exact number of licenses required to meet the State’s needs and connect the State with the software vendor account teams.

Licensing and Hosting costs will be paid after installation, configuration, and State testing and acceptance of the Solution.

The contract pricing for Support Fees will be awarded based on a firm fixed fee.  However, for price evaluation purposes, Bidder must provide a breakdown of how Support Fees were calculated.

Slalom Enhance and Operate Fees - Application Support is provided by Slalom’s Enhance & Operate services model with defined Service Level Targets. Platform and Application Support are combined to provide EGLE’s solutions with end-to-end coverage and servicing needs from platform up-time to continuous enhancements and modifications to the system and solutions. Slalom’s Enhance & Operate services model will ensure EGLE’s Salesforce solutions are prepared for the Salesforce releases and that EGLE takes full advantage of the newest Salesforce features and functionality.

Our clients typically request that we continually transition support of our solutions to them over time, so that they are not beholden to a third-party vendor for support in perpetuity. We have assumed that in our model below.

| Year | Support Fees | Invoicing Schedule | Fee Breakdown |
| --- | --- | --- | --- |
| 1 | $806,707 | Monthly invoices: $67,226 /month | 2 Full time Slalom Enhance and Operate Contractors |
| 2 | $838,975 | Monthly invoices: $69,915 /month | 2 Full time Slalom Enhance and Operate Contractors |
| 3 | $436,267 | Monthly invoices: $36,356 /month | 1 Full time Slalom Enhance and Operate Contractor |
| 4 | $226,859 | Monthly invoices: $18,905 /month | 1 Half time Slalom Enhance and Operate Contractor |
| 5 | $235,933 | Monthly invoices: $19,661 /month | 1 Half time Slalom Enhance and Operate Contractor |

4. Implementation Fees.  All costs associated with Implementation Services are included below (e.g. configuration, customization, migration, integration, testing, etc.) (the “Implementation Fees”).  All costs are firm fixed.

Bidder must provide detailed pricing and a payment schedule for the implementation of their product.

Implementation Fees will be awarded based on a firm fixed fee. However, for price evaluation purposes, Bidder must provide a detailed breakdown of how Implementation Fees were calculated.

Slalom Implementation Fees & Payment Schedule

| # | Milestone | Associated Milestone Deliverables and Activities | Schedule | Fee |
| --- | --- | --- | --- | --- |
| 1 | Project Planning & Kickoff | High Level Project work plan delivered and accepted by State Project Kickoff Complete | Contract Execution + 30 calendar days Week 1 | $348,466 |
| 2 | Discovery | Current State Assessment Data Migration Tooling Selections Data Migration Plan with acceptance criteria Define Product Roadmap Create Backlog: User Stories Created Validation sessions Final Requirement Validation Document | Week 10 | $448,028 |
| 3 | Build: Sprints 1 & 2 | Final Design Document Setup Test Environment Setup Production Environment Validate Test and Production environments In each Sprint: Create Wireframes, Refined Technical Specifications, Epic/User Story Acceptance Criteria, Backlog Updated, Sprint Acceptance | Week 14 | $445,539 |
| 4 | Build: Sprints 3 & 4 | In each Sprint: Create Wireframes, Refined Technical Specifications, Epic/User Story Acceptance Criteria, Backlog Updated, Sprint Acceptance | Week 18 | $505,276 |
| 5 | Build: Sprints 5 & 6 | In each Sprint: Create Wireframes, Refined Technical Specifications, Epic/User Story Acceptance Criteria, Backlog Updated, Sprint Acceptance | Week 22 | $602,349 |
| 6 | Build: Sprints 7 & 8 | Data Assessment and Mapping Data Extraction Data Transformation Data Cleansing Data Validation and Enrichment Data - Implement Error Handling and Logging Validated Mock data migrations In each Sprint: Create Wireframes, Refined Technical Specifications, Epic/User Story Acceptance Criteria, Backlog Updated, Sprint Acceptance | Week 26 | $647,152 |
| 7 | Build: Sprints 9 & 10 | E2E and UAT Test Plans Setup UAT Test Environment Training: Training Plans Training: Training Materials Training: Logistics Final Implementation Document In each Sprint: Create Wireframes, Refined Technical Specifications, Epic/User Story Acceptance Criteria, Backlog Updated, Sprint Acceptance | Week 30 | $637,196 |
| 8 | End-to-End Testing | Execute E2E Testing Triage and Log Defects Remediate and retest high severity defects Execute Training | Week 33 | $448,028 |
| 9 | UAT Testing | Execute UAT Test Cases Triage and Log Defects Remediate and retest high severity defects Execute Training | Week 36 | $398,247 |
| 10 | Deploy/Go Live | Release Acceptance End User Setup in Production Migrate/Validate Final Data Execute Deployment Plan Perform Smoke/Regression testing and data validation | Week 37 | $497,809 |
| 11 | Post-Production Warranty |  | Production + 120 days | Included at no cost to the State |
| Total Implementation Fee |  |  |  | $4,978,090 |

Below is a breakdown of the implementation costs by scope and feature set for the State’s price evaluation purposes:

| Scope/Feature Set | Implementation Cost |
| --- | --- |
| Centralized Data Management | $1,393,865 |
| Application Interface Data Entry | $348,466 |
| Search Functionality | $149,342 |
| Security & User Management | $199,159 |
| Reports, Dashboards & Ad-Hoc Query | $696,932 |
| Data Explorers | $348,466 |
| Data Migration | $945,837 |
| Integration | $452,078 |
| Training | $443,945 |

5. Postproduction Warranty.  The Contractor must provide a 120 calendar days postproduction warranty at no cost to the State to begin after SOM acceptance of the last production release.  The postproduction warranty will meet all requirements of the contract, including all Support Services identified in Schedule D.

6. Rate Card for Ancillary Professional Services.

| Resource Role | 2023-2024 On-Shore Hourly Rate |
| --- | --- |
| Executive Project Leadership | $295 |
| Program Manager | $255 |
| Project Manager | $195 |
| Salesforce Architect | $255 |
| Senior Salesforce Developer | $210 |
| Junior Salesforce Developer | $170 |
| Data Architect | $240 |
| Senior Data Engineer | $198 |
| Junior Data Engineer | $185 |
| Software Architect | $255 |
| Quality Architect | $225 |
| Senior Quality Engineer | $198 |
| Junior Quality Engineer | $170 |
| Integration Architect | $255 |
| Integration Developer | $210 |
| Senior Quality Engineer | $198 |
| Experience Designer | $195 |
| Data Visualization Architect | $245 |
| Visualization Developer | $195 |
| Senior Training Lead | $265 |
| Training Developer | $195 |

Price proposals must include a fixed-price hourly-rate rate card for ancillary professional services (e.g. future enhancement configuration services) broken down by role (e.g. Solution design architect).  If Bidder differentiates between on-site and remote services, provide pricing for both.

7. Open Source or Third Party Products

The Contractor must identify any open source or third-party products that include a separate licensing fee and will be used in connection with the proposed Solution.

| Product | Price |
| --- | --- |

8. Reserved

9. Additional Pricing Terms

The Contractor is encouraged to offer quick payment terms.  The number of days must not include processing time for payment to be received by the Contractor's financial institution.

Quick payment terms: ___0_____ % discount off invoice if paid within _n/a_days after receipt of invoice.

If Contractor reduces its prices, or offers a lower price to any other entity, private or public, for any of the software or services during the term of this Contract, the State shall have the immediate benefit of such lower prices for new purchases.  Contractor shall send notice to the State’s Contract Administrator with the reduced prices within fifteen (15) Business Days of the reduction taking effect.

Invoice Requirements

All invoices submitted to the State must include: (a) date; (b) purchase order or delivery order; (c) quantity; (d) description of the Solution; (e) unit price; (f) shipping cost (if any); (g) Contractor-generated invoice number and (h) total price.

Travel and Expenses

The State does not pay for overtime or travel expenses