## Attachment C
Attachment C - Draft WBS Structure Optimized - MDHHS | [8 empty] | #VALUE!
WBS |  |  | Description |  |  | Deliverable | Responsible / Accountable | Consulted / Informed | Day from Contract Execution | Notes
1.0 |  |  | Project Planning |  |  | Project Plan to review at Project Kickoff Meeting
| 1.1 |  |  | Project Planning |  | MDHHS Program Plan |  |  | -10
|  | 1.1.1 |  |  | "Draft" Schedule - Resourced |  | CMI Project Manager |  |  | During contract negotiations the CMI Project Manager will establish the "draft" project plan/schedule in Smartsheets. Note: schedule will be created from CMI Implementation Standard
|  | 1.1.2 |  |  | "Draft" Risk Management Plan |  | CMI Project Manager |  |  | During contract negotiations the CMI Project Manager will establish the "draft" risk management plan in Smartsheets. Note: plan will be establish from CMI Implementation Standard
|  | 1.1.3 |  |  | "Draft" Issue Tracking and Resolution Plan |  | CMI Project Manager |  |  | During contract negotiations the CMI Project Manager will establish the "draft" issue tracking and resolution plan in Smartsheets. Note: plan will be established from CMI Implementation Standard
|  | 1.1.4 |  |  | "Draft" Project Reporting / Communicitons |  | CMI Project Manager |  |  | During contract negotiaitons the CMI Project Manager will establish the "draft" project reporting and communications program, inclusive of periodic project reporting, communications model - meetings (agenda/frequencey/attendees), non-reporting updates / communications, etc. Note: reports/communications will be established from CMI Implementation Standard
| 1.2 |  |  | Project Kickoff
|  | 1.2.1 |  |  | Project Kickoff Planning |  | CMI Project Manager |  | -10 | During contract negotiations the CMI Project Manager will establish "draft" Project Kickoff agenda and materials.
[5 empty] | Project Kickoff Review |  | CMI Project Manager | MDHHS Key Stakeholder, Project Manager | +5 | CMI Project Manager will review agenda / materials with MDHHS Project Manager and Key Stakeholders. CMI Project Manager will revise materials, schedule meeting.
[5 empty] | Project Kickoff |  | CMI Project Manager | MDHHS Key Stakeholders, Project Manager, Key Program Staff |  | CMI Project Manager conducts MDHHS Program Kickoff Meeting
2.0 |  |  | Requirements and Design Validation |  |  | Validation sessions, Final Requirement Validation Document, Final Design Document, Final Implementation Document
| 2.1 |  |  | MDHHS "Draft" Functional Documentation |  |  | CMI Project Manager | CMI Product Manager, CMI Product Owners | -10 | During contract negotiations the CMI Project Manager working with the CMI Product Manager and Product Owners to assemble final functional documentation as aligned to the MDHHS Program requirements. Note: These materials will be an optimization of all existing materials.
| 2.2 |  |  | MDHHS "Draft" Technical Documentation |  |  | CMI Project Manager | CMI CTO, CMI Solutions Architect, CMI Cloud Architect | -10 | During contract negotiations the CMI Project Manager working with the CMI Chief Technology Officer, CMI Solutions Architect and CMI Cloud Architect to assemble final functional documentation as aligned to the MDHHS Program requirements. Note: These materials will be an optimziation of existing materials.
| 2.3 |  |  | MDHHS "Draft" Guide |  |  | CMI Project Manager | CMI Training Lead, CMI Product Manager, CMI Lead Service Desk Analyst | -10 | During contract negotiations the CMI Project Manager working with the CMI Training Lead, CMI Product Manager, CMI Lead Service Desk Analyst will assemble "Draft" Training Materials, "Draft" User/Operating Manuals, "Draft" Service Desk Knowledgebase, etc. Note: These materials will be an optimization of all existing materials.
| 2.4 |  |  | Conduct Functional / Technical / Guide Validation Session |  |  | CMI Project Manager | CMI Product Manager, CMI Product Owners, MDHHS Project Manager, MDHHS Key Program Staff | +10 | Conduct validation workshops with Identified MDHHS key stakeholders / subject matter experts
| 2.5 |  |  | Finalize Design / Configuration Specifications |  |  | CMI Project Manager | CMI Product Owners, CMI Architects, CMI Lead Service Desk Analyst | +20 | Conduct final review / signoff of functional, technical and implementation design for the project.
| 2.6 |  |  | Speicifcation Turnover |  |  | CMI Project Manager |  | +30 | CMI Project Manager will transition specifications to the CMI Chief Technology Officer and CMI Product Owners for implementation
3.0 |  |  | Provision environments |  |  | Validate Test and Production environments
| 3.1 |  |  | Establish "Baseline" SIMS MDHHS Solution |  |  | CMI Operations |  | +10 | CMI Operations configures
| 3.2 |  |  | Regression / Compliance Validation |  |  | CMI Operations | CMI QA, CMI Compliance | +25 | CMI QA / Compliance executes comprehensive testing - Functional, DR/BC, etc. of baseline platform.
| 3.3 |  |  | Finalize Environment Observability / Customer Reporting |  |  | CMI Operations |  | +25 | CMI Cloud Operations finalized CSA, APM, DEM and customer reporting
| 3.4 |  |  | Finalize Environment Security Operations |  |  | CMI Operations |  | +25 | CMI CTO finalized transition and operations of CrowdStrike SOC services.
| 3.5 |  |  | Transition Platform for Field Implementation |  |  | CMI Operations | CMI Project Manager, CMI Training Lead
4.0 |  |  | Installation and Configuration of software |  |  | Final Solution and Testing Document
| 4.1 |  |  | Configure Solution to MDHHS Approved Specification |  |  | CM Project Manager | CMI Operations | +45 | Base solution is configured to support MDHHS final specificaitons
| 4.2 |  |  | Configure CMI Service Desk / Knowledgebase for MDHHS Solution |  |  | CM Project Manager | CMI Lead Service Desk Analyst | +45 | Base service desk environment is configured to support MDHHS requirments.
| 4.3 |  |  | Integrated SIMS Auth0 to MDHHS A&A / Validate |  |  | CMI Operations | MDHHS Operations |  | SIMS solution is integrated with MDHHS Authentication solution to support federated specificaitons.
| 4.4 |  |  | Conduct Solution and Service Desk Walkthrough with MDHHS Key Stakeholders / Subject Matter Experts |  |  | CM Project Manager, CMI Training Lead | MDHHS Key Stakeholders, MDHHS Project Manager, MDHHS Key Program Staff | +45 | Full configure solution walkthrough is conducted with MDHHS key stakeholders and users to support orientation for User Acceptance Testing (UAT)
| 4.5 |  |  | Transition Platform for Testing and Acceptance |  |  | CMI Project Manager | MDHHS Project Manager | +45 | SIMS solution is turned over to MDHHS Project Manager (configured to support user access for UAT)
5.0 |  |  | Testing and Acceptance |  |  | Final Test Results Report, Final Training Documentation, Final Acceptance
| 5.1 |  |  | Develop Acceptance Testing Plan / Scenarios |  |  | MDHHS Project Manager, MDHHS Key Program Staff | CMI Project Manager, CMI Training Lead | +30 | MDHHS staff develops UAT plans and test scenarios in anticipation of solution UAT
| 5.2 |  |  | Conduct SIMS Acceptable Testing |  |  | MDHHS Project Manager, MDHHS Key Program Staff | CMI Project Manager, CMI Training Lead | +75 | MDHHS staff conducts UAT tests with support from CMI staffing. Note: preliminary training will be conducted to ensure testing orientation. The CMI Service Desk will be used to receive and track defects / gaps identified by UAT. Daily standups will be conducted by the CMI/MDHHS Project Managers. Daily flash reports will be produced by the CMI Project Manager.
| 5.3 |  |  | Platform Acceptance Signoff |  |  | MDHHS Project Manager, MDHHS Key Program Staff | CMI Project Manager | +75 | Final review / acceptance workshop will be scheduled and conducted by the CMI Project Manager.
| 5.4 |  |  | Finalize MDHHS Training Plan |  |  | CMI Training Lead | CMI Project Manager, MDHHS Key Stakeholders, MDHHS Project Manager, MDHHS Key Program Staff | +30 | CMI Training Lead will collaborate with the CMI Project Manager, MDHHS Project Managers, MDHHS Key Project Stakeholders and MDHHS Key Project Staff to establish a full program training schedule.
| 5.5 |  |  | Finalize MDHHS Training Materials |  |  | CMI Training Lead |  | +45 | CMI Training Lead will optimize SIMS training materials to specific MDHHS configurations.
| 5.6 |  |  | MDHSS Program Training Plan / Materials Approval |  |  | CMI Project Manager / CMI Training Lead | MDHHS Project Manager, MDHHS Key Program Staff | +60 | CMI will conduct a full walkthrough of final training schedule and training materials fro approval
6.0 |  |  | Go-Live Activities |  |  | - Provider / User Training Plan Activities Completed
| 6.1 |  |  | Conduct Provider / End User Training (Complete) |  |  | CMI Training Lead | CMI Project Manager, MDHHS Project Manager, MDHHS Solution Users | +80 | CMI Training Lead will conduct program training as per approved schedule. One (1) training session will be recorded and made available through the CMI Service Desk. All training materials will be made available through the CMI Service Desk.
| 6.2 |  |  | Establish / Approve "Go-Live" Checklist (including cutover validation) |  |  | CMI Project Manager | MDHHS Key Stakeholders, MDHHS Project Manager, MDHHS Key Program Staff | +60 | CMI Project Manager will establish a pre and post "Go-Live" checklist to ensure completeness and comprehensive support of the solution "Go-live" activities and acceptance.
| 6.3 |  |  | Final QA Validation (Regression) / Compliance Validation (DR/BC Testing) |  |  | CMI Operations | CMI Project Manager, MDHHS Project Manager | +75 | CMI QA / Compliance executes final comprehensive testing of the MDHHS solution implementation - Functional, DR/BC, etc. of baseline platform.
| 6.4 |  |  | Mock Go-live Walkthrough |  |  | CMI Project Manager | MDHHS Project Manager, MDHHS Key Program Staff, CMI CTO, CMI Operations, CMI Lead Service Desk Analyst | +80 | CMI Project Manager will schedule a full walkthrough of the "Go-live" checklist (and status).
7.0 |  |  | Go-Live |  |  | Production Cut-over, Services Validation, Cooldown |  |  | '+90 | Complete "Go-live" checklist. Conduct "Max attention" go-live cooldown to address any issues experienced during production cutover.
8.0 |  |  | Post Production Warranty |  |  | Included in the cost of Solution. |  |  |  | Conduct 90 day post production warranty support
9.0 |  |  | Production Support Services |  |  | Ongoing after Final Acceptance.