## Trans In-Out Implementatio
Transition In and Out Plan
Milestone Perspective of Resource Transition
Item | Transition Milestone | Resource | Transition Type | Transition Reference | D-10 | 2024-05-01 | D5 | D10 | D15 | D20 | D25 | D30 | D40 | D45 | D50 | D55 | D60 | D65 | D70 | D75 | D80 | D83 | D90 | 2024-10-01 | 2024-11-01
1 | Notice of Award | CMI Project Manager, CMI Training and Support Lead, CMI Operations / Engineering | In | 1
2 | Project Planning
3 | Contract Execution
4 | Project Kick-off Meeting with MDHHS and Training Vendor | MDHHS Stakeholders, MDHHS Project Manager | In | 2
5 | Requirements and Design Validation | MDHHS Key Staff | In | 3
6 | Provision environments
7 | Installation and Configuration of software
8 | Testing and Acceptance
9 | Go-Live Activities | CMI Operations / Engineering | Out | 4
10 | Go Live
11 | Warranty Period Complete | CMI Project Manager | Out | 5
12 | Pilot Study Start
Transitions
Item | Transition Scope | Transition Steps | Success Criteria | Estimate Duration
1 | CMI Team is assigned to engagement and begins assembling draft materials to expedite ramp of the MDHHS program. These draft materials will be used to support the Project Kickoff Meetings as well as expediting materials for the Requirements and Design Validation workshops. The early assignments will development draft materials based upon the RFP Proposal. | 1 - Assemble CMI customer facing and support team for implementation engagement. 2 - Conduct internal kick-off meeting inclusive of objectives, assignments, RFP proposal review and schedule. 3 - Establish project repositories - SmartSheets, Jira 4 - Establish CMI Service Desk Region - MDHHS 5 - Establish draft materials and place in project repositories for later use. | All draft preparation materials are in respective project repositories. | 2 weeks
2 | Pre-review draft perpetration materials (specifically project management plan - schedule and management plan, risk management plan, issue tracking and resolution plan, project reporting and communications plan, project kick off materials). | 1 - Conduct collaborative review and update project management plan with MDHHS Project Manager to ensure alignment of execution and resourcing. 2 - Conduct collaborative review of project kickoff materials with MDHHS Project Manager and Key Stakeholders to ensure alignment on program objectives and communications. 3 - Conduct project kick-off meeting with MDHHS Project Manager, Key Stakeholders and Key Staff. | Full aligned and agreed upon project management plan is published. Project Kick-off Meeting is executed. | 1 week
3 | Onboard Project Key Staff members with initial review of draft solution requirements and design materials. Ensure initial alignment with the solution to form the basis for the requirements and design review workshops. | 1 - Conduct initial orientation meetings with materials and base solution demonstration to ensure MDHHS Key Staff understanding: a) functional solution review - user manuals/guides, solution demonstrations, etc. b) technical solution review - architecture and design reviews focusing on integration needs c) training material reviews d) CMI Service Desk review. | Project Key Staff has understanding of solution attributed to support requirements and design workshops | 1 week
4 | Conduct final operational review and checklist to move MDHHS solution to production readiness. | 1 - Conduct full readiness checklist review with CMI Service Desk Staff, MDHHS Key Staff to ensure operational readiness of CMI Service Desk 2 - Conduct full project ticketing and tracking to ensure solution is ready for production and warranty period. | SIMS Solution and support services are ready for full production operations. | 2 weeks
5 | Conclude implementation efforts for MDHHS Solution by successful completion of the Warranty period. | 1 - Conduct warranty closure reviews to complete warranty period. 2 - Ensure transition of support for MDHHS to the CMI Service Desk. CMI Training and Service Support Lead will remain with engagement. | Warranty period is successfully completed with no identified issues. MDHHS is successfully transitioned to CMI Service Desk for support | 90 days

## Trans In-Out Contract Close
Transition In and Out Plan
Milestone Perspective of Resource Transition
Item | Transition Milestone | Resource | Transition Type | Transition Reference
1 | Contract Concluded or Contract Termination | CMI Operations / Engineering, MDHHS Project Key Staff | Out | 1
Transition Out
Item | Transition Scope | Transition Steps | Success Criteria | Estimate Duration
1 | CMI SIMS Data for MDHHS has been successfully delivered to MDHHS. | 1 - CMI collaborates with MDHHS Key Staff to determine requirements for system data migration. 2 - CMI reviews data model and catalog/dictionary with MDHHS Key Staff 3 - CMI assist MDHHS Key Staff with receipt and using solution data (assuming transition to another system) | SIMS Solution data has been successfully migrated to MDHHS to support go forward needs | 2 - 4 weeks