## Sheet1
Bidder Budgeting document: a.—e.
Michigan Wildlife Council — Tasks | Timing | Staff Resources | Estimated Hours | Hourly Rate | Estimated Total
Campaign Management Services
Account Management
• Management and oversight of all deliverables associated with the campaign | Jan. 2025-Jan. 2026 | Account Manager | 440 | Monthly Fixed Fee: $4,766 | 57200
• Project plan development, updates and management
• Coordination around biweekly, quarterly meetings with MWC/state representatives
• Ongoing communications with MWC, MWC subcommittee, DNR key staff via Basecamp (plans, approvals, creative review)
• Billing and financial management
• Monthly and periodic status reports
Quarterly Meetings
• Development of agendas, preparation and distribution of materials for review
• Participation and facilitation of presentations, reviewing data and sharing stories
• Meeting summaries
Annual Account Management Fee |  |  |  |  | 57200
Additional Presentations | As requested
• Campaign presentations and reporting to Michigan Department of Natural Resources, Natural Resources Commission, Legislature and other relevant agencies, as requested by Michigan Wildlife Council |  | Coordinated presentations and associated resources/staff will be identified and managed at the discretion and approval of the Council
Development of Annual Communications/Marketing Plan
Set Campaign Strategy for Reaching Target Audiences | Feb. 2025-Mar. 2025 | Strategic Planning Director | 10 | 140 | 1400
• Engagement of strategy, creative and planning teams in "green light" session |  | Strategic Planner | 10 | 140 | 1400
• Messaging and positioning considerations to align with audience(s) |  | Senior Strategist | 10 | 140 | 1400
• Identify innovative, creative and cost-effective ways to reach target audience
• Development of campaign strategic brief to inform planning
Outline Annual Communications/Marketing Plan | Mar. 2025-Apr. 2025 | Strategic Planning Director | 20 | 140 | 2800
• Creation of high-level integrated plan supported by statewide research |  | Strategic Planner | 15 | 140 | 2100
• Present plan recommendations to Council |  | Senior Strategist | 5 | 140 | 700
Annual Campaign Management Services Budget (Inclusive of Account Management Fee) |  |  |  |  | 67000
Market Research
Audit of Current Data and Research Plan Recommendations | Jan. 2025-Feb. 2025 | Strategic Planning Director | 5 | 140 | 700
• Analysis of primary research findings and prior-year campaign data |  | Research Manager | 10 | 140 | 1400
• Outline findings and how they’ve fulfilled metrics of success |  | Strategic Planner | 5 | 140 | 700
• Outline and present research recommendations to MWC on primary and secondary target audiences |  | Digital Specialist | 5 | 140 | 700
Identify Metrics of Success |  | Strategic Planning Director | 5 | 140 | 700
• Assimilate all ongoing tracking and monitoring information (KPIs) |  | Research Manager | 10 | 140 | 1400
• Audience definition and segmentation as applicable |  | Senior Strategist | 5 | 140 | 700
• Update metrics of success and outline strategies for moving the needle on increasing the public’s awareness and understanding of the values of hunting, fishing and trapping for impending annual campaign |  | Strategic Planner | 5 | 140 | 700
• Development of campaign strategic brief to inform planning
Michigan Wildlife Council — Tasks | Timing | Staff Resources | Estimated Hours | Hourly Rate | Estimated Total
Primary Research: Maximum Difference Analysis | Jan. 2025-Feb. 2025
• Draft online survey from qualitative insights from previous campaign |  | Strategic Planning Director | 5 | 140 | 700
• Audience outreach/recruitment coordination |  | Research Manager | 10 | 140 | 1400
• Quantitative online survey fielded, uncovering audiences' preferences to key messaging and creative concepts |  | Senior Strategist | 10 | 140 | 1400
• Analysis of similarities and differences in preferences between target audience groups; development of report |  | Creative Director | 10 | 140 | 1400
• Outline findings and present to Council
Primary Research: Qualitative Research | Feb. 2025-Apr. 2025
• Draft discussion guide |  | Research Manager | 15 | 140 | 2100
• Audience definition and outreach/recruitment coordination |  | Senior Strategist | 5 | 140 | 700
• Direct, authentic dialogue with identified target audiences through interactive exercises surrounding campaign messaging, recall and individual perceptions/attitudes toward hunting/fishing/trapping |  | Creative Director | 5 | 140 | 700
• Coordination and facilitation with research partner
• Analysis and reporting
• Development of report
• Outline findings and present to Council
Primary Research: Statewide Survey | Nov. 2025-Feb. 2026
• Questionnaire review and revisions |  | Research Manager | 25 | 140 | 3500
• Coordination and facilitation with research partner |  | Research Coordinator | 10 | 140 | 1400
• Survey programming — Research Partner (mixed methodology — phone, text, web)
• Survey retesting — Güd and Research Partner
• Survey deployment and fielding
• Data cleaning — Research Partner
• Data analysis and reporting
• Presentation development; development of final report
• Outline findings and present to Council
Secondary Research and Tracking | Jan. 2025-Jan. 2026
• Ongoing monitoring/tracking of emerging national and state wildlife issues |  | Research Manager | 20 | 140 | 2800
• Research team to report out to all implementation/marketing teams |  | Research Coordinator | 30 | 140 | 4200
Event Intercept Interviews (As applicable) | As applicable
• Draft interview guide based on planned in-person event(s) |  | Coordinated engagement and associated resources/staff at events will be identified and managed at the discretion and approval of the Council
• One-on-one engagement with event attendees (live/in-person conversations or short survey on device/QR code)
Primary Research: Maximum Difference — Direct Expense: Research Partner costs that include online survey programming, recruitment, fielding, data clearing and tabulation |  |  |  |  | 23000
Primary Research: Statewide Survey — Direct Expense: Research Partner costs that include online survey programming, recruitment, fielding, testing, data clearing and tabulation |  |  |  |  | 65000
Primary Research: Qualitative Research — Direct Expense: Research Partner costs that include survey programming, recruitment, facilities, moderation, testing and tabulation |  |  |  |  | 20700
Annual Market Research Budget Total |  |  |  |  | 136000
Michigan Wildlife Council — Tasks | Timing | Staff Resources | Estimated Hours | Hourly Rate | Estimated Total
Campaign Messaging and Implementation
Creative Messaging and Campaign Concept (Creative Services Fee) |  |  |  |  | 21700
Development of creative brief based on campaign strategy | Feb. 2025-Apr. 2025
• Creative team is launched from the approved strategic/campaign brief |  | Creative Director | 35 | 140 | 4900
• Audience-specific research reviewed; exploration of new messaging and creative concepts as applicable |  | Art Director | 40 | 140 | 5600
Campaign Concept Development |  | Graphic Designer | 40 | 140 | 5600
• Development of three (3) creative concepts for MWC review |  | Strategic Planning Director | 20 | 140 | 2800
• Presentation of concepts to full Council for approval |  | Senior Strategist | 20 | 140 | 2800
One (1) concept is taken to final art/script, reviewed and approved by the Council and implemented in all campaigns and with messaging aimed toward their appropriate target audiences to meet goals and outcomes.
Development of All Campaign Assets (Creative Services Fee) |  |  |  |  | 122500
• Account manager launches creative team based on approved plan and primary research data to develop campaign assets | Spring and fall 2025 | Creative Director | 300 | 140 | 42000
• Key specialists work on development of campaign assets to include social, digital, PR, content, outdoor, videos, radio, etc. (Many assets developed matching specifications from media vendors, in multiple sizes and orientations) |  | Art Director | 275 | 140 | 38500
• Campaign deliverables are refined and revised and final assets are developed for campaign launch; final reviews with MWC subcommittee and final reviews by Güd team |  | Graphic Designer | 150 | 140 | 21000
• Approved deliverables are trafficked to the appropriate media platforms |  | Copywriter | 150 | 140 | 21000
Campaign Implementation | Spring, fall and winter 2025 | Strategic Planning Director | 45 | 140 | 6300
• Social Engagement: Management of organic social engagement, scheduling and publishing organic posts across all social media channels, monitoring and responses (Twitter, Facebook, Instagram, LinkedIn, etc.); also includes oversight of paid influencers sharing key messages |  | Senior Strategist | 50 | 140 | 7000
• Digital: Search terms, management of digital engagement with online content |  | Strategic Planner | 50 | 140 | 7000
• Website: Ongoing website maintenance including backups, plug-in and security updates, and improvement of search engine optimization |  | Implementation Manager | 175 | 140 | 24500
• Public Relations/Content: Statewide media outreach, news conferences, legislative meetings, content development; creation of organic social media calendar; development of newsletters |  | Executive Producer | 215 | 140 | 30100
• Events/Partnership: Development, planning and organization of events and partnership program |  | Production Coordinator | 172 | 140 | 24080
• Presentations: Development of content to share from reports, stories, engagement, etc. |  | Public Relations Manager | 116 | 140 | 16240
|  | Digital Media Specialist | 150 | 140 | 21000
|  | Community Engagement Specialist | 75 | 140 | 10500
|  | Full Stack Developer | 65 | 140 | 9100
|  | Resource Manager | 45 | 140 | 6300
Direct Expense: D, E & I Consultation and Support |  |  |  |  | 10000
Outside Production Direct Expense: Video Production Support, Talent Fees, Licensing Fees, Image Fees, Staging costs, talent agency fees, original music open and other miscellaneous expenses involved in filming (e.g., mileage, food, lodging) |  |  |  |  | 55000
Annual Campaign Messaging & Implementation Budget (Inclusive of Creative Services Fee) |  |  |  |  | 371320
Michigan Wildlife Council — Tasks | Timing | Staff Resources | Estimated Hours | Hourly Rate | Estimated Total
Paid Media
Development of Media Plan for All Campaigns | Ongoing
• Media team is launched from the approved strategic/campaign brief |  | Strategic Planner, Media Manager, Media Buyer, Media Coordinator, Resource Manager, Digital Specialist | 450 | N/A | 0
• Collaboration between research, strategy and implementation teams | Ongoing | * Güd Marketing will present the initial plan at the Q2 full-Council meeting for Council approval; revisions, additions and/or alterations will also be presented and approved at the Q3 full-Council meeting for the remainder of the year
• Audience-specific media research conducted; exploration of new platforms and media innovations; development of media impact strategy
• Engage media partners for proposals including added-value considerations
• Development of a comprehensive media plan for all campaigns and their appropriate target audiences, messages, message strategies and communications vehicles designed to meet goals and outcomes
• Present plan recommendations to Council*
Campaign Optimization and Reporting | Ongoing monitoring & optimization; reporting two months after each buy
• Monitor and analyze media metrics and campaign analytics
• Provide a final report of base buy (plus bonus weight) 60 days after media buy and bonus have aired; return on investment included in report
Potential Paid Media Options for 2025 Campaign
TV/Digital Video |  |  |  |  | 206750
Outdoor |  |  |  |  | 49620
Radio/Digital Audio |  |  |  |  | 165000
Paid Social Media |  |  |  |  | 239830
Influencer Marketing |  |  |  |  | 40250
Event Marketing/Sponsorships |  |  |  |  | 107690
Print |  |  |  |  | 16540
Annual Paid Media Budget Total |  |  |  |  | 825680
Total Annual Campaign Budget: $1,400,000.00
3-Year Total Budget: $4,200,000.00
f. Billing Summary by Month (Estimated) |  | Estimated Monthly Totals
2025-01-01 |  | 68989
Account Management | 4766
Research | 4200
Paid Media | 27522.66
Outside Costs (reseach) | 32500
2025-02-01 |  | 40416
Account Management | 4766
Annual Communications/Marketing Plan | 4900
Campaign Messaging and Implementation | 10850
Research | 4900
Outside costs (research) | 15000
2025-03-01 |  | 73228
Account Management | 4766
Annual Communications/Marketing Plan | 4900
Research | 5500
Campaign Messaging and Implementation | 27062
Outside Costs (reseach) | 18000
Outside Costs (campaign implementation) | 13000
2025-04-01 |  | 89741
Account Management | 4766
Research | 2500
Campaign Messaging and Implementation | 31252
Paid Media | 27522.66
Outside Costs (reseach) | 10700
Outside Costs (campaign implementation) | 13000
2025-05-01 |  | 77041
Account Management | 4766
Research | 500
Campaign Messaging and Implementation | 31252
Paid Media | 27522.66
Outside Costs (campaign implementation) | 13000
2025-06-01 |  | 93757
Account Management | 4766
Research | 500
Campaign Messaging and Implementation | 47968
Paid Media | 27522.66
Outside Costs (campaign implementation) | 13000
2025-07-01 |  | 286415
Account Management | 4766
Research | 500
Campaign Messaging and Implementation | 47968
Paid Media | 220181.33
Outside Costs (campaign implementation) | 13000
2025-08-01 |  | 256699
Account Management | 4766
Research | 500
Campaign Messaging and Implementation | 31252
Paid Media | 220181.33
2025-09-01 |  | 256699
Account Management | 4766
Research | 500
Campaign Messaging and Implementation | 31252
Paid Media | 220181.33
2025-10-01 |  | 64041
Account Management | 4766
Research | 507
Campaign Messaging and Implementation | 31252
Paid Media | 27522.66
2025-11-01 |  | 51851
Account Management | 4766
Research | 3350
Campaign Messaging and Implementation | 16212
Paid Media | 27522.66
2025-12-01 |  | 41123
Account Management | 4766
Research | 3857
Outside Costs (reseach) | 32500
g. Outside Costs (pass-through) Pricing & Value Explanation: · Primary Research Subcontractors · Video Production Support, Talent Fees, Licensing Fees, Image Fees, Staging costs · DE&I consultants · Media Güd Marketing’s staff of 45+ professionals will accomplish the majority of the MWC RFP's requirements. However, we align ourselves with key partners (subcontractors) to add value to our service delivery, such as research, DE&I, video production support, talent fees, media, etc. Once the planning phase is completed and a direction is approved, Güd Marketing’s in-house Delivery Director, along with key Directors (e.g., Research Manager, Creative Director and Strategic Planner), evaluates the pool of possible partners/subcontractors that may be required to deliver the best value and quality to the State of Michigan.
For MWC, we know that we need a strong research partner with experience providing statewide primary research to understand attitudes toward natural resources and outdoor recreation issues. Research pricing is estimated based on the requirements outlined in the RFP as well as requests from the MWC council. The value the State receives is the reliability and statistical accuracy required for the MWC campaign evaluation. In some cases, additional support may be required to execute creative and deliverables (e.g., for urgent requests that demand quick action). In these instances, Güd Marketing will consider partners that have reliably delivered for past projects as well as new vendors who may offer greater value. We’ll evaluate partners based on price, experience, timing and, as always, maximizing the MWC’s investment. We’ll negotiate media placements according to the approved campaign plan to procure the best deals, added value and innovation. We’ll access vendor partner proposals with a critical lens and make selections that provide the best value to support us in delivering on the MWC’s goals. Working with a broad pool of media partners, our team will continue to seek value-added placements of at least 25% and up to 40% of the GRP goal in our proposed media buy.