## Sheet1
Michigan Wildlife Council 2025
|  |  | 2025 | [52 empty] | 2026
|  |  | Jan. |  |  |  |  | Feb. |  |  |  | Mar. |  |  |  |  | Apr. |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug. |  |  |  |  | Sept. |  |  |  | Oct. |  |  |  | Nov. |  |  |  |  | Dec. |  |  |  | Jan. |  |  |  | Feb.
Task | Resources | Hours | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23
Account Management
• Updates and revisions to work plan | Account Manager | 440
• In-person kick-off meeting with MWC and State Representatives
• Ongoing communications with MWC, DNR, project manager and subcommittee (plans, approvals, creative review)
• Billing and financial management
• Monthly and periodic status reports
• Management and oversight of all deliverables associated with the campaign
• Preparation and facilitation of all quarterly meetings
Anticipated outcomes: Detailed work plans, monthly and periodic status reporting, proactive account management (timelines/deadlines, approvals, etc.), budget management and documentation, meeting coordination and facilitation and overall issue resolution as needed.
1. LISTEN, LEARN & LEAD
Establish strong lines of communication with MWC and share an understanding of goals and priorities
Audit of current data and research plan recommendations
• Analysis of primary research findings and prior year campaign data | Strategic Planning Director | 5
• Outline findings and how they’ve fulfilled metrics of success | Research Manager | 10
• Outline research findings and methodology recommendations for primary and secondary target audiences | Senior Strategist | 5
| Strategic Planner | 5
Anticipated outcomes: Compilation of statewide research insights to support the development of the annual communications/marketing plan; presentation for the approval of research methodologies to be conducted in the upcoming campaign year
Identify Metrics of Success
• Assimilate all ongoing tracking and monitoring information (KPI) | Strategic Planning Director | 5
• Audience definition and segmentation as applicable | Research Manager | 10
• Update metrics of success and outline strategies for moving the needle on increasing the public’s awareness and understanding of the values of hunting, fishing and trapping for impending annual campaign | Senior Strategist | 5
• Development of campaign strategic brief to inform planning | Strategic Planner | 5
Anticipated outcomes: Metrics identified/updated, audiences defined and refined, insights collected to inform planning efforts (strategic brief)
Quarterly Meeting — Q1
Anticipated outcomes: Research report out from previous campaign year; final media report out from previous campaign year; identify metrics of success for 2025 — clarity on direction and audience of focus; alignment on goals and priorities for 2025 |  |  | The Q1 full-council meeting will allow for an opportunity to establish absolute understanding and alignment between Güd Marketing and the council regarding priorities/goals, roles, timing and key milestones. The meeting will also allow for review of prior year campaign highlights and research insights to help inform high-level recommendations for the year ahead.
|  |  | 2025 | [52 empty] | 2026
|  |  | Jan. |  |  |  |  | Feb. |  |  |  | Mar. |  |  |  |  | Apr. |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug. |  |  |  |  | Sept. |  |  |  | Oct. |  |  |  | Nov. |  |  |  |  | Dec. |  |  |  | Jan. |  |  |  | Feb.
Task | Resources | Hours | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23
2. DISCOVER THE WHY — RESEARCH PHASE
Learn about the audiences
Primary Research: Maximum Difference Analysis
• Draft online survey from qualitative insights from previous campaign | Strategic Planning Director | 5
• Audience outreach/recruitment coordination | Research Manager | 10
• Quantitative online survey fielded, uncovering audiences' preferences to key messaging and creative concepts | Senior Strategist | 10
• Analysis of similarities and differences in preferences between target audience groups; development of report | Creative Director | 10
• Outline findings and present to council
Anticipated outcomes: Compilation of statewide research insights to support the development of the annual communications/marketing plan; presentation for the approval of research methodologies to be conducted in the upcoming campaign year
Primary Research: Qualitative Research
• Draft discussion guide | Research Manager | 15
• Audience definition and outreach/recruitment coordination | Senior Strategist | 5
• Direct, authentic dialogue with identified target audiences through interactive exercises surrounding campaign messaging, recall and individual perceptions/attitudes toward hunting/fishing/trapping | Creative Director | 5
• Coordination and facilitation with research partner
• Analysis and reporting
• Development of report
• Outline findings and present to council
Anticipated outcomes: Qualitative insights from target audiences; report presented to council in findings report.
Primary Research: Statewide Survey
• Questionnaire review and revisions | Research Manager | 25
• Coordination and facilitation with research partner | Research Coordinator | 10
• Survey programming – Research Partner (phone, text, web)
• Survey retesting – Güd and Research Partner
• Survey deployment and fielding
• Data cleaning – Research Partner
• Data analysis and reporting
• Outline findings and present to council
Anticipated outcomes: Full statewide survey findings report
Secondary Research and Tracking
• Ongoing monitoring/tracking of emerging national and state wildlife issues | Strategic Planning Director | 20
• Research team to report out to all implementation/marketing teams | Research Manager | 30
Anticipated outcomes: Periodic reporting on key findings
Event Intercept Interviews (As applicable)
• Draft interview guide based on planned in-person event(s)
• One-on-one engagement with event attendees
|  |  | 2025 | [52 empty] | 2026
|  |  | Jan. |  |  |  |  | Feb. |  |  |  | Mar. |  |  |  |  | Apr. |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug. |  |  |  |  | Sept. |  |  |  | Oct. |  |  |  | Nov. |  |  |  |  | Dec. |  |  |  | Jan. |  |  |  | Feb.
Task | Resources | Hours | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23
3. UNCOVER SOLUTIONS — PLANNING PHASE
Develop a communications/marketing plan to reach MWC's goals
Development of Annual Communications/Marketing Plan
Develop Campaign Strategy Plan for Reaching Target Audiences | Strategic Planning Director | 10
• Engagement of strategy, creative and planning teams in "green light" session | Strategic Planner | 10
• Messaging and positioning considerations to align with audience(s) | Senior Strategist | 10
• Identify innovative, creative and cost-effective ways to reach target audience
Anticipated outcomes: Alignment on campaign strategy plan and defined audience segmentation
Outline Annual Communications/Marketing Plan | Strategic Planning Director | 20
• Creation of high-level integrated plan supported by statewide research | Strategic Planner | 15
• Present plan recommendations to council | Senior Strategist | 5
Anticipated outcomes: Cost-efficient, comprehensive statewide annual communications/marketing plan that reaches target audiences
Creative Messaging Strategies and Campaign Concept
Development of creative brief based on campaign strategy | Creative Director | 35
• Creative team is launched from the approved strategic/campaign brief | Art Director | 40
• Audience-specific research reviewed; exploration of new messaging and creative concepts as applicable | Graphic Designer | 40
Campaign Concept Development | Strategic Planning Director | 20
• Development of three (3) creative concepts for MWC review | Senior Strategist | 20
• Presentation of concepts to full council for approval
One (1) concept is taken to final art/script; reviewed and approved by the council and implemented in all campaigns and with messaging aimed toward their appropriate target audiences to meet goals and outcomes.
Anticipated outcomes: Approved campaign concept and messaging strategies for annual campaign
Quarterly Meeting — Q2
Anticipated outcomes: Presentation of the recommended plan and campaign concept/messaging strategies; media plan recommendations and strategy for the campaign |  |  | The Q2 full-council meeting will see Güd Marketing presenting the annual communications/marketing plan for review, discussion and approval. Additionally, the council will see refreshed, evolved and/or new creative concepts for review and approval.
4. IGNITE CHANGE — DEVELOPMENT + IMPLEMENTATION
Develop and implement all communication tasks and deliverables
Development of Paid Media Plan for All Campaigns
• Media team is launched from the approved strategic/campaign brief | Strategic Planner, Media Manager, Media Buyer, Media Coordinator, Resource Manager, Digital Specialist | 450
• Collaboration between research, strategy, and implementation teams
• Audience-specific media research conducted; exploration of new platforms and media innovations; development of media impact strategy
• Engage media partners for proposals including added-value considerations
|  |  | 2025 | [52 empty] | 2026
|  |  | Jan. |  |  |  |  | Feb. |  |  |  | Mar. |  |  |  |  | Apr. |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug. |  |  |  |  | Sept. |  |  |  | Oct. |  |  |  | Nov. |  |  |  |  | Dec. |  |  |  | Jan. |  |  |  | Feb.
Task | Resources | Hours | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23
• Development of a comprehensive media plan for all campaigns and their appropriate target audiences, messages, message strategies and communications vehicles designed to meet goals and outcomes
• Presentation of concepts to full council for approval*
* Güd Marketing will present the initial plan at the Q2 full council meeting for council approval; revisions, additions, and/or alterations will also be presented and approved at the Q3 full council meeting for the remainder of the year
Anticipated outcomes: Media plan recommendations and strategy for the campaign.
Development of All Campaign Assets
• Account managers launches creative team based on approved plan and primary research data to develop campaign assets | Creative Director | 300
• Key specialists work on development of campaign assets to include social, digital, PR, content, outdoor, videos, radio, etc. (many assets developed matching specifications from media vendors, in multiple sizes and orientations | Art Director | 275
• Campaign deliverables are refined and revised and final assets are developed for campaign launch; final reviews with MWC subcommittee and final reviews by Güd team | Graphic Designer | 150
• Approved deliverables are trafficked to the appropriate media platforms | Copywriter | 150
Anticipated outcomes: Deliverables reviewed/approved by subcommittee and trafficked to appropriate media outlets on time and on budget
Campaign Implementation
• Social Engagement: Management of organic social engagement, scheduling and publishing organic posts across all social media channels, monitoring and responses (Facebook, Instagram, LinkedIn, etc.) Also includes oversight of paid influencers sharing key messages | Strategic Planning Director | 45
• Digital: Search terms, management of digital engagement with online content | Senior Strategist | 50
• Website: Ongoing website maintenance including back-ups, plug-in and security updates, and improvement of search engine optimization | Strategic Planner | 50
• Public Relations/Content: Statewide media outreach, news conferences, legislative meetings, content development. Creation of organic social media calendar; Development of newsletters | Implementation Manager | 175
• Events/Partnership: Development, planning and organization of events and partnership program | Executive Producer | 215
• Presentations: Development of content to share from reports, stories, engagement, etc. | Production Coordinator | 172
| Public Relations Manager | 116
| Digital Media Specialist | 150
| Community Engagement Specialist | 75
| Full Stack Developer | 65
| Resource Manager | 45
Anticipated outcomes: Strategic engagement of the right audiences, with the right message, at the right time and platform
Additional Presentations
• Campaign presentations and reporting to Michigan Department of Natural Resources, Natural Resources Commission, legislature and other relevant agencies, as requested by Michigan Wildlife Council | As requested | N/A
|  |  | 2025 | [52 empty] | 2026
|  |  | Jan. |  |  |  |  | Feb. |  |  |  | Mar. |  |  |  |  | Apr. |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | Aug. |  |  |  |  | Sept. |  |  |  | Oct. |  |  |  | Nov. |  |  |  |  | Dec. |  |  |  | Jan. |  |  |  | Feb.
Task | Resources | Hours | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23
Quarterly Meeting — Q3
Anticipated outcomes: Quarterly updates including available media reporting, presentations on campaign progress (retrospective and upcoming milestones), where we’re moving the needle; research setup |  |  | The Q3 full-council meeting will allow Güd Marketing to present on the campaign in progress and what's to come for the Fall/Winter. Q3 also presents an opportunity to discuss known research results, metrics and any proposed changes to the communications/marketing plan for the remainder of the year.
5. MEANINGFUL, MEASURABLE IMPACT — TRACKING + REPORTING
Monitor, optimize and report
Campaign Optimization and Reporting
• Monitor and analyze media metrics and campaign analytics | Media Team | N/A
• Provide a final report of base buy (plus bonus weight) 60 days after media buy and bonus have aired; return on investment included in report
Anticipated outcomes: Up-to-date analytics, insights and recommendations; real-time performance monitoring; and in-flight adjustments based on performance. |  |  | Once our team has implemented the communication/marketing plan’s strategies, tactics and deliverables, we’ll continue to work with the MWC to provide expert recommendations and ongoing support.
Quarterly Meeting — Q4
Anticipated outcomes: Presentation focused on Fall campaign (in progress); high-level results from spring/summer campaign — media, research insights and metrics |  |  | During the Q4 full-council meeting our team will present high-level metric results from the spring/summer/fall. The full annual report of campaign performance is then presented at the 2026 Q1 full-Council meeting (est. Feb. 2026).