## 4.2 Project Timeline
Task | Sub Task | Task Detail | Responsible Key Staff | Start Date | End Date | Duration | Predecessors
Fusion92 Sample Project Plan
Transition & Program Onboarding
Transition Period | Contract award notification | Anticipated contract begin date (Transition begins) | Account Manager | 2024-12-10 | 2024-12-10 | 1d
Transition Period | Review & Documentation | Review existing contracts and documentation | Contractor Representative, Account Manager, Project Manager | 2024-12-11 | 2024-12-24 | 10d | 3
Transition Period | Review & Documentation | Compile all relevant data and requirements from current operations | Contractor Representative, Account Manager, Project Manager | 2024-12-25 | 2024-12-31 | 5d | 4
Transition Period | Stakeholder Engagement | Identify key stakeholders | Contractor Representative, Account Manager | 2025-01-01 | 2025-01-03 | 3d | 5
Transition Period | Stakeholder Engagement | In-Person Kick Off Meeting to Discuss Transition Plans (within 15 days of Effective Contract Date) | Contractor Representative, Account Manager, Project Manager | 2025-01-06 | 2025-01-06 | 1d | 6
Transition Period | Stakeholder Engagement | Develop Task Breakdown | Contractor Representative, Account Manager, Project Manager | 2025-01-07 | 2025-01-09 | 3d | 7
Transition Period |  | Develop Transition Project Plan - Against Identified Task | Contractor Representative, Account Manager, Project Manager | 2025-01-10 | 2025-01-14 | 3d | 8
Transition Period | Compliance & Procedures | Verify compliance and establish contract needs | Contractor Representative | 2025-01-15 | 2025-01-17 | 3d | 9
Transition Period | Compliance & Procedures | Draft and Finalize Statement of Work | Contractor Representative, Account Manager, Project Manger | 2025-01-20 | 2025-01-31 | 10d | 10
Transition Period | Compliance & Procedures | Identify Social Ad Manager Ownership (SOM or Fusion92) | Contractor Representative, Account Manager, Ad Ops | 2025-02-03 | 2025-02-03 | 1d | 11
Transition Period | Resourcing | Identify resources and finalize key personnel/assign task | Contractor Representative | 2025-02-04 | 2025-02-10 | 5d | 12
Transition Period | Risk Management & Contingency Planning | Identify potential risks associated with the transition | Contractor Representative, Account Manager, Project Manager | 2025-02-11 | 2025-02-24 | 10d | 13
Transition Period | Compliance & Procedures | Setup collaborative Sharepoint and Confluence pages for both internal and external team communicatons and file share | Project Manager | 2025-02-25 | 2025-02-26 | 2d | 14
Transition Period | Compliance & Procedures | Establish Transition Status Meetings, Status Tracker with identified Transition Task and owners | Account Manager | 2025-02-27 | 2025-02-27 | 1d | 15
Transition Period | Risk Management & Contingency Planning | Develop and document contingency plans | Account Manager, Project Manager | 2025-02-28 | 2025-03-06 | 5d | 16
Transition Period | Final Review & Preparation | Final review of all transition plans and readiness for contract start | Account Manager | 2025-03-07 | 2025-03-07 | 1d | 17
Transition Period | Final Review & Preparation | Sign-off from outgoing contractor - confimring all transaction acitivities are complete | Contractor Representative, Account Manager | 2025-03-10 | 2025-03-10 | 1d | 18
1.1.H Implementation | Review existing campaigns and performance reports. | Collect and compile all existing campaigns and performance data | Data Analyst | 2025-03-11 | 2025-03-17 | 5d | 19
1.1.H Implementation | Review existing campaigns and performance reports. | Conduct initial assessment to identify areas of focus | Media Planner | 2025-03-18 | 2025-03-20 | 3d | 20
1.1.H Implementation | Detailed analysis on existing campaigns and performance reports | Analyze performance reports to identify trends and inefficiencies | Data Analyst | 2025-03-21 | 2025-03-27 | 5d | 21
1.1.H Implementation | Strategy development for existing campaigns | Develop strategies to optimize the existing media mix | Media Planner | 2025-03-28 | 2025-04-03 | 5d | 22
1.1.H Implementation | Strategy development for existing campaigns | Create a detailed recommendation report | Media Planner | 2025-04-04 | 2025-04-08 | 3d | 23
1.1.H Implementation | Client Presentation & Feedback | Present findings and recommendations | Account Manager, Media Planner | 2025-04-09 | 2025-04-09 | 1d | 24
1.1.H Implementation | Implementation Planning | Plan the implementation of accepted recommendations | Account Manager, Media Planner | 2025-04-10 | 2025-04-16 | 5d | 25
1.1.H Implementation | Confirm Social Ad Manager | Option A: Fusion92 to run ads out of existing ads account - ads account ID required for F92 to request access Option B: F92 owns ad account under F92 business manager - request access | Account Manager | 2025-04-17 | 2025-04-21 | 3d | 26
Services Begin | Contract start | Services Begin | All Teams | 2025-06-08 | 2025-06-08 | 1d
1d
Market Research
1.1.B Market Research | Stakeholder interviews | Conduct stakeholder interviews with key MWC members | Researcher | 2025-06-09 | 2025-06-26 | 14d | 28
1.1.B Market Research | Audience profiling | Conduct audience profiling research using existing research, syndicated sources and Experian profiling | Media planner/researcher | 2025-06-27 | 2025-07-10 | 10d | 31
1.1.B Market Research | Qualitative creative testing | Conduct recommended discsussion groups | Researcher/research partner | 2025-10-29 | 2025-12-09 | 30d | 63
1.1.B Market Research | Quantitative brand tracking research | Collaborate with MWC and preferred provider to conduct yearly measurement | Researcher | 2025-10-29 | 2025-12-30 | 45d | 63
Campaign Management Services
1.1A Communications/Marketing Plan | Determine success measurement | Determine which of the research questions will be our KPI for success and which will be secondary measures | Researcher | 2025-07-11 | 2025-07-17 | 5d | 32
1.1A Communications/Marketing Plan | Identify audiences | Agree upon key audiences for communications | Media Planner | 2025-07-18 | 2025-07-31 | 10d | 37
1.1A Communications/Marketing Plan | Audience profiling | Gain deep understanding using tracking study and syndicated research | Media planner | 2025-08-01 | 2025-08-14 | 10d | 38
1.1A Communications/Marketing Plan | Communicatons Planning | Communication Brief Development | Account Manager, Researcher, Media Planner | 2025-08-15 | 2025-08-21 | 5d | 39
1.1A Communications/Marketing Plan | Communications Planning | Communication Brief Client Sign-Off | Account Manager | 2025-08-22 | 2025-08-26 | 3d | 40
1.1A Communications/Marketing Plan | Media Planning | Media Planning Kick-Off | Account Manager | 2025-08-27 | 2025-08-27 | 1d | 41
1.1A Communications/Marketing Plan | Media Planning | Develop media strategy | Media Planner | 2025-08-28 | 2025-09-24 | 20d | 42
1.1A Communications/Marketing Plan | Content Strategy | Develop Content Strategy | Content Strategist | 2025-08-27 | 2025-09-23 | 20d | 41
1.1A Communications/Marketing Plan | Media Planning | Client Media Plan Reviews/Feedback/Revisions | Account Manager | 2025-09-24 | 2025-09-30 | 5d | 44
1.1A Communications/Marketing Plan | Media Planning | Client Approval/Sign-Off of Media Plan | Account Manager | 2025-10-01 | 2025-10-07 | 5d | 45
1.1.G Additional Services | Public Relations Strategy Development | Develop overall PR strategy and objectives | Media Relations Manager | 2025-08-27 | 2025-09-16 | 15d | 41
1.1.G Additional Services | Public Relations Strategy Development | Identify key messages and communication goals | Media Relations Manager | 2025-09-17 | 2025-09-30 | 10d | 47
1.1.G Additional Services | Media Relations | Compile media outreach list | Media Relations Manager | 2025-10-01 | 2025-10-21 | 15d | 48
1.1.G Additional Services | Media Relations | Prepare and distribute press releases | Media Relations Manager | 2025-10-22 | 2026-06-07 | Ongoing, as needed | 49
1.1.G Additional Services | Media Relations | Monitor media coverage and analyze PR Impact | Media Relations Manager | 2025-10-22 | 2026-06-07 | Ongoing | 49
1.1.G Additional Services | Media Relations | Regular updates to the Michigan Wildlife Council Team | Media Relations Manager | 2025-10-22 | 2026-06-07 | Ongoing, as needed | 49
1.1.G Additional Services | Event Management | Plan and organize press conferences & public speaking events | Media Relations Manager | 2025-10-22 | 2026-06-07 | 15 days per event | 49
1.3 Training | Media Training | Develop media training materials and curriculum | Media Relations Manager | 2025-10-22 | 2025-11-11 | 15d | 49
1.3 Training | Media Training | Conduct media training sessions | Media Relations Manager | 2025-11-12 | 2025-11-13 | 2d | 54
4.2 Meetings | Account Management and Ongoing Communications | Status Meetings | Account Manager and Project Manager | 2024-12-08 | 2026-06-07 | Ongoing
4.2 Meetings | Confer monthly with MWC and DNR representatives to review progress and mitigate issues | Status Meetings | Account Manager and Project Manager | 2024-12-08 | 2026-06-07 | Monthly
4.2 Meetings | Quarterly Meetings with the full MWC to review plans and deliverables | Status Meetings | Account Manager and Project Manager | 2024-12-08 | 2026-06-07 | Quarterly
4.2 Meetings | Within 10 calendar days of the Annual Campaign Meeting | Submission of Annual Campaign Plan for Final Approval | Account Manager and Project Manager | 2024-12-08 | 2026-06-07 | Annually
4.3 Reporting | Monitor campaign performance and provide quarterly reports. | Monitor campaign performance, provide quarterly reports, offer optimization recommendations | Data Analyst | 2024-12-08 | 2026-06-07 | Quarterly
Campaign Messaging & Implementation
1.1.D Creative | Creative Concept Development | Creative/Project Brief | Account Manager, Art Director, Copywriter, Content Strategist | 2025-10-08 | 2025-10-14 | 5d | 46
1.1.D Creative | Creative Concept Development | Brainstorming & Ideation | Account Manager, Art Director, Copywriter, Content Strategist | 2025-10-15 | 2025-10-28 | 10d | 62
1.1.D Creative | Creative Concept Development | Develop initial creative concepts | Art Director, Copywriter | 2025-10-29 | 2025-11-06 | 7d | 63
1.1.D Creative | Creative Review & Approval | Internal review of creative concepts | Account Manager, Content Strategist, Art Director, Copywriter | 2025-11-07 | 2025-11-10 | 2d | 64
1.1.D Creative | Creative Review & Approval | Client presentation & feedback | Account Manager, Project Manager, Art Director, Copywriter | 2025-11-11 | 2025-11-13 | 3d | 65
1.1.D Creative | Creative Review & Approval | Finalize creative concepts | Art Director, Copywriter | 2025-11-14 | 2025-11-19 | 4d | 66
1.1.D Creative | Creative Review & Approval | Gain approval on platform to execute | Account Manager | 2025-11-20 | 2025-11-21 | 2d | 67
1.1.E Production | Production Planning | Select production vendors | Producer, Art Director, Copywriter | 2025-11-24 | 2025-12-03 | 8d | 68
1.1.E Production | Production Planning | Production scheduling and logistics | Producer | 2025-12-04 | 2025-12-09 | 4d | 69
1.1.E Production | Creative Production | Produce digital and print materials | Production Team, Producer, Art Director, Copywriter | 2025-12-10 | 2025-12-23 | 10d | 70
1.1.E Production | Creative Production | Produce video and audio content | Production Team, Producer, Art Director, Copywriter | 2025-12-24 | 2026-01-27 | 25d | 71
1.1.E Production | Creative Production | Review and revise production elements | Account Manager, Producer, Art Director, Copywriter | 2026-01-28 | 2026-02-03 | 5d | 72
1.1.E Production | Launch & Distribution | Final approval of all creative assets | Account Manager | 2026-02-04 | 2026-02-05 | 2d | 73
1.1.E Production | Launch & Distribution | Distribute materials to media team | Project Manager, Producer | 2026-02-06 | 2026-02-10 | 3d | 74
1.1.F Website Management, Development & Maintenance | Manage and update the campaign website. | Project Kick Off | Account Manager, Project Manager, Content Strategist, Developer | 2025-07-07 | 2025-07-07 | 1d
1.1.F Website Management, Development & Maintenance | Manage and update the campaign website. | Define Website Requirements | Project Manager, Content Strategist, Developer | 2025-07-08 | 2025-07-14 | 5d | 76
1.1.F Website Management, Development & Maintenance | Manage and update the campaign website. | Setup hosting environment | Web Developer | 2025-07-15 | 2025-07-17 | 3d | 77
1.1.F Website Management, Development & Maintenance | Manage and update the campaign website. | Perform Security Checks | Quality Assurance Analyst | 2025-07-18 | 2025-07-24 | 5d | 78
1.1.F Website Management, Development & Maintenance | Manage and update the campaign website. | Mobile & Browser Compatibility Testing, WCAG testing, & User Acceptance Testing | Quality Assurance Analyst | 2025-07-25 | 2025-08-07 | 10d | 79
1.1.F Website Management, Development & Maintenance | Manage and update the campaign website. | Web Launch | Account Manager, Web Developer | 2025-08-08 | 2025-08-12 | 3d | 80
1.1.F Website Management, Development & Maintenance | Manage and update the campaign website. | Conduct training sessions for MWC staff & handover documentation | Web Developer | 2025-08-13 | 2025-08-19 | 5d | 81
1.1.F Website Management, Development & Maintenance | Manage and update the campaign website. | Monthly Web Maintenace | Web Developer | 2025-07-07 | 2026-06-07 | Ongoing
Paid Media Management
1.1.C Media | Media Management | Manage and Optimize current live paid media | Media Activation Manager | 2025-06-08 | 2026-06-05 | 261d
1.1.C Media | Gain approval for media buying of new plan | Develop media authorizations | Account manager | 2025-10-08 | 2025-10-09 | 2d | 46
1.1.C Media | Gain approval for media buying of new plan | Client approval of media authorizations | Account manager | 2025-10-10 | 2025-10-13 | 2d | 87
1.1.C Media | Negotiate and place buys | Agree on pricing and secure inventory | Media Activation Manager | 2025-10-14 | 2025-10-20 | 5d | 88
1.1.C Media | Media Activation | Media Buy Spec Kick-Off | Media Activation Manager | 2026-01-28 | 2026-01-28 | 1d
1.1.C Media | Media Activation | Develop/Confirm Buy Specs | Media Activation Manager | 2026-01-29 | 2026-02-02 | 3d | 90
1.1.C Media | Media Activation | Flight Check Submission | Media Activation Manager | 2026-02-03 | 2026-02-03 | 1d | 91
1.1.C Media | Media Activation | Buy Spec Review | Media Activation Manager | 2026-02-04 | 2026-02-05 | 2d | 92
1.1.C Media | Media Activation | Buy Spec QA | Media Activation Manager | 2026-02-06 | 2026-02-09 | 2d | 93
1.1.C Media | Media Activation | Buy Report Distribution | Media Activation Manager | 2026-02-10 | 2026-02-10 | 1d | 94
1.1.C Media | Media Activation | Buy Approved | Media Activation Manager | 2026-02-11 | 2026-02-12 | 2d | 95
1.1.C Media | Media Activation | Confirm Receipt of Creative Assets/File Names (Min 5 days prior to launch) | Media Activation Manager | 2026-02-11 | 2026-02-11 | 1d | 75
1.1.C Media | Media Activation | Platform Build (Digital Only) | Media Activation Manager | 2026-02-12 | 2026-02-18 | 5d | 97
1.1.C Media | Media Activation | Traffic | Media Activation Manager | 2026-02-12 | 2026-02-17 | 4d | 97
1.1.C Media | Media Activation | Traffic QA | Media Activation Manager | 2026-02-18 | 2026-02-18 | 1d | 99
1.1.C Media | Media Activation | Campaign Build QA | Media Activation Manager | 2026-02-19 | 2026-02-19 | 1d | 100
1.1.C Media | Media Activation | Campaign Launch | Media Activation Manager | 2026-02-20 | 2026-02-20 | 1d | 101
1.1.C Media | Media Activation | Post Activation QA (5 days post launch) | Media Activation Manager | 2026-02-23 | 2026-02-23 | 1d | 102
1.1.C Media | Media Activation | Pacing (Digital Only) and Ongoing Optimizations | Media Activation Manager | 2026-02-24 | 2025-06-08 | Ongoing | 103
1.1.C Media | Ad Ops | Tag Map Development (URL to be provided and confirmed KPI) | Ad Operations | 2026-02-04 | 2026-02-06 | 3d | 92
1.1.C Media | Ad Ops | Tag Development | Ad Operations | 2026-02-09 | 2026-02-10 | 2d | 105
1.1.C Media | Ad Ops | Tag Implementation | Ad Operations | 2026-02-11 | 2026-02-16 | 4d | 106
1.1.C Media | Ad Ops | Tag QA | Ad Operations | 2026-02-17 | 2026-02-20 | 4d | 107
1.1.C Media | Ad Ops | UTM Development | Ad Operations | 2026-02-12 | 2026-02-13 | 2d | 97
1.1.C Media | Ad Ops | UTM QA | Ad Operations | 2026-02-16 | 2026-02-17 | 2d | 109

## 4.3 Summary Budget Detail
Budget Detail Sheet
Below is a summary of our detailed budget by category and year, with a combined three-year total.
In the subsequent tabs you'll find the supporting detail for each year that shows the number of hours needed by each resource to achieve program success on an annualized basis.
As a part of our onboarding process, we would work collaboratively with the State of Michigan Wildlife Council team to formalize an agreed upon scope and project timeline.
| 1400000 | 1400000 | 1400000 | 4200000 | Key Personnel
| Year 1 | Year 2 | Year 3 | 3-Year Total | Account Manager | Julia Francke
Campaign Management Services (variable price based on a blended hourly rate) |  |  |  |  | Project Manager | TBH
1.1A Communications/Marketing Plan & 1.1.H Implementation | 54023.85 | 34959 | 34959 | 123941.85 | Media Planner | Kaylee Brown
1.1.G Additional Services & 1.3 Training | 19816.875 | 25365.6 | 25365.6 | 70548.075 | Researcher & Senior-Level Strategic Counsel | Sue LaRue
4.3 Reporting | 10052.745 | 9280.395 | 9280.395 | 28613.535 | Brand & Content Strategy | Kirstin Barton
[5 empty] | Public Relations Manager | Bill Nowling
Market Research (fixed hourly rate) |  |  |  |  | Art Director | Andy Gregor
1.1.B Market Research | 10032.42 | 4849.545 | 4849.545 | 19731.51 | Copywriter | Rebecca Maxey
1.1.B Market Research OOP | 40000 |  |  | 40000 | Producer | Johnathon Hubert-McLennan
(Includes tracking study; doesn't include recommended new research as reflected in proposal) |  |  |  |  | Web Developer | Isaac Scroggins
[5 empty] | QA Analyst | Salvatore Palazzolo
Campaign Messaging & Implementation (variable price based on a blended hourly rate) |  |  |  |  | Media Activation Manager - Social | Gabriella Cortese
1.1.D Creative & 1.1.E Production Time of Staff | 116921.595 | 95230.755 | 95230.755 | 307383.105 | Media Activation Manager - Programmatic | TBH
1.1.E Production OOP Expense | 135000 | 120000 | 120000 | 375000 | Media Operations | Maria Cioletti
1.1.F Website Management, Development & Maintenance | 63576.6 | 63576.6 | 63576.6 | 190729.8 | Data Analyst | Bryan Petrosky
[5 empty] | Senior-Level Strategic Counsel - Client Services | Rebecca Nuno
Paid Media 1.1.C (commission-based 6% fee) | 50150 | 56050 | 56050 | 162250 | Senior-Level Strategic Counsel - Media Planning | Keith Hamilton
[5 empty] | Senior-Level Strategic Counsel - Creative | Greg Auer
Account & Project Management Fee (variable price based on a blended hourly rate) | 50934.45 | 50385.675 | 50385.675 | 151705.8 | Senior-Level Strategic Counsel - Media Activation | Johanna Berger
Including 4.1 Project Plan, 4.2 Meetings |  |  |  |  | Senior-Level Strategic Counsel - Technology | Randy Bishop
Total Statement of Work Fee | 550508.535 | 459697.57 | 459697.57 | 1469903.675
Working Media Budget | 849491.465 | 940302.43 | 940302.43 | 2730096.325

## Worksheet (hidden)
CLIENT | State of MI DNR RFP |  | COMPLETED BY | J. Williams and Team
JOB / SCOPE # |  |  | START DATE |  |  |  |  | RATE CARD | Rate_24F92 |  |  |  | [Blue] = Fill In
SOW WS DATE COMPLETED | 5.29.24 |  | END DATE |  |  |  |  | RC Col Num | 21 |  |  |  | [Grey] = Calculated/Automated
Staffing | Name if known | Account & Project Management | Brand / Content / Research | Creative & Production | Website / Email Migration / Newletter | Comms Planning | Media Activation | Reporting | PR |  | TOTAL HOURS PER ROLE | WS SPECIFIC RATE CARD | Account & Project Management | Brand / Content / Research | Creative & Production | Website / Email Migration / Newletter | Comms Planning | Media Activation | Reporting | PR | F92 Rate Card | F92 RC ROLE BILLINGS
Project Management
Project Manager | TBH | 200 | [8 empty] | 200 | 135 | 27000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 30000
Senior Project Manager | [10 empty] | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
Assoc Dir Project Management | [10 empty] | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Director Project Management | Kelly Thorp | 5 | [8 empty] | 5 | 230 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 1125
Resource Manager | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0
Proofreader | Tim Skorupski | 50 | [8 empty] | 50 | 115 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 7500
|  | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 255 |  | 33900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 38625
Client Services
Account Executive | [10 empty] | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Account Executive | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
Account Supervisor | [10 empty] | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
VP, Account Director | [10 empty] | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
Account Executive | Julia Francke | 175 | [8 empty] | 175 | 95 | 16625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SVP, Account Management | Rebecca Nuno | 5 | 1 | 4 | 1 |  |  | 2 |  |  | 13 | 340 | 1700 | 340 | 1360 | 340 | 0 | 0 | 680 | 0 | 275 | 3575
|  | 180 | 1 | 4 | 1 | 0 | 0 | 2 | 0 |  | 188 |  | 18325 | 340 | 1360 | 340 | 0 | 0 | 680 | 0 |  | 3575
Operations/Executive
Founder/CEO | [10 empty] | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0
President | [10 empty] | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0
EVP, Activation | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Creative
Art Director |  |  |  | 260 | 50 | [5 empty] | 310 | 135 | 0 | 0 | 35100 | 6750 | 0 | 0 | 0 | 0 | 135 | 41850
Copywriter |  |  |  | 260 | 50 | [5 empty] | 310 | 135 | 0 | 0 | 35100 | 6750 | 0 | 0 | 0 | 0 | 135 | 41850
Designer |  |  |  |  | 50 | [5 empty] | 50 | 115 | 0 | 0 | 0 | 5750 | 0 | 0 | 0 | 0 | 135 | 6750
Senior Copywriter | [10 empty] | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Senior Art Director | [10 empty] | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Creative Director | Susie Campo |  |  | 80 | [6 empty] | 80 | 230 | 0 | 0 | 18400 | 0 | 0 | 0 | 0 | 0 | 250 | 20000
Executive Creative Director |  |  |  | 12 | [6 empty] | 12 | 340 | 0 | 0 | 4080 | 0 | 0 | 0 | 0 | 0 | 325 | 3900
Group Creative Director | [10 empty] | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Creative Director | [10 empty] | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Executive Producer |  |  |  | 12 | [6 empty] | 12 | 230 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 0 | 250 | 3000
Producer |  |  |  | 125 | [6 empty] | 125 | 115 | 0 | 0 | 14375 | 0 | 0 | 0 | 0 | 0 | 65 | 8125
Business Manager |  |  |  | 25 | [6 empty] | 25 | 135 | 0 | 0 | 3375 | 0 | 0 | 0 | 0 | 0 | 90 | 2250
|  | 0 | 0 | 774 | 150 | 0 | 0 | 0 | 0 |  | 924 |  | 0 | 0 | 113190 | 19250 | 0 | 0 | 0 | 0 |  | 127725
Studio
Photographer | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0
PrePress Manager |  |  |  | 50 | [6 empty] | 50 | 135 | 0 | 0 | 6750 | 0 | 0 | 0 | 0 | 0 | 140 | 7000
Production Designer |  |  |  | 125 | [6 empty] | 125 | 135 | 0 | 0 | 16875 | 0 | 0 | 0 | 0 | 0 | 135 | 16875
Studio Manager |  |  |  | 50 | [6 empty] | 50 | 160 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 125 | 6250
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 |  | 225 |  | 0 | 0 | 31625 | 0 | 0 | 0 | 0 | 0 |  | 30125
Strategy - Brand/Content
Marketing Analyst | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Content Strategist | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0
Senior Brand/Content Strategist |  |  |  | 75 | [6 empty] | 75 | 160 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 200 | 15000
SVP, Brand Strategy | [10 empty] | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
Brand Strategist | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
EVP, Strategy |  |  | 30 | [7 empty] | 30 | 375 | 0 | 11250 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 13500
|  | 0 | 30 | 75 | 0 | 0 | 0 | 0 | 0 |  | 105 |  | 0 | 11250 | 12000 | 0 | 0 | 0 | 0 | 0 |  | 28500
Marketing Technology
Junior Developer | [10 empty] | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0
Developer |  |  |  |  | 150 | [5 empty] | 150 | 135 | 0 | 0 | 0 | 20250 | 0 | 0 | 0 | 0 | 135 | 20250
Senior Developer | [10 empty] | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
Technical Manager |  |  |  |  | 20 | [5 empty] | 20 | 160 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 175 | 3500
UX Designer | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
SVP, Product | [10 empty] | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Front End Developer | [10 empty] | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Director of Technology |  |  |  |  | 12 | [5 empty] | 12 | 230 | 0 | 0 | 0 | 2760 | 0 | 0 | 0 | 0 | 255 | 3060
|  | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 0 |  | 182 |  | 0 | 0 | 0 | 26210 | 0 | 0 | 0 | 0 |  | 26810
CX (UX/UI; SEO; CRO)
UX Director | [10 empty] | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
UX Sr. Designer | [10 empty] | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
UI/UX Design System Engineer | [10 empty] | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0
VP, Group Creative Director | [10 empty] | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
EVP, Activation | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Director, SEO | [10 empty] | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
SEM Analyst | [10 empty] | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior SEO Manager | [10 empty] | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0
SVP, Activation | [10 empty] | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Product & Innovation
Analytics Engineer, Sr. | [10 empty] | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Application Testing Engineer | [10 empty] | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Azure DevOps Engineer |  |  |  |  | 80 | [5 empty] | 80 | 230 | 0 | 0 | 0 | 18400 | 0 | 0 | 0 | 0 | 200 | 16000
Business Intelligence Analyst | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0
Customer Support Specialist | [10 empty] | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
Database Admin | [10 empty] | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
DevOps Systems Operations Support | [10 empty] | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0
Product Director | [10 empty] | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Product Owner | [10 empty] | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
QA Analyst |  |  |  |  | 80 | [5 empty] | 80 | 135 | 0 | 0 | 0 | 10800 | 0 | 0 | 0 | 0 | 130 | 10400
Technical Director | [10 empty] | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 |  | 160 |  | 0 | 0 | 0 | 29200 | 0 | 0 | 0 | 0 |  | 26400
Data & Analytics
Analytics Engineer, Sr. | [10 empty] | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Data Analyst | [7 empty] | 110 |  |  | 110 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 10450 | 0 | 95 | 10450
Analytics Engineer, Sr. | [10 empty] | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
VP, Data & Analytics | [10 empty] | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
EVP, Data & Analytics | [10 empty] | 0 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 |  | 110 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10450 | 0 |  | 10450
Media: Strategy & Planning
Media Analyst | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0
Media Manager | M. Child |  |  |  |  | 350 |  |  |  |  | 350 | 135 | 0 | 0 | 0 | 0 | 47250 | 0 | 0 | 0 | 100 | 35000
Media Director | [10 empty] | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Associate Director, Media | K. Brown | [9 empty] | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Media Director | [10 empty] | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
VP, Media Strategy | K. Hamilton |  |  |  |  | 12 |  |  |  |  | 12 | 295 | 0 | 0 | 0 | 0 | 3540 | 0 | 0 | 0 | 275 | 3300
SVP, Media | [10 empty] | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
EVP, Activation | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Content Strategist | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 362 | 0 | 0 | 0 |  | 362 |  | 0 | 0 | 0 | 0 | 50790 | 0 | 0 | 0 |  | 38300
Media: Activation
Media Analyst | [10 empty] | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0
Senior Media Manager | Social Sr. Media manager | [5 empty] | 130 |  |  |  | 130 | 160 | 0 | 0 | 0 | 0 | 0 | 20800 | 0 | 0 | 150 | 19500
Senior Media Strategy Manager | Programmatic Sr. Media Manager | [5 empty] | 130 |  |  |  | 130 | 160 | 0 | 0 | 0 | 0 | 0 | 20800 | 0 | 0 | 0 | 0
Director, Social Media | Maddie Hauser | [5 empty] | 10 |  |  |  | 10 | 230 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0
Director, Programatic | John Trudell | [5 empty] | 10 |  |  |  | 10 | 230 | 0 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 190 | 1900
Associate Director, Media | Traffic - KJ | [5 empty] | 10 |  |  |  | 10 | 195 | 0 | 0 | 0 | 0 | 0 | 1950 | 0 | 0 | 150 | 1500
Associate Director, Media | Media Ops - Shannon | [5 empty] | 5 |  |  |  | 5 | 195 | 0 | 0 | 0 | 0 | 0 | 975 | 0 | 0 | 150 | 750
Media Manager | Media Ops - TBD | [5 empty] | 70 |  |  |  | 70 | 135 | 0 | 0 | 0 | 0 | 0 | 9450 | 0 | 0 | 100 | 7000
Associate Director, Media | Ad Ops - Lindsey Watters | [9 empty] | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Associate Director, Media | Jody Messinger | [5 empty] | 12 |  |  |  | 12 | 195 | 0 | 0 | 0 | 0 | 0 | 2340 | 0 | 0 | 150 | 1800
Account Supervisor | Bill Nowling | [7 empty] | 100 |  | 100 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 150 | 15000
[11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 100 |  | 477 |  | 0 | 0 | 0 | 0 | 0 | 60915 | 0 | 16000 |  | 47450
Total Labor Hours |  | 435 | 31 | 1078 | 493 | 362 | 377 | 112 | 100 |  | 2988 |  | 52225 | 11590 | 158175 | 75000 | 50790 | 60915 | 11130 | 16000 |  | 377960
Deliverable Budget |  | 52225 | 11590 | 158175 | 75000 | 50790 | 60915 | 11130 | 16000
SCOPE TOTAL HOURS |  | 2988
SCOPE TOTAL BILLINGS |  | 435825 | 145.8584 | Avg Hourly Rate
Scope Total at F92 RC |  | 377960 |  |  | Notes:
400-450k on agency revenue not inclusive of OOPs
750k media budget
External/Out-of-Pocket
Vendor name or service type | Cost code | [9 empty] | Mark up | Cost | Revenue
-
Working Media Budget | - | 844000 | [8 empty] | 0 | 844000 | 0
Qualitative Research | - | 40000 | [8 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
[11 empty] | Total OOP | 844000 | 0
F92 Stage/Studio | [10 empty] | Hours / Days | Billing rate | Revenue
Audio Studio Rental (per hour) | [12 empty] | 0
Video Stage Rental (per day) | [12 empty] | 0
Portable Light Kit Rental (per day) | [12 empty] | 0
HD Camera Package Rental (per day) | [10 empty] | 0 |  | 0
[10 empty] | Total Audio/Video |  |  | 0
[13 empty] | 0 | OOP and Studio Revenue
Media & Pass Thru
Vendor name or description | Type | Spend | Spend | Spend |  |  | Spend | Spend | Spend |  | Cost (PassThru) | Media Comms (or markup) | Revenue
| - | [9 empty] | 0 | 10% | 0
| - | [9 empty] | 0 | 15% | 0
| - | [9 empty] | 0 | 15% | 0
| - | [9 empty] | 0 | 15% | 0
| - | [9 empty] | 0 | 15% | 0
|  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 |  | 0
Administration fee 3% | [12 empty] | 13074.75
[10 empty] | Total Contract Value |  |  | 448899.75

## 4.3 Year 1 Budget Detail
CLIENT | State of MI DNR RFP |  |  | COMPLETED BY | J. Williams and Team |  |  |  | Discount | 18.7%
JOB / SCOPE # |  |  |  | START DATE | 2025-01-01 |  |  |  | RATE CARD | Rate_24F92 |  |  | [Blue] = Fill In
SOW WS DATE COMPLETED | 5.29.24 |  |  | END DATE | 2026-05-31 |  |  |  | RC Col Num | 21 |  |  | [Grey] = Calculated/Automated
Staffing | Employee Name | Employment Status | Account & Project Management Fee (Includes 4.2 Meetings) | 1.1.B Market Research | Campaign Messaging & Implementation (Section 1.1.D Creative & Section 1.1.E Production) | Campaign Messaging & Implementation (Section1.1.F Website Management, Development & Maintenance) | Campaign Management Services (1.1.A Commnications/Marketing Plan & 1.1.H Implementation) | Paid Media Management - Section 1.1.C Media (6% Commission - Hours Estimate Bleow) | Reporting (Section 4.3) | Campaign Management Services (1.1.G Additional Services & 1.3 Training) | TOTAL HOURS PER ROLE | WS SPECIFIC RATE CARD | Account & Project Management Fee (Includes 4.2 Meetings) | 1.1.B Market Research | Campaign Messaging & Implementation (Section 1.1.D Creative & Section 1.1.E Production) | Campaign Messaging & Implementation (Section1.1.F Website Management, Development & Maintenance) | Campaign Management Services (1.1.A Commnications/Marketing Plan & 1.1.H Implementation) | Paid Media Management - Section 1.1.C Media (6% Commission - Hours Estimate Bleow) | Reporting (Section 4.3) | Campaign Management Services (1.1.G Additional Services & 1.3 Training) | F92 Rate Card | F92 RC ROLE BILLINGS
Project Management
Project Manager | To Be Hired Upon Award |  | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230 | 109.755 | 25243.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 34500
Senior Project Manager |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
Assoc Dir Project Management |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Director Project Management | Kelly Thorp | Full Time Employee | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 186.99 | 934.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 1125
Resource Manager |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0
Proofreader | Tim Skorupski | Full Time Employee | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 93.495 | 4674.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 7500
|  |  | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 |  | 30853.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 43125
Client Services
Account Executive |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Account Executive |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
Account Supervisor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
VP, Account Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
Account Director | Julia Francke | Full Time Employee | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 186.99 | 18699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 18000
SVP, Account Management | Rebecca Nuno | Full Time Employee | 5 | 1 | 4 | 1 | 0 | 0 | 2 | 0 | 13 | 276.42 | 1382.1 | 276.42 | 1105.68 | 276.42 | 0 | 0 | 552.84 | 0 | 275 | 3575
|  |  | 105 | 1 | 4 | 1 | 0 | 0 | 2 | 0 | 113 |  | 20081.1 | 276.42 | 1105.68 | 276.42 | 0 | 0 | 552.84 | 0 |  | 21575
Operations/Executive
Founder/CEO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0
President |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0
EVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Creative
Art Director | Andy Gregor | Full Time Employee | 0 | 0 | 265 | 50 | 0 | 0 | 0 | 0 | 315 | 109.755 | 0 | 0 | 29085.075 | 5487.75 | 0 | 0 | 0 | 0 | 135 | 42525
Copywriter | Rebecca Maxey | Full Time Employee | 0 | 0 | 265 | 100 | 0 | 0 | 0 | 0 | 365 | 109.755 | 0 | 0 | 29085.075 | 10975.5 | 0 | 0 | 0 | 0 | 135 | 49275
Designer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
Senior Copywriter |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Senior Art Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Executive Creative Director | Greg Auer | Full Time Employee | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 32 | 276.42 | 0 | 0 | 8845.44 | 0 | 0 | 0 | 0 | 0 | 325 | 10400
Group Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Executive Producer |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Producer | Johnathon Hubert - Mclenan | Full Time Employee | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 93.495 | 0 | 0 | 11686.875 | 0 | 0 | 0 | 0 | 0 | 65 | 8125
Business Manager | To be Assigned Upon Award | TBH | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 109.755 | 0 | 0 | 2743.875 | 0 | 0 | 0 | 0 | 0 | 90 | 2250
|  |  | 0 | 0 | 712 | 150 | 0 | 0 | 0 | 0 | 862 |  | 0 | 0 | 81446.34 | 16463.25 | 0 | 0 | 0 | 0 |  | 112575
Studio
Photographer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0
PrePress Manager | Brian Neidbala | Full Time Employee | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 109.755 | 0 | 0 | 5487.75 | 0 | 0 | 0 | 0 | 0 | 140 | 7000
Production Designer | To be Assigned Upon Award | Full Time Employee | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 115 | 109.755 | 0 | 0 | 12621.825 | 0 | 0 | 0 | 0 | 0 | 135 | 15525
Studio Manager | Rex Gustafson | Full Time Employee | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 130.08 | 0 | 0 | 6504 | 0 | 0 | 0 | 0 | 0 | 125 | 6250
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 215 |  | 0 | 0 | 24613.575 | 0 | 0 | 0 | 0 | 0 |  | 28775
Strategy - Brand/Content
Marketing Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Content Strategist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0
Senior Brand/Content Strategist | Kirstin Barton | Full Time Employee | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 130.08 | 0 | 0 | 9756 | 0 | 0 | 0 | 0 | 0 | 200 | 15000
SVP, Brand Strategy |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
Brand Strategist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
EVP, Strategy | Sue LaRue (Researcher) | Full Time Employee | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 304.875 | 0 | 9756 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 14400
|  |  | 0 | 32 | 75 | 0 | 0 | 0 | 0 | 0 | 107 |  | 0 | 9756 | 9756 | 0 | 0 | 0 | 0 | 0 |  | 29400
Marketing Technology
Junior Developer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0
Developer | Issac Scroggins | Full Time Employee | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 190 | 109.755 | 0 | 0 | 0 | 20853.45 | 0 | 0 | 0 | 0 | 135 | 25650
Senior Developer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
Technical Manager |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
UX Designer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
SVP, Product |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Front End Developer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Director of Technology | Randy Bishop | Full Time Employee | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 186.99 | 0 | 0 | 0 | 2243.88 | 0 | 0 | 0 | 0 | 255 | 3060
|  |  | 0 | 0 | 0 | 202 | 0 | 0 | 0 | 0 | 202 |  | 0 | 0 | 0 | 23097.33 | 0 | 0 | 0 | 0 |  | 28710
CX (UX/UI; SEO; CRO)
UX Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
UX Sr. Designer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
UI/UX Design System Engineer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0
VP, Group Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
EVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Director, SEO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
SEM Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior SEO Manager |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0
SVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Product & Innovation
Analytics Engineer, Sr. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Application Testing Engineer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Azure DevOps Engineer | Lindsey Watters | Full Time Employee | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 80 | 186.99 | 0 | 0 | 0 | 14959.2 | 0 | 0 | 0 | 0 | 200 | 16000
Business Intelligence Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0
Customer Support Specialist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
Database Admin |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
DevOps Systems Operations Support |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0
Product Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Product Owner |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
QA Analyst | Salvatore Palazzolo | Full Time Employee | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 80 | 109.755 | 0 | 0 | 0 | 8780.4 | 0 | 0 | 0 | 0 | 130 | 10400
Technical Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 160 |  | 0 | 0 | 0 | 23739.6 | 0 | 0 | 0 | 0 |  | 26400
Data & Analytics
Analytics Engineer, Sr. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Data Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 0 | 123 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 9499.905 | 0 | 95 | 11685
Analytics Engineer, Sr. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
VP, Data & Analytics |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
EVP, Data & Analytics |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 0 | 123 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9499.905 | 0 |  | 11685
Media: Strategy & Planning
Media Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0
Associate Director, Media | Kaylee Brown | Full Time Employee | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 250 | 158.535 | 0 | 0 | 0 | 0 | 39633.75 | 0 | 0 | 0 | 150 | 37500
Media Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Media Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
VP, Media Strategy | Keith Hamilton | Full Time Employee | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 239.835 | 0 | 0 | 0 | 0 | 14390.1 | 0 | 0 | 0 | 275 | 16500
SVP, Media |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
EVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Content Strategist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 310 | 0 | 0 | 0 | 310 |  | 0 | 0 | 0 | 0 | 54023.85 | 0 | 0 | 0 |  | 54000
Media: Activation
Media Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0
Senior Media Manager | Gabriella Corteze | Full Time Employee | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 130 | 130.08 | 0 | 0 | 0 | 0 | 0 | 16910.4 | 0 | 0 | 150 | 19500
Senior Media Manager | To Be Hired Upon Award | TBH | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 130 | 130.08 | 0 | 0 | 0 | 0 | 0 | 16910.4 | 0 | 0 | 150 | 19500
EVP, Media & Activation | Johanna Berger | Full Time Employee | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 304.875 | 0 | 0 | 0 | 0 | 0 | 3048.75 | 0 | 0 | 400 | 4000
Director, Programatic |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 0
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Media Manager | Maria Cioletti | Full Time Employee | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 90 | 109.755 | 0 | 0 | 0 | 0 | 0 | 9877.95 | 0 | 0 | 100 | 9000
Associate Director, Media | Bill Nowling - Public Relations Manager | Sub-Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19816.875 | 150 | 18750
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Account Supervisor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 360 | 0 | 125 | 485 |  | 0 | 0 | 0 | 0 | 0 | 46747.5 | 0 | 19816.875 |  | 70750
Total Labor Hours |  |  | 390 | 33 | 1006 | 513 | 310 | 360 | 125 | 125 | 2862 |  | 50934.45 | 10032.42 | 116921.595 | 63576.6 | 54023.85 | 46747.5 | 10052.745 | 19816.875 |  | 426995
Deliverable Budget |  |  | 50934.45 | 10032.42 | 116921.595 | 63576.6 | 54023.85 | 46747.5 | 10052.745 | 19816.875
SCOPE TOTAL HOURS |  |  | 2862
SCOPE TOTAL BILLINGS |  |  | 372106.035 | 130.0161 | Avg Hourly Rate
Scope Total at F92 RC |  |  | 426995
External/Out-of-Pocket
Vendor name or service type | Cost code | [9 empty] | Mark up | Cost | Revenue
-
Qualitative Research |  |  | Cost estimated based on analysis of similar past client projects. | [8 empty] | 40000 | 0
Creative Production | - |  | Cost estimate, dependent on final campaign selections, and media assests required. Estimated based on similar past client production and assuming the followng: | [7 empty] | 0 | 150000 | 0
| - |  | OTT 1 x :30 X :15 cutdown | [7 empty] | 0 | 0 | 0
| - |  | Digital/Social - 3 Refresh | [7 empty] | 0 | 0 | 0
| - |  | Assumes multiple 1 day shoot, 1 location | [7 empty] | 0 | 0 | 0
| - |  | 1 Client reviews/revisions | [7 empty] | 0 | 0 | 0
| - |  | Music: 1 Track | [7 empty] | 0 | 0 | 0
[11 empty] | Total OOP | 190000 | 0
Media & Pass Thru
Vendor name or description | Type |  | Spend | Spend | Spend |  |  | Spend | Spend | Spend | Cost (PassThru) | Media Comms (or markup) | Revenue
Working Media | - |  | 850000 | [7 empty] | 850000 | 5.9% | 50150
| - | [9 empty] | 0 |  | 0
| - | [9 empty] | 0 |  | 0
| - | [9 empty] | 0 |  | 0
| - | [9 empty] | 0 |  | 0
|  |  | 850000 | 0 | 0 |  |  | 0 | 0 | 0 | 850000 |  | 50150

## 4.3 Year 2 Budget Detail
CLIENT | State of MI DNR RFP |  |  | COMPLETED BY | J. Williams and Team |  |  |  | Discount | 18.7%
JOB / SCOPE # |  |  |  | START DATE | 2025-01-01 |  |  |  | RATE CARD | Rate_24F92 |  |  | [Blue] = Fill In
SOW WS DATE COMPLETED | 5.29.24 |  |  | END DATE | 2026-05-31 |  |  |  | RC Col Num | 21 |  |  | [Grey] = Calculated/Automated
Staffing | Employee Name | Employment Status | Account & Project Management Fee (Includes 4.2 Meetings) | 1.1.B Market Research | Campaign Messaging & Implementation (Section 1.1.D Creative & Section 1.1.E Production) | Campaign Messaging & Implementation (Section1.1.F Website Management, Development & Maintenance) | Campaign Management Services (1.1.A Commnications/Marketing Plan & 1.1.H Implementation) | Paid Media Management - Section 1.1.C Media (6% Commission - Hours Estimate Bleow) | Reporting (Section 4.3) | Campaign Management Services (1.1.G Additional Services & 1.3 Training) | TOTAL HOURS PER ROLE | WS SPECIFIC RATE CARD | Account & Project Management Fee (Includes 4.2 Meetings) | 1.1.B Market Research | Campaign Messaging & Implementation (Section 1.1.D Creative & Section 1.1.E Production) | Campaign Messaging & Implementation (Section1.1.F Website Management, Development & Maintenance) | Campaign Management Services (1.1.A Commnications/Marketing Plan & 1.1.H Implementation) | Paid Media Management - Section 1.1.C Media (6% Commission - Hours Estimate Bleow) | Reporting (Section 4.3) | Campaign Management Services (1.1.G Additional Services & 1.3 Training) | F92 Rate Card | F92 RC ROLE BILLINGS
Project Management
Project Manager | To Be Hired Upon Award |  | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 109.755 | 24694.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 33750
Senior Project Manager |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
Assoc Dir Project Management |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Director Project Management | Kelly Thorp | Full Time Employee | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 186.99 | 934.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 1125
Resource Manager |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0
Proofreader | Tim Skorupski | Full Time Employee | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 93.495 | 4674.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 7500
|  |  | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 |  | 30304.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 42375
Client Services
Account Executive |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Account Executive |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
Account Supervisor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
VP, Account Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
Account Director | Julia Francke | Full Time Employee | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 186.99 | 18699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 18000
SVP, Account Management | Rebecca Nuno | Full Time Employee | 5 | 1 | 4 | 1 | 0 | 0 | 2 | 0 | 13 | 276.42 | 1382.1 | 276.42 | 1105.68 | 276.42 | 0 | 0 | 552.84 | 0 | 275 | 3575
|  |  | 105 | 1 | 4 | 1 | 0 | 0 | 2 | 0 | 113 |  | 20081.1 | 276.42 | 1105.68 | 276.42 | 0 | 0 | 552.84 | 0 |  | 21575
Operations/Executive
Founder/CEO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0
President |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0
EVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Creative
Art Director | Andy Gregor | Full Time Employee | 0 | 0 | 175 | 50 | 0 | 0 | 0 | 0 | 225 | 109.755 | 0 | 0 | 19207.125 | 5487.75 | 0 | 0 | 0 | 0 | 135 | 30375
Copywriter | Rebecca Maxey | Full Time Employee | 0 | 0 | 175 | 100 | 0 | 0 | 0 | 0 | 275 | 109.755 | 0 | 0 | 19207.125 | 10975.5 | 0 | 0 | 0 | 0 | 135 | 37125
Designer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
Senior Copywriter |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Senior Art Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Executive Creative Director | Greg Auer | Full Time Employee | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 276.42 | 0 | 0 | 6910.5 | 0 | 0 | 0 | 0 | 0 | 325 | 8125
Group Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Executive Producer |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Producer | Johnathon Hubert - Mclenan | Full Time Employee | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 93.495 | 0 | 0 | 11686.875 | 0 | 0 | 0 | 0 | 0 | 65 | 8125
Business Manager | To be Assigned Upon Award | TBH | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 109.755 | 0 | 0 | 2743.875 | 0 | 0 | 0 | 0 | 0 | 90 | 2250
|  |  | 0 | 0 | 525 | 150 | 0 | 0 | 0 | 0 | 675 |  | 0 | 0 | 59755.5 | 16463.25 | 0 | 0 | 0 | 0 |  | 86000
Studio
Photographer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0
PrePress Manager | Brian Neidbala | Full Time Employee | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 109.755 | 0 | 0 | 5487.75 | 0 | 0 | 0 | 0 | 0 | 140 | 7000
Production Designer | To be Assigned Upon Award | Full Time Employee | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 115 | 109.755 | 0 | 0 | 12621.825 | 0 | 0 | 0 | 0 | 0 | 135 | 15525
Studio Manager | Rex Gustafson | Full Time Employee | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 130.08 | 0 | 0 | 6504 | 0 | 0 | 0 | 0 | 0 | 125 | 6250
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 215 |  | 0 | 0 | 24613.575 | 0 | 0 | 0 | 0 | 0 |  | 28775
Strategy - Brand/Content
Marketing Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Content Strategist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0
Senior Brand/Content Strategist | Kirstin Barton | Full Time Employee | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 130.08 | 0 | 0 | 9756 | 0 | 0 | 0 | 0 | 0 | 200 | 15000
SVP, Brand Strategy |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
Brand Strategist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
EVP, Strategy | Sue LaRue (Researcher) | Full Time Employee | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 304.875 | 0 | 4573.125 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 6750
|  |  | 0 | 15 | 75 | 0 | 0 | 0 | 0 | 0 | 90 |  | 0 | 4573.125 | 9756 | 0 | 0 | 0 | 0 | 0 |  | 21750
Marketing Technology
Junior Developer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0
Developer | Issac Scroggins | Full Time Employee | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 190 | 109.755 | 0 | 0 | 0 | 20853.45 | 0 | 0 | 0 | 0 | 135 | 25650
Senior Developer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
Technical Manager |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
UX Designer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
SVP, Product |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Front End Developer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Director of Technology | Randy Bishop | Full Time Employee | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 186.99 | 0 | 0 | 0 | 2243.88 | 0 | 0 | 0 | 0 | 255 | 3060
|  |  | 0 | 0 | 0 | 202 | 0 | 0 | 0 | 0 | 202 |  | 0 | 0 | 0 | 23097.33 | 0 | 0 | 0 | 0 |  | 28710
CX (UX/UI; SEO; CRO)
UX Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
UX Sr. Designer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
UI/UX Design System Engineer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0
VP, Group Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
EVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Director, SEO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
SEM Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior SEO Manager |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0
SVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Product & Innovation
Analytics Engineer, Sr. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Application Testing Engineer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Azure DevOps Engineer | Lindsey Watters | Full Time Employee | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 80 | 186.99 | 0 | 0 | 0 | 14959.2 | 0 | 0 | 0 | 0 | 200 | 16000
Business Intelligence Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0
Customer Support Specialist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
Database Admin |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
DevOps Systems Operations Support |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0
Product Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Product Owner |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
QA Analyst | Salvatore Palazzolo | Full Time Employee | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 80 | 109.755 | 0 | 0 | 0 | 8780.4 | 0 | 0 | 0 | 0 | 130 | 10400
Technical Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 160 |  | 0 | 0 | 0 | 23739.6 | 0 | 0 | 0 | 0 |  | 26400
Data & Analytics
Analytics Engineer, Sr. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Data Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 0 | 113 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 8727.555 | 0 | 95 | 10735
Analytics Engineer, Sr. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
VP, Data & Analytics |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
EVP, Data & Analytics |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 0 | 113 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8727.555 | 0 |  | 10735
Media: Strategy & Planning
Media Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0
Associate Director, Media | Kaylee Brown | Full Time Employee | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 160 | 158.535 | 0 | 0 | 0 | 0 | 25365.6 | 0 | 0 | 0 | 150 | 24000
Media Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Media Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
VP, Media Strategy | Keith Hamilton | Full Time Employee | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 239.835 | 0 | 0 | 0 | 0 | 9593.4 | 0 | 0 | 0 | 275 | 11000
SVP, Media |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
EVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Content Strategist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 0 | 0 | 34959 | 0 | 0 | 0 |  | 35000
Media: Activation
Media Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0
Senior Media Manager | Gabriella Corteze | Full Time Employee | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 130.08 | 0 | 0 | 0 | 0 | 0 | 15609.6 | 0 | 0 | 150 | 18000
Senior Media Manager | To Be Hired Upon Award | TBH | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 130.08 | 0 | 0 | 0 | 0 | 0 | 15609.6 | 0 | 0 | 150 | 18000
EVP, Media & Activation | Johanna Berger | Full Time Employee | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 35 | 304.875 | 0 | 0 | 0 | 0 | 0 | 10670.625 | 0 | 0 | 400 | 14000
Director, Programatic |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 0
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Media Manager | Maria Cioletti | Full Time Employee | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 90 | 109.755 | 0 | 0 | 0 | 0 | 0 | 9877.95 | 0 | 0 | 100 | 9000
Associate Director, Media | Bill Nowling - Public Relations Manager | Sub-Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25365.6 | 150 | 24000
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Account Supervisor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 160 | 525 |  | 0 | 0 | 0 | 0 | 0 | 51767.775 | 0 | 25365.6 |  | 83000
Total Labor Hours |  |  | 385 | 16 | 819 | 513 | 200 | 365 | 115 | 160 | 2573 |  | 50385.675 | 4849.545 | 95230.755 | 63576.6 | 34959 | 51767.775 | 9280.395 | 25365.6 |  | 384320
Deliverable Budget |  |  | 50385.675 | 4849.545 | 95230.755 | 63576.6 | 34959 | 51767.775 | 9280.395 | 25365.6
SCOPE TOTAL HOURS |  |  | 2573
SCOPE TOTAL BILLINGS |  |  | 335415.345 | 130.3596 | Avg Hourly Rate
Scope Total at F92 RC |  |  | 384320
External/Out-of-Pocket
Vendor name or service type | Cost code | [9 empty] | Mark up | Cost | Revenue
-
0
Creative Production | - | [9 empty] | 0 | 120000 | 0
| - |  | OTT 1 x :30 X :15 cutdown | [7 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
[11 empty] | Total OOP | 120000 | 0
Media & Pass Thru
Vendor name or description | Type |  | Spend | Spend | Spend |  |  | Spend | Spend | Spend | Cost (PassThru) | Media Comms (or markup) | Revenue
Working Media | - |  | 950000 | [7 empty] | 950000 | 5.9% | 56050
| - | [9 empty] | 0 |  | 0
| - | [9 empty] | 0 |  | 0
| - | [9 empty] | 0 |  | 0
| - | [9 empty] | 0 |  | 0
|  |  | 950000 | 0 | 0 |  |  | 0 | 0 | 0 | 950000 |  | 56050

## 4.3 Year 3 Budget Detail
CLIENT | State of MI DNR RFP |  |  | COMPLETED BY | J. Williams and Team |  |  |  | Discount | 18.7%
JOB / SCOPE # |  |  |  | START DATE | 2025-01-01 |  |  |  | RATE CARD | Rate_24F92 |  |  | [Blue] = Fill In
SOW WS DATE COMPLETED | 5.29.24 |  |  | END DATE | 2026-05-31 |  |  |  | RC Col Num | 21 |  |  | [Grey] = Calculated/Automated
Staffing | Employee Name | Employment Status | Account & Project Management Fee (Includes 4.2 Meetings) | 1.1.B Market Research | Campaign Messaging & Implementation (Section 1.1.D Creative & Section 1.1.E Production) | Campaign Messaging & Implementation (Section1.1.F Website Management, Development & Maintenance) | Campaign Management Services (1.1.A Commnications/Marketing Plan & 1.1.H Implementation) | Paid Media Management - Section 1.1.C Media (6% Commission - Hours Estimate Bleow) | Reporting (Section 4.3) | Campaign Management Services (1.1.G Additional Services & 1.3 Training) | TOTAL HOURS PER ROLE | WS SPECIFIC RATE CARD | Account & Project Management Fee (Includes 4.2 Meetings) | 1.1.B Market Research | Campaign Messaging & Implementation (Section 1.1.D Creative & Section 1.1.E Production) | Campaign Messaging & Implementation (Section1.1.F Website Management, Development & Maintenance) | Campaign Management Services (1.1.A Commnications/Marketing Plan & 1.1.H Implementation) | Paid Media Management - Section 1.1.C Media (6% Commission - Hours Estimate Bleow) | Reporting (Section 4.3) | Campaign Management Services (1.1.G Additional Services & 1.3 Training) | F92 Rate Card | F92 RC ROLE BILLINGS
Project Management
Project Manager | To Be Hired Upon Award |  | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 109.755 | 24694.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 33750
Senior Project Manager |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
Assoc Dir Project Management |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Director Project Management | Kelly Thorp | Full Time Employee | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 186.99 | 934.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 1125
Resource Manager |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0
Proofreader | Tim Skorupski | Full Time Employee | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 93.495 | 4674.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 7500
|  |  | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 |  | 30304.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 42375
Client Services
Account Executive |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Account Executive |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
Account Supervisor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
VP, Account Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
Account Director | Julia Francke | Full Time Employee | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 186.99 | 18699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 18000
SVP, Account Management | Rebecca Nuno | Full Time Employee | 5 | 1 | 4 | 1 | 0 | 0 | 2 | 0 | 13 | 276.42 | 1382.1 | 276.42 | 1105.68 | 276.42 | 0 | 0 | 552.84 | 0 | 275 | 3575
|  |  | 105 | 1 | 4 | 1 | 0 | 0 | 2 | 0 | 113 |  | 20081.1 | 276.42 | 1105.68 | 276.42 | 0 | 0 | 552.84 | 0 |  | 21575
Operations/Executive
Founder/CEO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0
President |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0
EVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Creative
Art Director | Andy Gregor | Full Time Employee | 0 | 0 | 175 | 50 | 0 | 0 | 0 | 0 | 225 | 109.755 | 0 | 0 | 19207.125 | 5487.75 | 0 | 0 | 0 | 0 | 135 | 30375
Copywriter | Rebecca Maxey | Full Time Employee | 0 | 0 | 175 | 100 | 0 | 0 | 0 | 0 | 275 | 109.755 | 0 | 0 | 19207.125 | 10975.5 | 0 | 0 | 0 | 0 | 135 | 37125
Designer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
Senior Copywriter |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Senior Art Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Executive Creative Director | Greg Auer | Full Time Employee | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 276.42 | 0 | 0 | 6910.5 | 0 | 0 | 0 | 0 | 0 | 325 | 8125
Group Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Executive Producer |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
Producer | Johnathon Hubert - Mclenan | Full Time Employee | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 125 | 93.495 | 0 | 0 | 11686.875 | 0 | 0 | 0 | 0 | 0 | 65 | 8125
Business Manager | To be Assigned Upon Award | TBH | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 109.755 | 0 | 0 | 2743.875 | 0 | 0 | 0 | 0 | 0 | 90 | 2250
|  |  | 0 | 0 | 525 | 150 | 0 | 0 | 0 | 0 | 675 |  | 0 | 0 | 59755.5 | 16463.25 | 0 | 0 | 0 | 0 |  | 86000
Studio
Photographer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0
PrePress Manager | Brian Neidbala | Full Time Employee | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 109.755 | 0 | 0 | 5487.75 | 0 | 0 | 0 | 0 | 0 | 140 | 7000
Production Designer | To be Assigned Upon Award | Full Time Employee | 0 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 115 | 109.755 | 0 | 0 | 12621.825 | 0 | 0 | 0 | 0 | 0 | 135 | 15525
Studio Manager | Rex Gustafson | Full Time Employee | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 130.08 | 0 | 0 | 6504 | 0 | 0 | 0 | 0 | 0 | 125 | 6250
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 215 |  | 0 | 0 | 24613.575 | 0 | 0 | 0 | 0 | 0 |  | 28775
Strategy - Brand/Content
Marketing Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Content Strategist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0
Senior Brand/Content Strategist | Kirstin Barton | Full Time Employee | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 130.08 | 0 | 0 | 9756 | 0 | 0 | 0 | 0 | 0 | 200 | 15000
SVP, Brand Strategy |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
Brand Strategist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0
EVP, Strategy | Sue LaRue (Researcher) | Full Time Employee | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 304.875 | 0 | 4573.125 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 6750
|  |  | 0 | 15 | 75 | 0 | 0 | 0 | 0 | 0 | 90 |  | 0 | 4573.125 | 9756 | 0 | 0 | 0 | 0 | 0 |  | 21750
Marketing Technology
Junior Developer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0
Developer | Issac Scroggins | Full Time Employee | 0 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 190 | 109.755 | 0 | 0 | 0 | 20853.45 | 0 | 0 | 0 | 0 | 135 | 25650
Senior Developer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
Technical Manager |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
UX Designer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0
SVP, Product |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Front End Developer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Director of Technology | Randy Bishop | Full Time Employee | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 186.99 | 0 | 0 | 0 | 2243.88 | 0 | 0 | 0 | 0 | 255 | 3060
|  |  | 0 | 0 | 0 | 202 | 0 | 0 | 0 | 0 | 202 |  | 0 | 0 | 0 | 23097.33 | 0 | 0 | 0 | 0 |  | 28710
CX (UX/UI; SEO; CRO)
UX Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
UX Sr. Designer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
UI/UX Design System Engineer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0
VP, Group Creative Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
EVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Director, SEO |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
SEM Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93.495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior SEO Manager |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0
SVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Product & Innovation
Analytics Engineer, Sr. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Application Testing Engineer |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Azure DevOps Engineer | Lindsey Watters | Full Time Employee | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 80 | 186.99 | 0 | 0 | 0 | 14959.2 | 0 | 0 | 0 | 0 | 200 | 16000
Business Intelligence Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 0
Customer Support Specialist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
Database Admin |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 0
DevOps Systems Operations Support |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0
Product Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Product Owner |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
QA Analyst | Salvatore Palazzolo | Full Time Employee | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 80 | 109.755 | 0 | 0 | 0 | 8780.4 | 0 | 0 | 0 | 0 | 130 | 10400
Technical Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 160 |  | 0 | 0 | 0 | 23739.6 | 0 | 0 | 0 | 0 |  | 26400
Data & Analytics
Analytics Engineer, Sr. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Data Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 0 | 113 | 77.235 | 0 | 0 | 0 | 0 | 0 | 0 | 8727.555 | 0 | 95 | 10735
Analytics Engineer, Sr. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
VP, Data & Analytics |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 239.835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
EVP, Data & Analytics |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 304.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 0 | 113 |  | 0 | 0 | 0 | 0 | 0 | 0 | 8727.555 | 0 |  | 10735
Media: Strategy & Planning
Media Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0
Associate Director, Media | Kaylee Brown | Full Time Employee | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 160 | 158.535 | 0 | 0 | 0 | 0 | 25365.6 | 0 | 0 | 0 | 150 | 24000
Media Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Media Director |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
VP, Media Strategy | Keith Hamilton | Full Time Employee | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 40 | 239.835 | 0 | 0 | 0 | 0 | 9593.4 | 0 | 0 | 0 | 275 | 11000
SVP, Media |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0
EVP, Activation |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Content Strategist |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 0 | 0 | 34959 | 0 | 0 | 0 |  | 35000
Media: Activation
Media Analyst |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 0
Senior Media Manager | Gabriella Corteze | Full Time Employee | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 130.08 | 0 | 0 | 0 | 0 | 0 | 15609.6 | 0 | 0 | 150 | 18000
Senior Media Manager | To Be Hired Upon Award | TBH | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 130.08 | 0 | 0 | 0 | 0 | 0 | 15609.6 | 0 | 0 | 150 | 18000
EVP, Media & Activation | Johanna Berger | Full Time Employee | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 35 | 304.875 | 0 | 0 | 0 | 0 | 0 | 10670.625 | 0 | 0 | 400 | 14000
Director, Programatic |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 186.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 0
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Media Manager | Maria Cioletti | Full Time Employee | 0 | 0 | 0 | 0 | 0 | 90 | 0 | 0 | 90 | 109.755 | 0 | 0 | 0 | 0 | 0 | 9877.95 | 0 | 0 | 100 | 9000
Associate Director, Media | Bill Nowling - Public Relations Manager | Sub-Contractor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25365.6 | 150 | 24000
Associate Director, Media |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 158.535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
Account Supervisor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 130.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 365 | 0 | 160 | 525 |  | 0 | 0 | 0 | 0 | 0 | 51767.775 | 0 | 25365.6 |  | 83000
Total Labor Hours |  |  | 385 | 16 | 819 | 513 | 200 | 365 | 115 | 160 | 2573 |  | 50385.675 | 4849.545 | 95230.755 | 63576.6 | 34959 | 51767.775 | 9280.395 | 25365.6 |  | 384320
Deliverable Budget |  |  | 50385.675 | 4849.545 | 95230.755 | 63576.6 | 34959 | 51767.775 | 9280.395 | 25365.6
SCOPE TOTAL HOURS |  |  | 2573
SCOPE TOTAL BILLINGS |  |  | 335415.345 | 130.3596 | Avg Hourly Rate
Scope Total at F92 RC |  |  | 384320
External/Out-of-Pocket
Vendor name or service type | Cost code | [9 empty] | Mark up | Cost | Revenue
-
0
Creative Production | - | [9 empty] | 0 | 120000 | 0
| - |  | OTT 1 x :30 X :15 cutdown | [7 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
| - | [9 empty] | 0 | 0 | 0
[11 empty] | Total OOP | 120000 | 0
Media & Pass Thru
Vendor name or description | Type |  | Spend | Spend | Spend |  |  | Spend | Spend | Spend | Cost (PassThru) | Media Comms (or markup) | Revenue
Working Media | - |  | 950000 | [7 empty] | 950000 | 5.9% | 56050
| - | [9 empty] | 0 |  | 0
| - | [9 empty] | 0 |  | 0
| - | [9 empty] | 0 |  | 0
| - | [9 empty] | 0 |  | 0
|  |  | 950000 | 0 | 0 |  |  | 0 | 0 | 0 | 950000 |  | 56050

## menu items (hidden)
OOP | OOP mark up | Media & Pass Thru | Media labor | Job type
- | - | - | - | -
Audio Video/PostProduction | 1.35 | Digital | Campaign Mgmt | Fixed Fee
Audio Video/Production | 1.35 | Traditional | Reporting/Analytics | T&M
Content Production | 1.35 | Postage | Publisher Services
Data Serv/Analysis | 1.35 | Prize Pool | Strategy/Planning
Data Serv/Data Mgmt | 1.35 | Freight
Data Serv/List | 1.35
Data Serv/Model-Augm | 1.35
Dev/App | 1.35
Email/Delivery | 1.35
Email/License | 1.35
Email/Mgmt | 1.35
Email/Strategy | 1.35
Equipment/LicPermits | 1.35
Equipment/Logistics | 1.35
Equipment/Maintence | 1.35
Equipment/Operating | 1.35
Equipment/Other | 1.35
Equipment/Rental | 1.35
Equipment/Sales | 1.35
Events / Logistics | 1.35
Events/Lic & Permits | 1.35
Events/Mgmt | 1.35
Events/Other | 1.35
Events/Sponsorships | 1.35
Events/Staffing | 1.35
Events/Supplies | 1.35
Events/Venue | 1.35
Fulfillment | 1.35
Hosting/Domain name | 1.35
Hosting/Monthly | 1.35
Hosting/Set up | 1.35
Licensing/Other | 1.35
Licensing/Stock | 1.35
Licensing/Technology | 1.35
Misc job costs | 1.35
Photo/PostProduction | 1.35
Photo/Production | 1.35
Phys Med/ CD Rom | 1.35
Phys Med/Blu-ray | 1.35
Phys Med/Holograms | 1.35
Phys Med/Other | 1.35
Phys Med/USB | 1.35
Printing/Direct mail | 1.35
Printing/Other | 1.35
Promotion/Legal | 1.35
Promotion/Mgmt | 1.35
Promotion/Strategy | 1.35
Promotion/Technology | 1.35
Research | 1.35
Strategy | 1.35
Vehicles
Airfare
Lodging

## rates-original (hidden)
Dept | Role | Cost rate | Bill rate
| - | 0 | 0
Strategy | President | 135.5 | 400
| Founder/CEO | 148 | 500
| VP Marketing Transformation & Insights | 100.5 | 275
| Marketing Analyst | 24 | 150
| Strategy Director | 59 | 225
| Strategic Planner | 24 | 150
| Strategy Intern | 15 | 45
-
Consulting | SVP Innovation | 102.75 | 275
-
Account | Marketing Coordinator | 18 | 75
| Account Coordinator | 23 | 75
| Account Manager | 27.5 | 115
| Account Supervisor | 46 | 150
| Account Director | 64 | 180
| SVP Client Services | 114 | 275
| - | 0 | 0
Design | Production Designer | 27 | 135
| Senior Production Designer | 42.5 | 150
| Design/Art Director Intern | 13.75 | 45
| Associate Art Director | 28 | 135
| Junior Designer | 23.75 | 115
| Designer | 27.5 | 135
| Senior Designer | 40 | 150
| Associate Director, Production | 63.5 | 175
| Associate Director - Creative Tech | 72 | 200
| Creative Technology Director | 70.25 | 200
| Executive Creative Director | 114.75 | 325
| Photographer | 22.75 | 115
| - | 0 | 0
IA/UX | UX Intern | 13.75 | 45
| UX Designer | 27 | 135
| SVP, Agency Services | 104 | 250
-
Copy | Copy Intern | 15 | 45
| Associate Copywriter | 27 | 115
| Copywriter | 31.75 | 135
| Senior Copywriter | 53 | 150
| Associate Creative Director | 42 | 175
| Creative Director | 63 | 250
| - | 0 | 0
Proj Mgmt | Project Management Intern | 18 | 45
| Project Coordinator | 33 | 65
| Digital Producer | 36.75 | 135
| Project Manager | 35.5 | 150
| Senior Integrated Producer | 54.5 | 175
| Director, Special Projects | 63.5 | 175
| VP, Project Operations | 69 | 200
| - | 0 | 0
Development | Junior Developer | 15 | 65
| Developer | 49.9 | 135
| Senior Developer | 61 | 175
| Technical Manager | 61.5 | 175
| - | 0 | 0
QA | QA Specialist | 30 | 150
| - | 0 | 0
Media | Media Analyst | 28.5 | 85
| Media Manager | 34 | 100
| Senior Media Manager | 37 | 115
| Associate Media Director | 51 | 150
| Media Director | 58.75 | 225
| SVP Media | 99 | 325
-
HVM | Account Management Lead (HVM) | 45.5 | 115
| Account Manager (HVM) | 40 | 100
| Jr. Account Manager (HVM) | 30 | 75
| Director of Media Services (HVM) | 80 | 190
| Junior Media Manager (HVM) | 27.5 | 70
| Manager, Media Services (HVM) | 55 | 135
| Marketing Manager (HVM) | 52 | 130
| Media Coordinator (HVM) | 27 | 70
| Media Manager (HVM) | 35 | 90
| Senior Account Manager (HVM) | 37 | 95
| Senior Director, Account Management (HVM) | 62 | 150
| Senior Media Manager (HVM) | 44 | 110
| Sr Ad Ops & Trafficking Manager (HVM) | 47 | 120
| Sr Media & Analytics Manager (HVM) | 47 | 120

## Rates-F92 (hidden)
Role | Dept | Rate_F92 | Rate_DP+ | Rate_DP_2 | Rate_ADM | ADM_Notes | Rate_BCBSM | Rate_BOS | Rate_FSVR | Rate_FSVOS | Rate_GRA | Rate_HDD | Rate_Mopar | Rate_NYL | Role_NYL | Rate_Studio | Rate_CRO | Rate_SEO | Rate_BCBS24 | Rate_24F92
Account Coordinator | Client Services | 75 | 150 |  | 75 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 75 |  | 75 | 75 | 185 | 160 | 95
Account Director | Client Services | 180 | 150 |  | 180 | ADM Ratecard | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 180 |  | 180 | 180 | 185 | 160 | 230
Account Executive | Client Services | [5 empty] | 150.75 | 152 | 121 | 90 | 135 | 169 | [6 empty] | 160 | 95
Account Executive | KT-OA | [5 empty] | 150.75 | 152 | 121 | 90 | 135 | 169 | [6 empty] | 160 | 95
Account Management Lead (HVM) | Media | 115 | 150 |  | 115 |  | 150.75 | 152 | 121 | 109 | 135 | 169 | 118 | 151.73 |  | 115 | 115 | 185 | 160 | 135
Account Manager | Client Services | 115 | 150 |  | 135 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 115 |  | 115 | 115 | 185 | 160 | 135
Account Manager (HVM) | Media | 100 | 150 |  | 135 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 100 | 100 | 185 | 160 | 135
Account Supervisor | Client Services | 150 | 150 |  | 150 |  | 150.75 | 152 | 159 | 152 | 135 | 169 | 118 | 150 |  | 150 | 150 | 185 | 160 | 160
Ad Ops Specialist | Media | [5 empty] | 150.75 | 152 | 121 | 128 | 135 | 169 | [6 empty] | 160 | 135
Analyst, Analytics | KT-OA | [5 empty] | 150.75 | 152 | 121 | 128 | 135 | 169 | [6 empty] | 160
Analytics Engineer, Sr. | Product | 200 | 150 |  | 200 |  | 150.75 | 152 | 121 | 185 | 135 | 169 | 118 | 170 |  | 200 | 200 | 185 | 160 | 195
Application Testing Engineer | Product | 200 | 150 |  | 200 |  | 150.75 | 152 | 121 | 185 | 135 | 169 | 118 | 150 |  | 200 | 200 | 185 | 160 | 195
Art Director | Creative | 135 | 150 |  | 140 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 135 | 135 | 185 | 160 | 135
Assistant Business Analyst | Product | 60 | 150 | 140 | 60 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 100 |  | 60 | 60 | 185 | 160 | 95
Assoc Dir Project Management | Project Management | 225 | 150 | 140 | 225 |  | 150.75 | 152 | 121 | 185 | 135 | 169 | 118 | 151.73 |  | 225 | 225 | 185 | 160 | 195
Associate Account Director | Client Services | [5 empty] | 150.75 | 152 | 121 | 128 | 135 | 169 | [6 empty] | 160 | 195
Associate Art Director | Creative | 135 | 150 | 140 | 135 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 135 |  | 135 | 135 | 185 | 160 | 95
Associate Copywriter | Creative | 115 | 150 | 140 | 115 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 115 | Copywriter, Jr. | 115 | 115 | 185 | 160 | 95
Associate Creative Director | Creative | 175 | 150 | 140 | 185 | ADM Sr creative approved rate | 150.75 | 152 | 159 | 185 | 135 | 169 | 118 | 175 |  | 175 | 175 | 185 | 160 | 195
Associate Director, Analytics | Creative | 200 | 150 | 140 | 200 |  | 150.75 | 152 | 159 | 185 | 135 | 169 | 118 | 151.73 |  | 200 | 200 | 185 | 160 | 195
Associate Director, Client Engagement | Client Services | 70 | 150 | 140 | 70 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 135 | Assistant Account Manager | 70 | 70 | 185 | 160 | 195
Associate Director, Creative Delivery | Creative | 200 | 150 | 140 | 200 |  | 150.75 | 152 | 159 | 185 | 135 | 169 | 118 | 151.73 |  | 200 | 200 | 185 | 160 | 195
Associate Director, Media | Media | 150 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 185 | 135 | 169 | 118 | 150 |  | 150 | 150 | 185 | 160 | 195
Associate Director, Production | Studio | 175 | 150 | 140 | 175 |  | 150.75 | 152 | 159 | 185 | 135 | 169 | 118 | 175 |  | 175 | 175 | 185 | 160 | 195
Associate Director, Technology | KT-OA |  |  |  | 185 |  | 150.75 | 152 | 159 | 185 | 135 | 169 | [6 empty] | 160 | 195
Associate Director, UX | Creative | 210 | 150 | 140 | 185 | ADM Sr. UX Lead | 150.75 | 152 | 159 | 185 | 135 | 169 | 118 | 151.73 |  | 210 | 210 | 185 | 160 | 195
Asst Project Manager | Project Management | 135 | 150 | 140 | 135 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 65 |  | 135 | 135 | 185 | 160 | 95
Asst. Account Executive | KT-OA | [5 empty] | 150.75 | 152 | 121 | 90 | 135 | 169 | [6 empty] | 160 | 95
Azure DevOps Engineer | Product | 200 | 150 | 140 | 200 |  | 150.75 | 152 | 121 | 185 | 135 | 169 | 118 | 170 |  | 200 | 200 | 185 | 160 | 230
Backend Developer | Technology | 135 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 150 |  | 135 | 135 | 185 | 160 | 135
Brand Strategist | Operations | 45 | 150 | 140 | 45 |  | 150.75 | 152 | 121 | 57 | 135 | 169 | 118 | 151.73 |  | - | 45 | 185 | 160 | 135
Business Intelligence Analyst | Data & Analytics | 115 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 109 | 135 | 169 | 118 | 175 |  | 115 | 115 | 185 | 160 | 135
Business Manager | Creative | 90 | 150 | 140 | 90 |  | 150.75 | 152 | 121 | 109 | 135 | 169 | 118 | 151.73 |  | 90 | 90 | 185 | 160 | 135
CFO | Finance | 425 | 150 | 140 | 425 |  | 150.75 | 152 | 192 | 356 | 135 | 169 | 118 | 200 |  | - | 425 | 185 | 160 | 375
Content Strategist | Strategy | 90 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 90 | 90 | 185 | 160 | 135
Controller | Finance | 200 | 150 | 140 | 200 |  | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 151.73 |  | - | 200 | 185 | 160 | 340
Copy Intern | Creative | 45 | 150 | 140 | 45 |  | 150.75 | 152 | 76 | 57 | 135 | 169 | 118 | 151.73 |  | 45 | 45 | 185 | 160 | 60
Copywriter | Creative | 135 | 150 | 140 | 140 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 135 |  | 135 | 185 | 185 | 160 | 135
Creative Director | Creative | 250 | 150 | 140 | 225 | ADM Ratecard | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 200 |  | 250 | 250 | 185 | 160 | 230
Creative MW Contractor | Creative | 250 | 150 | 140 | 250 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | 250 | 250 | 185 | 160 | 230
Creative Technology Director | Creative | 200 | 150 | 140 | 200 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 200 |  | 200 | 200 | 185 | 160 | 230
Customer Support Specialist | Product | 100 | 150 | 140 | 100 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 70 |  | 100 | 100 | 185 | 160 | 95
Data Analyst | Data & Analytics | 95 |  |  | 150 | ADM Ratecard | 150.75 | 152 | 76 | 90 | 135 | 169 | [6 empty] | 160 | 95
Database Admin | Product | 175 | 150 | 140 | 175 |  | 150.75 | 152 | 121 | 185 | 135 | 169 | 118 | 130 |  | 175 | 175 | 185 | 160 | 195
Database Architect | Product | [5 empty] | 150.75 | 152 | 159 | 219 | 135 | 169 | [6 empty] | 160 | 230
Design/Art Director Intern | Creative | 45 | 150 | 140 | 45 |  | 150.75 | 152 | 76 | 57 | 135 | 169 | 118 | 151.73 |  | 45 | 45 | 185 | 160 | 60
Designer | Creative | 135 | 150 | 140 | 140 |  | 150.75 | 152 | 121 | 109 | 135 | 169 | 118 | 135 |  | 135 | 135 | 185 | 160 | 115
Dev Ops Lead | [6 empty] | 150.75 | 152 | 159 | 219 | 135 | 169 | [6 empty] | 160 | 230
Developer | Technology | 135 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 135 | 135 | 185 | 160 | 135
DevOps Systems Operations Support | Product | 80 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 150 |  | 80 | 80 | 185 | 160 | 95
Digital Designer | Product | 135 | 150 | 140 | 135 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 65 | 135 | 185 | 160 | 135
Digital Producer | Project Management | 135 | 150 | 140 | 150 | Project Manager | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 135 |  | 135 | 135 | 185 | 160 | 135
Director Business Analytics | Analytics | 250 | 150 | 140 | 250 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | 250 | 250 | 185 | 160 | 230
Director of Technology | Technology | 255 | 150 | 140 | 225 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | 255 | 255 | 185 | 160 | 230
Director Project Management | Project Management | 225 | 150 | 140 | 180 | Program Director | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | 225 | 185 | 185 | 160 | 230
Director, Analytics | KT-OA | [5 empty] | 150.75 | 152 | 159 | 219 | 135 | 169 | [6 empty] | 160 | 230
Director, Business Development | Growth | 225 | 150 | 140 | 225 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | - | 225 | 185 | 160 | 230
Director, Development | Product | 225 | 150 | 140 | 225 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 200 |  | 225 | 225 | 185 | 160 | 230
Director, Growth | KT-OA | [5 empty] | 150.75 | 152 | 159 | 219 | 135 | 169 | [6 empty] | 160 | 230
Director, Programatic | Media | 190 | 150 | 140 | 190 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | 190 | 190 | 185 | 160 | 230
Director, Resourcing & Delivery | Project Management | 200 | 150 | 140 | 200 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | 200 | 200 | 185 | 160 | 230
Director, SEO | Media | 225 | 150 | 140 | 225 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | 225 | 225 | 185 | 160 | 230
Director, Social Media | Media | [5 empty] | 150.75 | 152 | 159 | 219 | 135 | 169 | [6 empty] | 160 | 230
Director, Special Projects | Project Management | 175 | 150 | 140 | 175 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 175 |  | 175 | 175 | 185 | 160 | 230
Editing Manager | Project Management | 160 |  |  | 160 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | [6 empty] | 160 | 160
EVP, Media & Activation | Media | 400 | 150 | 140 | 400 |  | 150.75 | 152 | 192 | 356 | 135 | 169 | 118 | 151.73 |  | 400 | 400 | 185 | 160 | 375
EVP, Analytics | KT-OA | [5 empty] | 150.75 | 152 | 192 | 356 | 135 | 169 | [6 empty] | 160 | 375
EVP, Client Services | KT-OA | [5 empty] | 150.75 | 152 | 192 | 356 | 135 | 169 | [6 empty] | 160 | 375
EVP, Data & Analytics | Analytics | 400 | 150 | 140 | 400 |  | 150.75 | 152 | 192 | 356 | 135 | 169 | 118 | 151.73 |  | 400 | 400 | 185 | 160 | 375
EVP, ICOE | KT-OA | [5 empty] | 150.75 | 152 | 192 | 356 | 135 | 169 | [6 empty] | 160 | 375
EVP, Marketing Services | Executive | [5 empty] | 150.75 | 152 | 192 | 356 | 135 | 169 | [6 empty] | 160 | 375
EVP, Product | KT-OA | [5 empty] | 150.75 | 152 | 192 | 356 | 135 | 169 | [6 empty] | 160 | 375
EVP, Strategy | Strategy | 450 | 150 | 140 | 450 |  | 150.75 | 152 | 192 | 356 | 135 | 169 | 118 | 151.73 |  | 450 | 450 | 185 | 160 | 375
Executive Creative Director | Creative | 325 | 150 | 140 | 325 |  | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 200 |  | 325 | 325 | 185 | 160 | 340
Executive Producer | Creative | 250 | 150 | 140 | 250 |  | 150.75 | 152 | 192 | 219 | 135 | 169 | 118 | 151.73 |  | 225 | 225 | 185 | 160 | 230
Founder/CEO | Executive | 500 | 150 | 140 | 500 |  | 150.75 | 152 | 192 | 428 | 135 | 169 | 118 | 200 |  | 500 | 500 | 185 | 160 | 450
Front End Designer | Creative | 125 | 150 | 140 | 125 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 135 |  | 125 | 125 | 185 | 160 | 135
Front End Developer | Technology | 150 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 150 |  | 150 | 185 | 185 | 160 | 160
Full-Stack Developer | Technology | 200 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 150 |  | 200 | 200 | 185 | 160 | 160
Group Account Director | Client Services | 275 |  |  | 275 |  | 150.75 | 152 | 192 | 261 | 135 | 169 | [6 empty] | 160 | 275
Group Creative Director | Creative | [5 empty] | 150.75 | 152 | 192 | 261 | 135 | 169 | [6 empty] | 160 | 275
Growth Operations Manager | Growth | 75 | 150 | 140 | 75 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 75 | 75 | 185 | 160 | 160
Intern |  | 45 | 150 | 140 | 45 |  | 150.75 | 152 | 76 | 57 | 135 | 169 | 118 | 151.73 |  | 45 | 45 | 185 | 160 | 60
Junior Account Manager | Media | 75 | 150 | 140 | 75 |  | 150.75 | 152 | 76 | 90 | 135 | 169 | 118 | 151.73 |  | 75 | 75 | 185 | 160 | 95
Junior Analyst, Analytics | KT-OA | [5 empty] | 150.75 | 152 | 76 | 90 | 135 | 169 | [6 empty] | 160 | 95
Junior Backend Developer | Technology | 150 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 76 | 90 | 135 | 169 | 118 | 125 |  | 150 | 150 | 185 | 160 | 95
Junior Designer | Creative | 115 | 150 | 140 | 115 |  | 150.75 | 152 | 76 | 90 | 135 | 169 | 118 | 115 | Designer, Jr. | 115 | 115 | 185 | 160 | 95
Junior Developer | Technology | 65 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 76 | 90 | 135 | 169 | 118 | 151.73 |  | 65 | 65 | 185 | 160 | 95
Junior Full-Stack Developer | Technology | 150 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 76 | 90 | 135 | 169 | 118 | 125 |  | 150 | 150 | 185 | 160 | 95
Junior Media Manager | Media | 70 | 150 | 140 | 70 |  | 150.75 | 152 | 76 | 90 | 135 | 169 | 118 | 151.73 |  | 70 | 70 | 185 | 160 | 95
Junior Production Designer | KT-OA | [5 empty] | 150.75 | 152 | 76 | 90 | 135 | 169 | [6 empty] | 160 | 95
Manager, Analytics | KT-OA | [5 empty] | 150.75 | 152 | 121 | 128 | 135 | 169 | [6 empty] | 160 | 135
Manager, Growth | KT-OA | [5 empty] | 150.75 | 152 | 121 | 128 | 135 | 169 | [6 empty] | 160 | 135
Manager, Media Services (HVM) | Media | 135 | 150 | 140 | 135 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 135 | 135 | 185 | 160 | 135
Manager, Strategy | KT-OA |  |  |  | 135 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | [6 empty] | 160 | 135
Marketing Analyst | Strategy | 150 | 150 | 140 | 150 |  | 150.75 | 152 | 76 | 128 | 135 | 169 | 118 | 150 |  | 150 | 150 | 185 | 160 | 135
Marketing Coordinator | Client Services | 75 | 150 | 140 | 100 |  | 150.75 | 152 | 76 | 90 | 135 | 169 | 118 | 75 |  | 75 | 75 | 185 | 160 | 95
Marketing Manager |  | 130 | 150 | 140 | 130 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 130 |  | 130 | 130 | 185 | 160 | 135
Marketing Manager (HVM) | Media | 130 | 150 | 140 | 130 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 130 | 130 | 185 | 160 | 135
Media Analyst | Media | 85 | 150 | 140 | 115 |  | 150.75 | 152 | 121 | 109 | 135 | 169 | 118 | 85 |  | 85 | 85 | 185 | 160 | 135
Media Coordinator | Media | 70 | 150 | 140 | 70 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 151.73 |  | 70 | 70 | 185 | 160 | 95
Media Coordinator (HVM) | Media | 70 | 150 | 140 | 70 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 151.73 |  | 70 | 70 | 185 | 160 | 95
Media Director | Media | 225 | 150 | 140 | 225 | pitch rate and aligns with ADM strat director and under exec dir | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 200 |  | 225 | 225 | 185 | 160 | 230
Media Manager | Media | 100 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 135 |  | 100 | 100 | 185 | 160 | 135
Media Manager (HVM) | Media | 90 | 150 | 140 | 90 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 90 | 90 | 185 | 160 | 135
Media Planner/Buyer | Media | 65 | 150 | 140 | 170 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 65 | 65 | 185 | 160 | 135
Media Specialist | KT-OA |  |  |  | 115 |  | 150.75 | 152 | 121 | 109 | 135 | 169 | [6 empty] | 160 | 115
Media Traffic Speacialist | Media | 130 | 150 | 140 | 130 |  | 150.75 | 152 | 76 | 90 | 135 | 169 | 118 | 151.73 |  | - | 130 | 185 | 160 | 115
Photographer | Studio | 115 | 150 | 140 | 115 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 175 |  | 200 | 115 | 185 | 160 | 135
PrePress Manager |  | 140 | 150 | 140 | 140 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 140 | 140 | 185 | 160 | 135
President | Executive | 400 | 150 | 140 | 400 |  | 150.75 | 152 | 192 | 356 | 135 | 169 | 118 | 200 |  | 400 | 400 | 185 | 160 | 375
Producer | Creative | 65 | 150 | 140 | 65 |  | 150.75 | 152 | 76 | 90 | 135 | 169 | 118 | 65 |  | 65 | 65 | 185 | 160 | 115
Product Director | Product | 225 | 150 | 140 | 225 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 195 |  | 225 | 225 | 185 | 160 | 230
Product Manager | Product | [5 empty] | 150.75 | 152 | 121 | 152 | 135 | 169 | [6 empty] | 160 | 160
Product Owner | Product | 100 | 150 | 140 | 100 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 145 |  | 100 | 100 | 185 | 160 | 230
Production Designer | Studio | 135 | 150 | 140 | 150 |  | 150.75 | 152 | 76 | 128 | 135 | 169 | 118 | 135 |  | 135 | 135 | 185 | 160 | 135
Program Lead | KT-OA | [5 empty] | 150.75 | 152 |  |  | 135 | 169 | [6 empty] | 160
Program Manager | Project Management | [5 empty] | 150.75 | 152 | 121 | 152 | 135 | 169 | [6 empty] | 160 | 160
Project Management Intern | Project Management | 45 | 150 | 140 | 45 |  | 150.75 | 152 | 76 | 57 | 135 | 169 | 118 | 151.73 |  | 45 | 45 | 185 | 160 | 60
Project Manager | Project Management | 150 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 150 |  | 65 | 150 | 185 | 160 | 135
Proofreader | Project Management | 150 | 150 | 140 | 150 | ADM QA role | 150.75 | 152 | 121 | 109 | 135 | 169 | 118 | 150 |  | 150 | 150 | 185 | 160 | 115
QA Analyst | Product | 130 | 130 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 130 |  | 150 | 150 | 185 | 160 | 135
Recruiter | HR | 65 | 150 | 140 | 65 |  | 150.75 | 152 | 121 | 90 | 135 | 169 | 118 | 151.73 |  | 100 | 65 | 185 | 160 | 115
Resource Director | Project Management | 125 | 150 | 140 | 150 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | 125 | 125 | 185 | 160 | 230
Resource Manager | Project Management | 125 | 150 | 140 | 150 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 125 | 125 | 185 | 160 | 135
Retoucher | Creative | 115 | 150 | 140 | 115 |  | 150.75 | 152 | 121 | 109 | 135 | 169 | 118 | 151.73 |  | 175 | 115 | 185 | 160 | 115
SCRUM Master | Product | 125 | 150 | 140 | 125 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 125 |  | 125 | 125 | 185 | 160 | 160
SEM Analyst | [6 empty] | 150.75 | 152 | 121 | 109 | 135 | 169 | [6 empty] | 160 | 115
SEM Manager | [6 empty] | 150.75 | 152 | 121 | 128 | 135 | 169 | [6 empty] | 160 | 135
Senior Account Executive | Client Services | 135 |  |  | 135 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | [6 empty] | 160 | 135
Senior Account Manager | Analytics | 150 |  |  |  |  | 150.75 | 152 | 121 | 152 | 135 | 169 | [6 empty] | 160 | 135
Senior Ad Ops & Trafficking Manager (HVM) | Media | 120 | 150 | 140 | 120 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 120 | 120 | 185 | 160 | 135
Senior Analytics Engineer |  | 150 | 150 | 140 | 150 |  | 150.75 | 152 | 159 | 152 | 135 | 169 | 118 | 170 |  | 150 | 150 | 185 | 160 | 160
Senior Applications Systems | KT-OA | [5 empty] | 150.75 | 152 |  |  | 135 | 169 | [6 empty] | 160 | 160
Senior Art Director | Creative | 150 | 150 | 140 | 150 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 150 |  | 150 | 150 | 185 | 160 | 160
Senior Art Director | KT-OA | [5 empty] | 150.75 | 152 | 121 | 152 | 135 | 169 | [6 empty] | 160 | 160
Senior Backend Developer | Technology | 175 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 159 | 152 | 135 | 169 | 118 | 170 |  | 175 | 175 | 185 | 160 | 160
Senior Brand/Content Strategist | Strategy | 200 | 150 | 140 | 185 | ADM_Brand Strategist | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 175 |  | 200 | 200 | 185 | 160 | 160
Senior Copywriter | Creative | 150 | 150 | 140 | 150 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 150 | Copywriter, Sr. | 150 | 150 | 185 | 160 | 160
Senior Customer Support Agent | KT-OA | [5 empty] | 150.75 | 152 | 121 | 152 | 135 | 169 |  | 70 |  |  |  |  | 160 | 160
Senior Data Manager | Media | 150 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 151.73 |  | 150 | 150 | 185 | 160 | 160
Senior Designer | Creative | 150 | 150 | 140 | 150 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 150 | Designer, Sr. | 150 | 150 | 185 | 160 | 160
Senior Developer | Technology | 175 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 151.73 |  | 175 | 175 | 185 | 160 | 160
Senior Director, Account Management (HVM) | Media | 150 | 150 | 140 | 150 |  | 150.75 | 152 | 159 | 261 | 135 | 169 | 118 | 151.73 |  | 150 | 150 | 185 | 160 | 275
Senior Director, Analytics | Media | 275 |  |  | 225 |  | 150.75 | 152 | 159 | 261 | 135 | 169 | [6 empty] | 160 | 275
Senior Director, Product | KT-OA | [5 empty] | 150.75 | 152 | 159 | 261 | 135 | 169 | [6 empty] | 160 | 275
Senior Director, Project Management | Project Management |  |  |  | 180 |  | 150.75 | 152 | 159 | 261 | 135 | 169 | [6 empty] | 160 | 275
Senior Director, Technology | KT-OA | [5 empty] | 150.75 | 152 | 159 | 261 | 135 | 169 | [6 empty] | 160 | 275
Senior Front End Developer | Technology | 175 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 159 | 152 | 135 | 169 | 118 | 150 |  | 175 | 175 | 185 | 160 | 160
Senior Integrated Producer | Project Management | 175 | 150 | 140 | 175 |  | 150.75 | 152 | 121 | 185 | 135 | 169 | 118 | 175 |  | 175 | 175 | 185 | 160 | 195
Senior IT Manager | KT-OA | [5 empty] | 150.75 | 152 |  |  | 135 | 169 | [6 empty] | 160
Senior Media & Analytics Manager (HVM) | Media | 120 | 150 | 140 | 120 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 151.73 |  | 120 | 120 | 185 | 160 | 160
Senior Media Manager | Media | 150 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 151.73 |  | 115 | 150 | 185 | 160 | 160
Senior Production Designer | Studio | 150 | 150 | 140 | 150 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 151.73 |  | 150 | 150 | 185 | 160 | 160
Senior Project Manager | Project Management | 175 | 150 | 140 | 150 | ADM Ratecard | 150.75 | 152 | 159 | 152 | 135 | 169 | 118 | 151.73 |  | 175 | 175 | 185 | 160 | 160
Senior Proofreader | Project Management | 150 | 150 | 140 | 150 |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 150 |  | 150 | 150 | 185 | 160 | 135
Senior QA Analyst | Product | 150 | 150 | 140 | 150 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 150 |  | 150 | 150 | 185 | 160 | 135
Senior SEM Manager | Strategy | 200 | 150 | 140 | 200 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 151.73 |  | 200 | 200 | 185 | 160 | 160
Senior SEO Manager | Strategy | 160 |  |  | 185 | ADM: Brand Strategist | 150.75 | 152 | 121 | 152 | 135 | 169 | [6 empty] | 160 | 160
Social Media Manager | Media | 150 | 150 | 140 | - |  | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | - | - | 185 | 160 | 135
Social Media Specialist | Media | [5 empty] | 150.75 | 152 | 121 | 109 | 135 | 169 | [6 empty] | 160 | 115
Solutions Architect |  | 225 | 150 | 140 | 165 | ADM Ratecard | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 151.73 |  | 225 | 225 | 185 | 160 | 230
Strategic Planner | Strategy | 150 | 150 | 140 | 150 | ADM : Strategist | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 150 | 150 | 185 | 160 | 135
Strategy Director | Strategy | 225 | 150 | 140 | 225 | ADM Ratecard | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 200 |  | 225 | 225 | 185 | 160 | 230
Strategy Intern | Strategy | 45 | 150 | 140 | 45 |  | 150.75 | 152 | 76 | 57 | 135 | 169 | 118 | 151.73 |  | 45 | 45 | 185 | 160 | 60
Studio Manager | Creative | 125 | 150 | 140 | 160 | ADM Ratecard | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 151.73 |  | 125 | 125 | 185 | 160 | 160
SVP, Account Management | Client Services | 275 | 150 | 140 | 325 | Exec Director role | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 200 |  | 275 | 275 | 185 | 160 | 340
SVP, Activation | Growth | 325 | 150 | 140 | 325 |  | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 151.73 |  | 325 | 325 | 185 | 160 | 340
SVP, Brand Strategy | Strategy | 325 | 150 | 140 | 250 |  | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 151.73 |  | 325 | 325 | 185 | 160 | 340
SVP, CRO | CRO | 325 | 150 | 140 | 325 |  | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 200 |  | 325 | 150 | 185 | 160 | 340
SVP, Executive Creative Director | KT-OA | [5 empty] | 150.75 | 152 | 192 | 323 | 135 | 169 | [6 empty] | 160 | 340
SVP, Growth | Growth | 325 | 150 | 140 | 250 |  | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 200 |  | 325 | 150 | 185 | 160 | 340
SVP, Media | Media | 325 | 150 | 140 | 250 | Exec Media Director ADM code | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 200 |  | 325 | 185 | 185 | 160 | 340
SVP, Media & Activation | KT-OA | [5 empty] | 150.75 | 152 | 192 | 323 | 135 | 169 | [6 empty] | 160 | 340
SVP, People Strategy & Innovation |  | 325 | 150 | 140 | 325 |  | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 200 |  | 325 | 325 | 185 | 160 | 340
SVP, Product | KT-OA | [5 empty] | 150.75 | 152 | 192 | 323 | 135 | 169 | [6 empty] | 160 | 340
SVP, Product & Innovation | Technology | 275 | 150 | 140 | 275 |  | 150.75 | 152 | 192 | 323 | 135 | 169 | 118 | 200 |  | 275 | 275 | 185 | 160 | 340
Technical Director | Product | 255 | 150 | 140 | 255 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 195 |  | 255 | 255 | 185 | 160 | 230
Technical Manager | Technology | 175 | 150 | 140 | 175 | ADM Ratecard | 150.75 | 152 | 159 | 152 | 135 | 169 | 118 | 175 |  | 175 | 175 | 185 | 160 | 160
Technical Writer |  | 175 | 150 | 140 | 175 |  | 150.75 | 152 | 121 | 152 | 135 | 169 | 118 | 125 |  | 175 | 175 | 185 | 160 | 160
UI/UX Design System Engineer |  | 125 | 150 | 140 | 125 |  | 150.75 | 152 | 159 | 152 | 135 | 169 | 118 | 200 |  | 125 | 125 | 185 | 160 | 160
UX Designer | Technology | 135 | 150 | 140 | 160 | ADM Ratecard | 150.75 | 152 | 121 | 128 | 135 | 169 | 118 | 151.73 |  | 135 | 135 | 185 | 160 | 135
UX Director | Creative | 250 | 150 | 140 | 250 |  | 150.75 | 152 | 159 | 219 | 135 | 169 | 118 | 200 |  | 250 | 250 | 185 | 160 | 230
UX Intern | Technology | 45 | 150 | 140 | 45 |  | 150.75 | 152 | 76 | 57 | 135 | 169 | 118 | 151.73 |  | 45 | 45 | 185 | 160 | 60
UX Sr. Designer |  | 150 | 150 | 140 | 170 | ADM_UX Architect | 150.75 | 152 | 159 | 152 | 135 | 169 | 118 | 150 |  | 150 | 150 | 185 | 160 | 160
Video Editor | Creative | 115 | 150 | 140 | 115 |  | 150.75 | 152 | 121 | 109 | 135 | 169 | 118 | 151.73 |  | 175 | 115 | 185 | 160 | 115
VP Technology | Technology | 295 |  |  | 250 |  | 150.75 | 152 | 192 | 280 | 135 | 169 | [6 empty] | 160 | 295
VP, Account Director | Client Services | 325 | 150 | 140 | 250 |  | 150.75 | 152 | 192 | 280 | 135 | 169 | 118 | 151.73 |  | - | 325 | 185 | 160 | 295
VP, Business Transformation |  | 275 | 150 | 140 | 275 |  | 150.75 | 152 | 192 | 280 | 135 | 169 | 118 | 151.73 |  | 425 | 275 | 185 | 160 | 295
VP, Client Services | KT-OA | [5 empty] | 150.75 | 152 | 192 | 280 | 135 | 169 | [6 empty] | 160 | 295
VP, Creative Director | KT-OA | [5 empty] | 150.75 | 152 | 192 | 280 | 135 | 169 | [6 empty] | 160 | 295
VP, Data & Analytics | Analytics | 325 | 150 | 140 | 250 |  | 150.75 | 152 | 192 | 280 | 135 | 169 | 118 | 151.73 |  | 325 | 325 | 185 | 160 | 295
VP, Group Account Director | KT-OA | [5 empty] | 150.75 | 152 | 192 | 280 | 135 | 169 | [6 empty] | 160 | 295
VP, Group Creative Director | Project Management | 200 | 150 | 140 | 200 |  | 150.75 | 152 | 192 | 280 | 135 | 169 | 118 | 151.73 |  | 200 | 200 | 185 | 160 | 295
VP, Growth | KT-OA | [5 empty] | 150.75 | 152 | 192 | 280 | 135 | 169 | [6 empty] | 160 | 295
VP, IT | KT-OA | [5 empty] | 150.75 | 152 | 192 | 280 | 135 | 169 | [6 empty] | 160 | 295
VP, Marketing Transformation & Insights | Strategy | 275 | 150 | 140 | 275 |  | 150.75 | 152 | 192 | 280 | 135 | 169 | 118 | 200 |  | 400 | 275 | 185 | 160 | 295
VP, Media Strategy | Media | 275 | 150 | 140 | 250 | Exec Media Director ADM code | 150.75 | 152 | 192 | 280 | 135 | 169 | 118 | 151.73 |  | 275 | 275 | 185 | 160 | 295
VP, Project Management | KT-OA | [5 empty] | 150.75 | 152 | 192 | 280 | 135 | 169 | [6 empty] | 160 | 295
VP, Sales | Client Services | [5 empty] | 150.75 | 152 | 192 | 280 | 135 | 169 | [6 empty] | 160 | 295
VP, SEM & Ecommerce | Media | 400 | 150 | 140 | 250 | ADM_Experience Lead | 150.75 | 152 | 192 | 280 | 135 | 169 | 118 | 200 |  | 400 | 400 | 185 | 160 | 295
VP, Special Projects | Project Management | 175 | 150 | 140 | 175 |  | 150.75 | 152 | 192 | 280 | 135 | 169 | 118 | 151.73 |  | 175 | 175 | 185 | 160 | 295

## RefRC (hidden)
RateCardName | RateCardColumn
Rate_24F92 | 21
Rate_ADM | 6
Rate_BCBS24 | 20
Rate_BCBSM | 8
Rate_BOS | 9
Rate_CRO | 18
Rate_DP_2 | 5
Rate_DP+ | 4
Rate_F92 | 3
Rate_FSVR | 10
Rate_FSVOS | 11
Rate_GRA | 12
Rate_HDD | 13
Rate_Mopar | 14
Rate_NYL | 15
Rate_SEO | 16
Rate_Studio | 17