Michigan Department of Health and Human Services (MDHHS)
Attn: Jarrod Barron
Constitution Hall
525 West Allegan Street
Lansing, MI 48909-7973

Re: MDHHS MIDASH RFP, RFP# 220000001798

Dear Mr. Barron,

Kunz, Leigh and Associates (KL&A) is pleased to propose professional custom software development services in response to the MDHHS MIDASH RFP, RFP# 220000001798.  We have carefully reviewed the RFP and believe that our firm’s experience with and knowledge of MDHHS’s business activities and technology landscape uniquely qualify us for this engagement.  We have three decades of experience building custom solutions for MDHHS that provide remarkably similar functionality to that which has been requested in the RFP.  For example, our Children’s Special Healthcare Services (CSHCS) system includes automated eligibility determination and our Third Party Liability Electronic Database (TED) trades data with over 100 other systems, including many of the systems cited in this RFP, to find TPL leads and ensure consistent and accurate data across the Medicaid landscape.  While the HIV-STD programs’ criteria will differ, our experience building solutions with configurable business rules, multiple integrations, client portals, and other similar functions demonstrates that we can deliver a solution that will increase efficiency, improve communication, ensure data integrity, and make all stakeholders’ lives much easier.

KL&A has a long history of high-quality performance in implementing technical solutions for various State of Michigan agencies, including MDHHS.  As a company, KL&A is committed to MDHHS and the State of Michigan.

We are excited about this opportunity to work with MDHHS again and believe that the combination of our experiences, our tools, and, most importantly, our staff, distinguishes us from our competitors.  We have submitted our proposal through the SIGMA VSS system.  Enclosed in the submission files, you will find comprehensive responses to all the prompts in the RFP.

The remainder of this cover letter provides an executive summary that communicates:

Our understanding of your mission and how we can help you fulfill it;

A high-level description of our approach;

A brief description of our company, credentials, and history with MDHHS;

Our statement of commitment to your success; and

A list of our submission files, along with an explanation of the helpful conventions we use.

# Your Mission and Our Solution

KL&A understands that the Division of HIV and STD Programs (DHSP) is responsible for:

Preventing, caring for, and treating HIV and STIs;

Administering the Ryan White HIV/AIDS Program within Michigan;

Providing support and consultation to local health departments and other healthcare professionals;

Collecting, analyzing, and sharing data on HIV and STIs;

Implementing evidence-based programs and strategies to control HIV and STIs;

Engaging in special studies related to the control of HIV and STIs; and

Acting as a liaison with the Centers for Disease Prevention and Control (CDC) and other federal partners on HIV- and STI-related issues.

We also understand that STD Surveillance, Prevention, and Care programs use a significant number of systems to collect HIV and STD-related data, which results in duplicative data entry, manual linking of data, duplicative client-contact efforts, data silos that reduce transparency, and, most importantly, delays in linking cases and engaging people into care.  The RFP indicates that DHSP is interested in consolidating the following eight systems into one, efficient, user-friendly, ADA-compliant, responsive web application:

CAREWare

Enhanced HIV/AIDS Reporting System (eHARS)

Advanced Public Health Information and Relational Mapping (APHIRM)

Michigan Drug Assistance Program (MiDAP)

ScriptGuide Rx

Michigan Disease Surveillance Systems (MDSS) current functionality for diseases under HIV and STD

Human Immunodeficiency Virus Laboratory Management System (HIVLMS)

HP Enterprise Content Manager

KL&A is proposing a custom solution that will leverage existing functionality from our platform, called KL&A Core, to reduce the time and cost of developing a custom solution.  Functions such as user security, notifications, letter generation, searches, dashboards, and notifications can be leveraged and customized to meet DHSP’s exact needs.

In addition to leveraging functionality, we can apply domain knowledge and functional concepts from other MDHHS systems that we developed, such as CSHCS and TED.  Both of these systems are case management systems that provide similar functionality to that which DHSP has requested.  We can use what we’ve learned from CSHCS to construct eligibility determination logic and we intend to apply case management, configurable workflow, and interface monitoring concepts from TED.

We are proposing a custom solution that will be hosted by DTMB in the State’s Azure or NGDI environment.  We will build the solution in collaboration with DHSP business owners and other identified stakeholders, resulting in a solution that meets all of DHSP’s business needs exactly.  The solution we are proposing will:

Reduce time and cost by eliminating duplicative data entry and manual linking of data, as well as automating data collection processes.

Improve data integrity by consolidating dispersed data into an efficient, normalized data model and implementing improved data validation and duplicate prevention logic.

Improve access to care by reducing delays in case progression through streamlined workflows with systematic work assignments, notifications, and dashboards that keep all stakeholders informed and on track.

Improve client engagement by facilitating communication with clients through a user-friendly, integrated eligibility/client portal.

Reduce frustration for all stakeholders by eliminating data silos, facilitating communications between all stakeholders, automating data collection and repetitive tasks, and providing an efficient, user-friendly solution that will give all stakeholders access to the information they need in one place.

Improve allocation of resources by providing analytics that support data-driven decision-making through an integration with the State’s instance of Power BI.

Lower total cost of ownership—maintaining, supporting, and hosting one system, instead of eight, means lower costs all around.  Using existing State technology, such as MiLogin, FileNet, and Power BI also produces cost savings.  Additionally, a common solution with a consistent user experience will reduce training costs because users will be able to assist each other across the HIV-STD ecosystem.

Peace of mind—the MIDASH Solution will be a highly secure system, architected in a modern framework, and hosted in the State’s GovCloud environment.  Additionally, KL&A is a vendor with a proven track record of delivering State of Michigan enterprise solutions, like CSHCS, TED, and MiCaRS.  DHSP can rest assured that its data will be secure, and that KL&A will deliver an elegant solution that satisfies DHSP’s business users and clients, on time and within budget.

To help evaluators envision our proposed solution, we’ve provided a comprehensive description in the file: 11_MDHHS_MIDASH_SoftwareDescription_FromKLA.docx.

Finally, KL&A understands that there are over 6000 users of the existing legacy systems that will need:

Communication about the impending changes and the reasons for those changes that will excite and engage them to mitigate the risk of resistance,

Communication about training opportunities and implementation events that will prepare them for the change,

Training to be successful, and

Easy-to-use, self-help resources, and a support system to help them if they encounter difficulties.

KL&A plans to partner with Springboard Consulting to provide organizational change management (OCM) and training activities.  Springboard is a Michigan-based, woman-owned consultancy that specializes in preparing people for change, using a people-focused approach to ensure successful system implementations.  Springboard ensures organizations are prepared with the training, tools, and templates needed to reach their goals and experience the benefits of change.  With over 20 years of experience leading change initiatives for private and public sector clients, including the State of Michigan, and several certifications, Springboard brings OCM expertise to the MIDASH Solution project.  Springboard will perform in-depth analyses to determine how and when OCM activities need to be executed and how DHSP can evaluate and monitor preparedness to mitigate risk.  They will work with DHSP and the KL&A technical team to ensure OCM, training, and implementation activities are coordinated.  They will follow the Prosci© methodology to develop an effective OCM strategy that will:

Achieve successful adoption of new processes, roles, and technology;

Develop a change-champion network to support change-enablement activities; and

Develop and sustain change competency.

From the OCM strategy, they will create a thorough OCM Plan that considers user influence, training, documentation, and implementation needs, as well as timing.  The OCM Plan will be designed to minimize user resistance, reduce the learning curve and frustration, empower users to support themselves and one another, avoid technical issues, and generally provide a seamless transition.  The plan will include several role-based elements and activities tailored to move HIV/STD stakeholders forward, such as:

Communication planning;

Project sponsor activities planning;

Manager and supervisor coaching;

Preparedness planning and monitoring;

Training; and

Resistance management.

In addition to a solid solution and thoughtful OCM Plan, a project’s success can also hinge on the implementation approach.

# Our Approach

KL&A is proposing a phased approach to delivering the MIDASH Solution that involves three phases:

Phase 1: Discovery will be an intensive review of business processes, business rules, existing functionality, pain points, and data from the eight systems that are slated for migration to develop a new, more efficient data model, find opportunities for automation, validate requirements, and build a preliminary backlog of user epics and user stories.  During this phase, KL&A will also work with DTMB to provision the necessary environments and with DHSP to develop the preliminary release plan for Phase 3.  Additionally, our OCM team will begin stakeholder analysis and planning activities.

Phase 2: Base Application Design, Development, and Implementation (DDI) will involve building the base application, testing, integrating with MiLogin, completing eMichigan reviews, gaining the Authority to Operate, and deploying the MIDASH Solution to the State’s GovCloud or NGDI infrastructure.

Phase 3: Integration, Migration, and Decommission will involve developing the identified integrations and interfaces and migrating data from and decommissioning the eight legacy systems.  This phase will involve eight rapid-fire releases, one per month, for each legacy HIV/STD-related system.

Figure 1. HIV/STD Solution Timeline

As Figure 1 (above) depicts, the phases will overlap.  Our proposed schedule begins October 3, 2022, with the base application going live on December 19, 2023, 15 months into the project.  All integrations, migrations, and decommissions will be completed on July 3, 2024.  The following table shows our development, UAT, and go-live dates for the eight system releases.

| Release | Dev/Test Start | Dev/Test Finish | UAT Start | UAT Approval | Go-Live |
| --- | --- | --- | --- | --- | --- |
| System 1 | 6/12/23 | 10/16/23 | 11/3/23 | 11/29/23 | 12/21/23 |
| System 2 | 7/14/23 | 11/17/23 | 12/11/23 | 1/16/24 | 1/30/24 |
| System 3 | 8/14/23 | 12/20/23 | 1/16/24 | 2/14/24 | 2/29/24 |
| System 4 | 9/12/23 | 1/25/24 | 2/14/24 | 3/7/24 | 3/29/24 |
| System 5 | 10/6/23 | 2/21/14 | 3/12/24 | 4/2/24 | 4/24/24 |
| System 6 | 11/2/23 | 3/19/24 | 4/8/24 | 4/29/24 | 5/21/24 |
| System 7 | 12/5/23 | 4/16/24 | 5/6/24 | 5/28/24 | 6/19/24 |
| System 8 | 12/19/23 | 4/30/24 | 5/20/24 | 6/11/24 | 7/3/24 |

We will work with DHSP to develop a roadmap that lays out the priorities of major functional components.  Please note that KL&A is open to accelerating the project timeline but would require additional staff on the KL&A side and additional time commitments from DHSP and DTMB.  Accelerating the timeline may also impact the project cost.

KL&A plans to use the Scrum/Agile development methodology.  The project will begin with an initiation, planning, and discovery phase, called sprint zero.  This phase will include requirements validation activities to ensure that planning reflects the full scope of the project, as well as elaboration activities that clarify and refine business and functional requirements, transforming them into user epics and user stories.  This will allow the team to build enough of the product backlog to keep the developers busy.  Throughout the project, the KL&A business analysts will continue requirements elaboration, producing user stories with acceptance criteria and mockups for each requirement.  This continuous stream of elaboration and design allows the developers to focus on what they do best, building the solution, and provides DHSP with agility to reprioritize requirements if the need arises.  OCM analysis and planning activities will also begin during sprint zero.

Figure 2. Scrum Process Diagram

In parallel with sprint zero, Phase 2: Base Application DDI will begin.  This phase will involve 24, 2-week development sprints.  Before each sprint, a DHSP-appointed product owner will review the product backlog prioritization, providing DHSP with the agility to respond to changing business needs.  The team will then plan the sprint, pulling as many of the highest priority stories off the product backlog as they can complete in the 2-week time box.  Then they will begin the sprint.  Toward the end of each sprint, the KL&A team will demonstrate the functionality developed during the sprint to field DHSP feedback.  Feedback can then be evaluated for project impact and potentially added to the product backlog.

Our testing cycles will also operate in sprints but will lag one sprint behind to maximize productivity.  The testing team will run automated regression tests and manual functional and system integration tests to ensure quality, after which they will facilitate a user acceptance test cycle for the sprint.  During each sprint, the business analysts will also update related State Unified Information Technology Environment (SUITE) documentation, user manuals, and training materials to ensure that these artifacts always reflect the current state of the software.  In addition to sprint UAT, our team will facilitate a UAT cycle for each release that is holistic and regressive.

This process of iteratively delivering tested functionality and updated documentation provides transparency that reduces risk, ultimately increasing DHSP’s confidence as the project progresses.  After all the sprints and the release are tested and user-accepted, we will work with DTMB to deploy the new MIDASH Solution to the production environment.

Phase 3: Integration, Migration, and Decommission will overlap with Phase 2.  It will involve eight system releases, each comprising nine 2-week sprints.  Each release will involve developing integrations/interface and data migration/conversion scripts, migrating data to a staging environment, reviewing data migration results, facilitating user acceptance of interfaces and data migration, deploying migrated data to production, and decommissioning the respective legacy system.

Figure 3. Daily Scrum

KL&A is a leader in introducing Agile methodologies to the State of Michigan.  In 2010, our CSHCS system implementation was the first MDHHS project that was purely Agile, while complying with the SUITE deliverable requirements.  Since 2010, we have continued our commitment to Agile methodologies, including providing Certified Scrum Master and/or Certified Product Owner training and certifications to over 37 of our staff members.  Each calendar year we renew that commitment and ask more staff members to complete Scrum training and certification.

KL&A differs from other vendors that use Agile approaches in that we believe that a project cannot be successful without the full buy-in of our clients.  In an Agile team, the “product owner” is the person who is responsible for prioritizing the product backlog and, therefore, should be a representative of the client’s organization.  In 2014, we asked our MDHHS Third Party Liability partner on the TED project to commit fully to this approach.  Before this decision, the KL&A project manager acted as the proxy product owner, prioritizing the backlog on behalf of the client.  The Director of Third Party Liability (TPL) agreed to fully commit to the Agile methodology.  She also had key project stakeholders attend KL&A-coordinated Scrum Product Owner training with the Scrum Alliance (www.scrumalliance.org).  After training and certification, four key MDHHS project stakeholders took on the role of “product owner” for various areas of the project.  Today, the MDHHS TPL team uses Jira, our backlog management, sprint planning, test tracking, and defect tracking tool, to participate as fully integrated team members.  Since then, we’ve repeated this process for other clients, such as MDHHS WIC, and have experienced significant decreases in scope changes and increases in project velocities.

More detail about our process is provided in our Statement of Work response:

10_MDHHS_MIDASH_Schedule-A-SOW_FromKLA.docx

In addition to a proven project approach, a vendor with the right credentials and a history that demonstrates success can provide DHSP with confidence that the MIDASH Solution project will be successful.

# Our Company, Credentials, and History with MDHHS

Figure 4. KL&A Partners Jim Kunz (left), David Desrochers (middle), and Martin Tompkins (right)

KL&A is an information technology solutions provider with two offices in the State of Michigan, $22.1 million in annual revenue, and 152 employees.  KL&A was founded in 1992, by partners Jim Kunz and John Leigh.

KL&A started with a small, but highly qualified staff operating out of our Lathrup Village office.  Over the past 30 years, KL&A has formed several long-lasting relationships with our clients.  Today, KL&A serves numerous commercial clients, several state governments, and 16 State of Michigan agencies.  These relationships have resulted in substantial growth of staff and service offerings.  In the past seven years, we’ve expanded our Okemos office three times and added new services, such as application hosting.  We’ve also become SOC 2 Type II Certified, a Microsoft Certified Gold Partner, and an Atlassian Solution Partner.

KL&A has a long history with MDHHS.  We’ve developed and modernized numerous MDHHS systems, such as CSHCS, TED, Medicare Buy-In, Newborn Screening Online (NBSO), MiTracking, HAI Tracker, and Michigan Cashiering and Receivables System (MiCaRS), just to name a few.

In addition to the aforementioned experience, we are uniquely qualified for this opportunity because:

Our experience with Medicaid-related projects, including eligibility determination/certification and benefits management used by the CSHCS system equip us with an understanding of complex business processes that are similar to those of the MDHHS MIDASH Initiative;

Our experience integrating systems with or working directly with CHAMPS, ISD/Bridges, the Data Warehouse, MCIR, MiHIN/HIE, SIGMA, FileNet, FTS, Power BI, and MiLogin means we can hit the ground running with modernization activities;

Our experience working with DTMB, Michigan Cyber Security (MCS), and eMichigan to ensure all our applications are secure, have Authority to Operate, and are compliant with Michigan’s look and feel standards, as well as the ADA, means you can count on us to deliver a secure, compliant, user-friendly, and responsive MIDASH Solution; and

Our comprehensive testing approach, which was used to help MDHHS establish the Testing Center of Excellence, will be used to ensure that modernized and new functionality is properly tested to provide a reliable and high-quality user experience.

Figure 5. KL&A Partners John Leigh (left), Justin Shaulis (middle), Tim Hollosy (right)

Our Okemos location allows us to better serve our State of Michigan government clientele while attracting top talent to give us our competitive edge.  Our contemporary, open, collaborative office design facilitates communication, teamwork, creativity, and innovation.  Pre-pandemic, we regularly extended our office to State of Michigan staff for team meetings and planning sessions.

However, it is important to note that KL&A’s staff have been working remotely, during the COVID-19 pandemic, with remarkable efficiency.  We’ve even begun new State of Michigan system modernization projects, such as the Michigan Agriculture Environmental Assurance Program (MAEAP) modernization project, the Food Inspection Regulatory System Technology (FIRST) project, and the MDHHS Women, Infants, and Children (WIC) maintenance project with several new development initiatives, without missing a beat.  We have the appropriate tools to provide real-time, synchronous communication with our clients, ensuring our projects run smoothly even when we cannot be in the same room.  We would like the State to know that we have proven our ability to initiate new projects for large-scale, complex modernizations under these trying circumstances.  We are prepared to begin this project, even if we are not able to meet in person.  The State can rest assured that there will be no delays or impediments to productivity if remote work is required.

Finally, KL&A’s commitment to our clients and our exceptional staff are the keys to our success.  We take a collaborative approach in the assessment, planning, design, development, testing, and implementation of any IT project, whether we are developing a software application or providing oversight or quality assurance services.  We work closely with business users, subject matter experts, and other project stakeholders to develop a comprehensive understanding of the needs and desires of our clients so that we can deliver high-quality services and products.  KL&A uses well-defined, repeatable processes and generates a prescribed set of project artifacts to ensure projects are completed on time, within budget, and that the results not only meet but exceed customer expectations.

# Your Success

When evaluating vendors for the MIDASH Solution, we believe KL&A is the clear choice.  We are proposing a custom solution that leverages our KL&A Core functional components, as well as the State of Michigan's existing IT investments to achieve a custom-built solution for less.  We also have a successful history with MDHHS, providing on-time, in-budget software development and implementation projects, such as CSHCS, TED, NBSO, MiTracking, HAI Tracker, MiCaRS, and others.  We have a proven track record of designing, developing, and implementing many successful large-scale .NET MVC applications for the State of Michigan.  The Agile (Scrum) development methodology is at the heart of our company culture.  The tenants of constant self-reflection, process improvement, and a commitment to deliver excellent software drive us forward.

Figure 6. Key Success Factors

Our single objective for the MDHHS MIDASH Initiative is the successful implementation of the desired features and functions within the established timeframe and budget, which is dependent upon each of the following key success factors:

A proven vendor with the State of Michigan;

Skilled, experienced, quality staff equipped with sophisticated tools and techniques;

Collaborative methodologies that encourage teamwork and client participation; and

Most importantly, a committed relationship with the MDHHS and DTMB.

KL&A has each of these key elements and has always taken great pride in our past and ongoing work with the State of Michigan and MDHHS.  We are committed to your success.

# This Proposal

Enclosed, you will find our proposal which remains in effect for 120 days from the submission date.  To comply with the file-size limitations of SIGMA, we’ve chosen to break up our response into the following documents:

Cover Letter

01_MDHHS_MIDASH_CoverLetter_FromKLA.docx

Confidentiality Form

02_MDHHS_MIDASH_ConfidentialityForm_FromKLA.docx

Vendor Question Worksheet and attachments

03_MDHHS_MIDASH_VendorQuestionWorksheet_FromKLA.docx

04_MDHHS_MIDASH-VQW-Attach1-AdditionalInfo-TED_FromKLA.docx

05_MDHHS_MIDASH-VQW-Attach2-AdditionalInfo-CSHCS.docx

06_MDHHS_MIDASH-VQW-Attach3-AdditionalInfo-LOTS_FromKLA.docx

07_MDHHS_MIDASH-VQW-Attach4-AdditionalInfo-HAI_FromKLA.docx

Resumes

08_MDHHS_MIDASH_Attachment1-Resumes-FromKLA.docx

IT Professional Contract Terms

09_MDHHS_MIDASH_ITContractTerms_FromKLA.docx

Statement of Work response and associated attachments

10_MDHHS_MIDASH_Schedule-A-SOW_FromKLA.docx

11_MDHHS_MIDASH_SoftwareDescription_FromKLA.docx

12_MDHHS_MIDASH_Transition-In-OutPlan_FromKLA.docx

13_MDHHS_MIDASH_Sample-MiEHDWIS_EntityActionsDrawer_Video.zip

14_MDHHS_MIDASH_Sample-Training-VMS_5_Release_2_Day_1_FromKLA.pptx

15_MDHHS_MIDASH_Sample-Training-VMS_5_Release_2_Day_2_FromKLA.pptx

16_MDHHS_MIDASH_Sample-Training-VMS_5_Release_2_Close_FromKLA.pptx

17_MDHHS_MIDASH_Sample-Training-VMS-5.2_Manual_FromKLA.pdf

18_MDHHS_MIDASH_Sample-Manual-OSRS_RMS_UserGuide_FromKLA.pdf

19_MDHHS_MIDASH_Springboard_JobAid_Example_FromKLA.pdf

20_MDHHS_MIDASH_WBS-Schedule-Detail_FromKLA.pdf

Schedule A, Specifications

21_MDHHS_MIDASH_ScheduleA-Table1-Specifications_FromKLA.docx

Schedule B, Pricing

22_MDHHS_MIDASH_ScheduleB-Pricing_FromKLA.docx

Schedules C-G

23_MDHHS_MIDASH_Schedules-C-G_FromKLA.docx

To aid document navigation and ease identification of response text, our proposal documents use the following conventions:

Hierarchical headings that can be displayed in the Microsoft Word navigation pane.  On a PC, Ctrl + F invokes the navigation pane.

Hyperlinked cross-references.  When viewing a document in MS Word, to jump to a referenced section, hold down Ctrl and click the section name or page number.

Blue response text that makes it easy to distinguish our responses from the RFP prompt text.

Navigation Pane

Hyperlinked Cross-References 
Ctrl + Click to Jump to Referenced Section

Blue Response Text for Easy Identification

Figure 7. Proposal Conventions Illustration

For any additional information or questions, please contact me at j.shaulis@kunzleigh.com or (517) 803-3217.

Sincerely,

Justin Shaulis
KL&A Partner

MDHHS DHSP About Us/How to Contact Our Staff Webpage