MIDASH Solution Proposal

Response to RFP# 220000001798
Schedule A – Statement of Work Response

Prepared for:

Michigan Department of Health and Human Services (MDHHS)

Division of HIV and STD Programs (DHSP)

Constitution Hall

525 West Allegan Street

Lansing, MI 48909-7973

Prepared by:

Kunz, Leigh & Associates

28081 Southfield Road

Lathrup Village, MI 48076-2816

V1.0

June 1, 2022

(Back of title page.)

Proposal Signatures

| Name/Title | Signature | Date |
| --- | --- | --- |
| Justin Shaulis, KL&A Partner |  | 6/1/22 |

Page intentionally blank to support duplex printing.

Table of Contents

Proposal Response Checklist	11

Schedule A: Statement of Work	15

1. DEFINITIONS	15

2. BACKGROUND	17

3. PURPOSE	17

4. IT ENVIRONMENT RESPONSIBILITIES	17

Bidder Response to Schedule E - Data Security Requirements	18

Security Officer	19

Contractor Responsibilities	19

Acceptable Use Policy	22

Protection of State’s Information	22

Security Accreditation Process	25

Unauthorized Access	26

Security Audits	27

Application Scanning	27

Infrastructure Scanning	28

Nonexclusive Remedy for Security Breach	28

5. ADA COMPLIANCE	29

Bidder Response to ADA Compliance	30

6. USER TYPE AND CAPACITY	33

Bidder Response to User Type and Capacity	35

How the Number of Concurrent Users will be Supported	35

Application Scaling	35

Latency Response Time	36

Capacity Planning	36

Required Network Connectivity and Equipment	36

Role-Based User Management	37

Roles and Responsibilities	37

7. ACCESS CONTROL AND AUTHENTICATION	38

Bidder Response to Access Control and Authentication	38

8. DATA RETENTION AND REMOVAL	39

Bidder Response to Data Retention Policy	40

9. END USER OPERATING ENVIRONMENT	40

Bidder Response to End-User Operating Environment	42

Optimal Technical Environment	42

State System-Access Requirements	43

Current and Future State Environment Compliance	43

Original Environment Support	43

Communication of Roadmap Changes	43

Customer Collaboration	43

Necessary Plug-Ins	44

10. SOFTWARE	44

Bidder Response to Software	46

Detailed Description of the MIDASH Solution	46

Unique Software Requirements	46

System Access Requirements	47

Custom Software Required to Support Internal SOM Systems	47

Third-Party and Open-Source Components	47

Look-and-Feel Standards	48

Mobile Responsiveness	49

Supported Mobile Devices	50

Features that Will Be Mobile Responsive	50

Optional Add-On Modules	50

Contractor Services	51

Functional Scalability	51

Roles and Responsibilities	52

11. INTEGRATION	53

Bidder’s Response to Integration	54

12. MIGRATION	56

13. TRAINING SERVICES	74

Bidder Response to Training Services	75

Options, Class Size, Materials, and Resources	75

Training Plan	76

Past Experience that Demonstrates Springboard’s Capabilities	77

Training Materials Examples	77

Training Video Examples	77

Other Training Materials Examples	78

Job Aid Example	79

14. TRANSITION RESPONSIBILITIES	79

Bidder Response to Transition Responsibilities	79

Transition-In and Transition-Out Plan	80

15. DOCUMENTATION	80

Bidder Response to Documentation	80

Examples of End-User Videos and Documentation	82

16. ADDITIONAL PRODUCTS AND SERVICES	82

Bidder Response to Additional Products and Services	82

Basic Elements	83

Roles and Responsibilities	85

Help Desk Process Phases	86

Phase 1: Planning	86

Phase 2: Defect Triage, Logging, and Assignment	87

Phase 3: Defect Repair and Closeout	87

17. CONTRACTOR PERSONNEL	88

Bidder Response to Contractor Personnel	88

Contractor Personnel	90

Project Manager	90

Security Lead	91

HIV/STI Functional Lead	91

Business Analyst Lead	92

Human-Centered Design (HCD) / User Experience (UX) Design Lead	93

Agile Team Lead / Technical Lead / Solution Architect	94

Integration Lead / Data Migration / Production Support Engineer	95

Test Lead	96

Organizational Change Management (OCM) Lead	96

Training and Business Readiness Lead	97

Resource Allocation Breakdown	99

18. CONTRACTOR KEY PERSONNEL	101

19. CONTRACTOR PERSONNEL REQUIREMENTS	101

Bidder Response to Disclosure of Subcontractor	102

20. STATE RESOURCES/RESPONSIBILITIES	104

21. MEETINGS	105

Bidder Response to Meetings	107

22. PROJECT CONTROL & REPORTS	110

Bidder Response to Project Control & Reports	111

23. OCM CONTROL & REPORTS	112

Bidder Response to OCM Control & Reports	112

24. PROJECT MANAGEMENT	113

Bidder Response to SUITE Documentation	114

Bidder Response to Agile Methodology	115

Sprint Zero	118

Requirements Validation Methodology	119

Discovery JADs	120

Functional JADs	121

Technical JADs	121

User Story Review and Approval Process	122

Application Development	123

Implementation	124

Testing	124

Automated Testing	125

Manual Testing	125

Closeout	127

Warranty Period	127

Maintenance and Support	127

Tools	127

Deliverable Review Process	129

Change Control	131

Change Control Roles and Responsibilities	131

Change Control Governance	132

Process Description	132

Steps and Actions	133

Capturing and Monitoring Project Changes	133

Communicating Project Changes	134

Bidder Response to Software Development Documentation	135

Bidder Response to Milestones and Deliverables	140

Proposed Timeline	140

Work Breakdown Structure (WBS) & Project Schedule	143

25. ORGANIZATIONAL CHANGE MANAGEMENT	143

Bidder Response to Executive Leadership and Middle Manager Engagement and Support	143

Bidder Response to Stakeholder Engagement and Support	144

Bidder Response to Solution and Stakeholder Alignment	145

Bidder Response to Business Readiness	146

Bidder Response to Change Champion Network Engagement and Support	147

Bidder Response to Communication Management	148

Bidder Response to Measurement	149

Bidder Response to Sustainment and Transfer of Ownership	150

26. ADDITIONAL INFORMATION	151

List of Figures

Figure 1. VMS Training Manuals Screen	79

Figure 2. VMS Training Manuals Screen	81

Figure 3. Organization Units that Interact with Jira	85

Figure 4. Resource Allocation Breakdown by Role and Month	99

Figure 5. Illustration for Agile Scrum Process	116

Figure 6. KL&A Associates Conducting a Collaborative Planning Session	116

Figure 7. Requirement Validation & Elaboration Process	120

Figure 8. Jira User Story Review Board	122

Figure 9. Release Mechanics Illustration (Repeated for Each Release)	126

Figure 10. Milestone/Deliverable Review Process Flow	129

Figure 11. Deliverable Comment Form (DCF)	131

Figure 12. Agile/Scrum Process	136

Figure 13. Proposed Implementation Timeline	141

List of Tables

Table 1. Proposal Response Checklist	11

Table 2. Third-Party Materials and Open-Source Components	47

Table 3. Defect Classification Required by  SCHEDULE D - SERVICE LEVEL AGREEMENT Provided with RFP# 220000001798	83

Table 4. Meetings KL&A will Regularly Conduct Throughout the Project	107

Table 5. KL&A's SDLC Tools	127

Table 6. QASP 18F Surveillance Metrics	137

Table 7. Proposed System Release Timeline	142

This page is intentionally blank to support duplex printing.

# Proposal Response Checklist

The following table came from the “Proposal Instructions” section of RFP# 220000001798.  The purpose of the table is to demonstrate that KL&A has responded to all required prompts.

Table 1. Proposal Response Checklist

| Document | Description | Bidder Response Instructions | Reference to KL&A’s Response |
| --- | --- | --- | --- |
| Cover Page | Provides title and number, important dates, and contact information for Solicitation Manager | Informational | N/A |
| Proposal Instructions | Provides instructions to Bidders | Informational | N/A |
| Confidential Treatment Form | Required verification on whether bidder’s proposal contains confidential information | Bidder must complete and submit by proposal deadline | Refer to file: 02_MDHHS_MIDASH_ConfidentialityForm_FromKLA.docx |
| Vendor Questions Worksheet | Background and Experience | Bidder must complete and submit by proposal deadline | Refer to file: 03_MDHHS_MIDASH_VendorQuestionWorksheet_FromKLA.docx We’ve also included attachments that provide functional narratives with screenshots for each project that is referenced in the Vendor Questions Worksheet. Refer to the following files: 04_MDHHS_MIDASH-VQW-Attach1-AdditionalInfo-TED_FromKLA.docx 05_MDHHS_MIDASH-VQW-Attach2-AdditionalInfo-CSHCS.docx 06_MDHHS_MIDASH-VQW-Attach3-AdditionalInfo-LOTS_FromKLA.docx 07_MDHHS_MIDASH-VQW-Attach4-AdditionalInfo-HAI_FromKLA.docx |
| Attachment 1, Resume Templates | Key Personnel Resume Template | Bidder must complete and submit by proposal deadline | Refer to file: 08_MDHHS_MIDASH_Attachment1-Resumes-FromKLA.docx |
| IT Professional Services Contract Terms and Conditions. | This document provides the Contract Terms for any contract awarded from this solicitation | Deemed accepted by Bidder unless information required in the Evaluation Process section of this document is submitted by the proposal deadline. | Refer to file: 09_MDHHS_MIDASH_ITContractTerms_FromKLA.docx |
| Schedule A—Statement of Work | Statement of Work details | Bidder must complete and submit by proposal deadline | This file contains KL&A’s Schedule A response. |
| Schedule A, Table 1 Business Specification Worksheet | Business requirements | Bidder must complete and submit by proposal deadline | Refer to file: 21_MDHHS_MIDASH_ScheduleA-Table1-Specifications_FromKLA.docx |
| Schedule B – Pricing | Pricing | Bidder must complete and submit by proposal deadline | Refer to file: 22_MDHHS_MIDASH_ScheduleB-Pricing_FromKLA.docx |
| Schedule C – Insurance | This document provides the Contract Insurance Requirements for any contract awarded from this contract. | Deemed accepted by Bidder unless information required in the Evaluation Process section of this document is submitted by the proposal deadline. | Refer to file: 23_MDHHS_MIDASH_Schedules-C-G_FromKLA.docx |
| Schedule D - Service Level Agreement | This document provides the Service Level Agreement for any contract awarded from this. | Deemed accepted by Bidder unless information required in the Evaluation Process section of this document is submitted by the proposal deadline. | Refer to file: 23_MDHHS_MIDASH_Schedules-C-G_FromKLA.docx |
| Schedule E – Data Security Requirements | This document provides the Data Security Requirements for any contract awarded from this. | Deemed accepted by Bidder unless information required in the Evaluation Process section of this document is submitted by the proposal deadline. | Refer to file: 23_MDHHS_MIDASH_Schedules-C-G_FromKLA.docx |
| Schedule F – Transition In and Out Plan | This document provides the Transition in and Out Plan from the Contractor for any contract awarded from this. | To be provided by Bidders and subject to negotiation. | Refer to files: 23_MDHHS_MIDASH_Schedules-C-G_FromKLA.docx 12_MDHHS_MIDASH_Transition-In-OutPlan_FromKLA.docx |
| Schedule G – Federal Provision | Explanation of Provision | Informational | Refer to file: 23_MDHHS_MIDASH_Schedules-C-G_FromKLA.docx |
| Schedule G, Attachment 1 Byrd Anti-Lobbying Certification | Limitation on Payments to Influence Certain Federal Transactions | To be completed by Bidders | Refer to file: 23_MDHHS_MIDASH_Schedules-C-G_FromKLA.docx |

# Schedule A: Statement of Work

BIDDER INSTRUCTIONS: This schedule identifies the anticipated requirements of any Contract resulting from this RFP. The term “Contractor” in this document refers to a bidder responding to this RFP. Bidder must respond to each requirement or question marked “BIDDER RESPONSE” below and explain how it will fulfill each requirement. Attach any supplemental information and appropriately reference within your response.

DEFINITIONS

The following terms have the meanings set forth below.  All initial capitalized terms that are not defined in this Schedule shall have the respective meanings given to them in Section 1 of the Contract Terms and Conditions.

| Term | Definition |
| --- | --- |
| SOM | State of Michigan |
| CBO | Community Based Organization |
| LHD | Local Health Department |
| CDC | Centers for Disease Control and Prevention |
| HRSA | Health Resources Services Administration |
| HIVLMS | HIV Laboratory Management System -The HIV Lab Management Database was developed to manage HIV/STD lab Results that are imported and stored as read-only entries in the application to maintain the integrity of the original lab. |
| MDSS | Michigan Disease Surveillance System – The MDSS is the main communicable disease reporting system for the state of Michigan covering all communicable diseases that are reportable under the Public Health Code. |
| eHARS | Enhanced HIV /AIDS Reporting System - eHARS collects HIV surveillance data from case reports, lab reports, death certificates, birth certificates, and other documents. |
| APHIRM | Advanced Public Health Information and Relational Mapping – Aphirm is a client-focused software system that handles data for multiple disease types and services to measure and evaluate outcomes related to CDC funded HIV Prevention activities. |
| EvalWeb/PSWeb | Evaluation Web and Partner Services Web are combined to create APHIRM |
| MiDAP (ADAP) | Michigan Drug Assistance Program (Formerly AIDS Drug Assistance Program) - MiDAP is a safety net program serving Michigan residents who are income eligible and are not Medicaid beneficiaries. |
| SGRX | ScriptGuideRx - is a Prescription Benefits Management Application that provides direct pharmacy and benefit coordination services for uninsured and underinsured eligible Ryan White HIV/AIDS Program (RWHAP) clients in the state of Michigan. |
| CAREWare | CAREWare is an electronic health and social support services information system for HRSA’s Ryan White HIV/AIDS Program recipients and providers. |
| CMS | Centers for Medicare and Medicaid Services |
| MiHIN | Michigan Health Information Network - Michigan Health Information Network (MiHIN) is a statewide effort to facilitate and coordinate advancing the use of health information technology and HIE in Michigan’s healthcare system to reduce the overall cost while increasing quality of care and patient safety. |
| NIST | National Institute of Standards and Technology - A physical sciences laboratory and a non-regulatory agency of the United States Department of Commerce. Its mission is to promote innovation and industrial competitiveness. |
| ESB | Enterprise Service Bus |
| DCH FTS | Department of Community Health File Transfer Service |
| CRF | Case Report Form – Paper or electronic form used to report newly diagnosed or update cases of HIV or STDs. The HIV CRF differs from the CRF for other STDs. |
| RIDR | Routine Interstate Duplicate Review – A CDC provided list of HIV cases reported within the preceding six months with a potential duplicate in another state. The list is generated every six months. |
| CIDR | Cumulative Interstate Duplicate Review – A one-time CDC provided list of all HIV cases with a potential duplicate in another states. |
| DDDM | Data Driven Decision Making is the process of using data to inform your decision-making process and validate a course of action before committing to it. |
| HCD | Human Centered Design - An approach to problem solving, commonly used in design and management frameworks that develops solutions to problems by involving the human perspective in all steps of the problem-solving process. |
| MPI | Master Person Index |

BACKGROUND

The MDHHS HIV and STI Surveillance, Prevention, and Care programs maintain a significant number of HIV and STI-related data systems. Most are specialized to collect specific types of data that must be manually linked to one another. The singular nature of these data systems causes a significant portion of staff-hours to be dedicated to entering duplicate information in separate systems, linking data among systems, and, in the case of partner services, duplicate efforts in contacting clients. Most significantly, the lack of interoperability across systems ultimately reduces the ability to quickly link and re-engage people into care. There are several main data systems that providers, LHDs, CBOs, and MDHHS use to track testing diagnoses and treatment of HIV and other STIs.

PURPOSE

The purpose of this RFP is to establish a multi-year contract with a Contractor that can consolidate the data from these systems and provide a cohesive interface that allows the consumption of all the data from a central location. The State is seeking a custom-developed, State-Hosted Software Solution and applicable Services. The State will be following an Agile methodology for this project.  The Contractor must also follow an Agile methodology for this project.

MDHHS anticipates that there will be three types of integrations:

Integrations which will no longer be necessary due to the merging of the existing systems

Integrations which will be required to implement the new system

Integrations which will be developed to support the user functionality needed by the MiDASH system.

See Integration section below for further details.

Contractor will need to migrate data from the following systems:

CAREWare

eHARS

APHIRM

MiDAP

MDSS (HIV and STI data only)

HIV LMS

See Migration section below for further details.

MDHHS anticipates that annually, or upon another cadence as may be requested by the State from time to time, the parties will determine required additional system enhancements.

IT ENVIRONMENT RESPONSIBILITIES

Bidder must confirm it is proposing a State-Hosted, custom-developed application.

BIDDER RESPONSE:

KL&A is proposing a custom-developed application that will be hosted on the State’s infrastructure.

Included in SCHEDULE E – Data Security Requirements; the bidder will be required to meet all State PSP’s, public and non-public applicable to this RFP.  Non-public State PSP’s are available to bidders under NDA. As part of this RFP, bidder is required to sign NDA before non-public PSP’s are distributed.
BIDDER RESPONSE:

KL&A has reviewed Schedule E – Data Security Requirements.  KL&A agrees to meet all State PSPs applicable to this RFP and takes no exceptions.  We are also willing to sign an NDA.

Bidder must describe how identified components will maintain compliance with requirements in the SCHEDULE E - Data Security Requirements.
BIDDER RESPONSE:

See KL&A’s response below in blue text.

### Bidder Response to Schedule E - Data Security Requirements

KL&A has completed a SOC 2 Type II examination.  A copy of our current SOC 2 Type II report is available upon request.

A SOC 2 Type II report is specifically intended to meet the common needs of a broad audience of KL&A’s Custom Development practice.  This includes prospective user entities, independent auditors, and practitioners providing services to such user entities, and regulators who have sufficient knowledge and understanding of the following:

The nature of the services provided by KL&A.

How KL&A’s system interacts with user entities, business partners, subservice organizations, and other parties.

Internal control and its limitations.

Complementary subservice organization and user entity controls and how those controls interact with related controls at KL&A to achieve KL&A’s service commitments and system requirements.

User entity responsibilities and how they may affect the user entity’s ability to effectively use KL&A’s services.

The applicable trust services criteria.

The risks that may threaten the achievement of the applicable trust services criteria and how controls address those risks.

The SOC examination includes information and our independent third-party CPA’s opinion about the description of our data security system, the suitability of its design, and the effectiveness of the operating controls.

Per RFP# 220000001798, the MIDASH Solution will be hosted in the State of Michigan managed IT environment, and our response to this section is based on this requirement.

#### Security Officer

KL&A will appoint an employee to respond to the State’s inquiries regarding the security of the solution.  This employee will have sufficient knowledge of the solution’s security and will also have the authority to act on behalf of KL&A in matters relating to the security of the solution.

#### Contractor Responsibilities

KL&A has an internal security group responsible for physical, network, data, and organizational security.  We have practices and policies in place to ensure data is not being used or accessed by unauthorized individuals or parties.  These policies include employee background checks, encrypted computers and mobile devices, a designated Privacy and Security Officer, and restricted building access.  Additionally, many of our associates complete, annually, the “Employee Security Awareness Training,” provided by the State of Michigan.

KL&A takes data privacy and information security seriously.  KL&A staff are deeply familiar with both federal and state regulations that impact security, privacy policy, and operations, including Personally Identifiable Information (PII), Protected Health Information (PHI), and Internal Revenue Service (IRS) standards.  KL&A staff involved in projects related to health privacy are mandated to complete the annual Health Insurance Portability and Accounting Act (HIPAA) and Health Information Technology for Economic and Clinical Health Act (HITECH) training.  Our data privacy and information security program, documented in our Employee Handbook, includes administrative, physical, technical, and organizational controls to ensure that only personnel who need to know can access protected data.

All KL&A employees are obligated to maintain confidentiality and to protect the security of data.  KL&A’s data privacy and information security awareness policies cover internal company data confidentiality, as well as external client data confidentiality.  Employees are granted access to administer and support data based upon their role and need to perform related necessary job activities.

Our networks and all devices used by KL&A staff are encrypted, password-protected, and required to run anti-virus software.  We use data corroboration methods, such as checksum, double-keying, message authentication, and digital signatures to ensure data integrity.  We also have procedures around authenticating entities with which we communicate.

To protect employees and safeguard both company and client assets, physical security is enabled and enforced at all KL&A facilities.  Access to our buildings is restricted to employees and invited guests who must sign in and out and be accompanied by a KL&A employee.  An automated lock system enforces badge access outside of business hours at KL&A’s customer-facing building.  For our non-customer-facing building, a passcode is required for access twenty-four hours a day.  Video surveillance is present in the customer-facing building to include points of access into the building and to provide additional security during off-hours.  Real-time alerts are provided to administrators as part of the monitoring process and the actual video is viewed by administrators periodically to ensure the alerts are accurate.

We also have procedures in place for ensuring data privacy and information security when an employee leaves KL&A.  This includes following a deprovisioning checklist to remove the authorization of all assigned physical and logical access, disabling enterprise domain accounts, and working with applicable clients to ensure all access is revoked.  Also, disposal procedures are in place to assist personnel in sanitizing equipment to ensure data is unrecoverable before retiring a virtual asset.

If company or client data or information is breached or is suspected to have been breached, the breach event must be immediately reported to KL&A’s designated Privacy and Security Officer as defined in our Employee Handbook.  The Privacy and Security Officer will follow state and federal guidelines for reporting the breach, if necessary, to the appropriate parties.

All KL&A associates share the responsibility for protecting the confidentiality and security of data.  The endorsed final copy of our Security Policy is made available to all employees and covers topics such as:

Privacy and Security Definitions

Confidentiality Agreement (which is required upon employment and at the start of contract work)

Company Data Confidentiality Policies

Client Data Confidentiality Policies

Protected Health Information Privacy

Subcontractor Requirements

Privacy Breach Reporting Requirements

Our Security Policy is incorporated into the company’s Employee Handbook as a code of practice for all associates.  Every associate is required to read, agree to, and sign an affirmation of these policies annually and new employees are introduced to these policies during orientation.

KL&A also requires our employees to abide by and follow our clients’ policies and procedures when given access to their facilities.  KL&A’s hiring policy requires an extensive background check, including a criminal background check, to make sure all our staff members are properly vetted.

KL&A’s policies and procedures are aligned with NIST SP 800-53 and are designed to:

(a) Ensure the security and confidentiality of our client’s data;

(b) Protect against any anticipated threats or hazards to the security or integrity of client data;

(c) Protect against unauthorized disclosure, access to, or use of the client data;

(d) Ensure the proper disposal of client data; and

(e) Ensure that all KL&A personnel comply with all of the foregoing.

Finally, KL&A acknowledges and is committed to complying with applicable State IT policies, standards, and procedures at all times.

KL&A’s role and responsibilities:

Establishing and maintaining a data privacy and information security program.

Complying with all applicable State IT Policies, Standards, and Procedures (PSPs).

Working with and assisting the State in completing infrastructure service requests and EASAs.

Designing and developing web services for secure data sharing.

Performing data security risk assessments and developing mitigation strategies.

Performing any necessary scans and penetration testing to ensure data security.

Ensuring that client data is properly disposed of.

Working with our team and the State to ensure all architecture and designs adhere to data security best practices and ensure all DTMB and Michigan Cyber Security (MCS) security assessments and documents are completed.

The State’s role and responsibilities:

Working with KL&A to meet data privacy and information security requirements.

Monitoring KL&A compliance with all State IT Policies, Standards, and Procedures (PSPs).

Leading the completion of infrastructure service requests and EASAs.

Working with KL&A to ensure all DTMB and MCS security assessments and documents are properly completed and stored for future use and reference.

#### Acceptable Use Policy

KL&A has read, understands, and agrees to comply with the State of Michigan Technical Standard 1340.00.130.02 Acceptable Use of Information Technology.  Our resources will only use State IT resources for work related to the project.

KL&A team members will agree, in writing, to the State’s Acceptable Use Policy before accessing the State’s system.  Each team member will sign any State required policy acknowledgment forms or agreements.  Further, KL&A will monitor team members’ usage of State resources to ensure compliance and will work with the State to quickly remedy any suspected violations.

KL&A’s role and responsibilities:

KL&A contract administrator will:

Be the single point of contact to which State personnel can report any concerns regarding suspected violations of the Acceptable Use Policy.

Ensure all concerns are properly handled in accordance with State expectations.

KL&A project manager will be responsible for:

Ensuring that all KL&A team members have provided written agreement to comply with the Acceptable Use Policy.

Monitoring KL&A team members' usage of State resources.

Escalating any violations to the KL&A contract administrator.

All KL&A team members will be responsible for:

Submitting a written agreement to the Acceptable Use Policy before gaining access to State systems.

Complying with the Acceptable Use Policy.

The State’s role and responsibilities:

Monitor KL&A team member usage of State of Michigan resources.

Report suspected violations to the KL&A contract administrator for remediation.

Terminate access for any KL&A team member who does not comply with the Acceptable Use Policy.

#### Protection of State’s Information

KL&A will ensure that the software and State data are securely hosted, supported, administered, accessed, and backed up in a data center that resides in the continental United States, and minimally meets Uptime Institute Tier 3 standards http://www.uptimeinstitute.com/ or its equivalent.  We will maintain and enforce an information security program, including safety, physical, technical, and security policies and procedures with respect to the processing of State data that complies with the requirements of the State’s data security policies as outlined in any awarded contract, and must, at a minimum, remain compliant with FISMA and NIST Special Publication 800-53 MOD Controls, using identified controls and minimum values as established in applicable State PSPs.

KL&A will provide technical and organizational safeguards against accidental, unlawful, or unauthorized access to or use, destruction, loss, alteration, disclosure, encryption, transfer, commingling, or processing of such information that ensure a level of security appropriate to the risks presented by the processing of State data consistent with best industry practices and applicable standards.

Further, KL&A will take all reasonable measures to secure and defend all locations, equipment, systems, and other materials and facilities employed in connection with the services against “malicious actors” and others who may seek, without authorization, to destroy, disrupt, damage, encrypt, modify, copy, access, or otherwise use hosted services or the information found therein.  KL&A will prevent:

The State and its authorized users from having access to the data of other customers, or such other customers’ users of the services.

State data from being commingled with or contaminated by the data of other customers or their users of the services.

Unauthorized access to any State data.

Data encryption will be used to provide a high level of security to the State’s electronic data by translating data into an unreadable format.  To protect the confidentiality and integrity of information, encryption will be used when moving or storing protected information to minimize the likelihood that the information is inadvertently disclosed or accessed.  Encryptions are managed by Secure Socket Layer (SSL) certificates and filesystem-level encryption.  KL&A will ensure that data is encrypted in transit across internal or external networks and at rest when stored in permanent or removable media.  Following SOM technical standards 1340.00.170.03 Electronic Data Encryption Standard and 1340.00.170.01 System and Communications Protection Standard, KL&A will use Advanced Encryption Standard (AES) 256-bit or higher symmetric key encryption algorithms.

The solution will integrate with MiLogin, which can be configured to support multifactor authentication via text, phone call back, e-mail, or through the IBM Security Verify mobile application, as well as identify proofing.

KL&A has substantial experience integrating SAML with Microsoft Internet Information Services (IIS).  We have many State of Michigan applications in production that use SAML 2.0 for MiLogin integration with applications, running on Microsoft IIS.  This includes:

LPS—In production since April 2019 (includes MiLogin Worker, MiLogin Citizen, and MiLogin Third Party)

INTELS—In production since July 2019 (includes MiLogin Worker and MiLogin Third Party)

FOIA—In production since January 2020 (includes MiLogin Worker and MiLogin Citizen)

911—In production since April 2020 (includes MiLogin Worker and MiLogin Third Party)

MiEHDWIS—In production since September 2020 (includes MiLogin Worker, MiLogin Citizen, and MiLogin Third Party)

For SAML integration, we will work with the MiLogin team (identity provider) to facilitate a secure metadata exchange.  Using this SAML-based metadata, KL&A (service provider) will configure native SAML solutions, during application startup.  For .NET/IIS applications, this entails application-level and session-level configuration to allow access only to those users whose identity and authorization, via secured SAML authentication messaging from MiLogin, have been verified.

Finally, we attest that we will remain in compliance and support the State of Michigan to remain compliant with HIPAA, IRS, PCI, FISMA, and NIST Special Publication 800.53 (most recent version) as established in the applicable State PSPs and as verified through the State’s security accreditation process and the DTMB/ Michigan Cyber Security (MCS) System Security Plan (SSP) process.

KL&A’s role and responsibilities:

Ensuring software and State data are securely hosted, supported, administered, accessed, and backed up in data centers that reside in the continental United States, and minimally meet Uptime Institute Tier 3 standards http://www.uptimeinstitute.com/ or its equivalent.

Maintaining and enforcing an information security program.

Providing technical and organizational safeguards to protect State data.

Taking all reasonable measures to protect State data and other customers’ data.

Ensuring that all data is encrypted in transit and at rest.

Working with the State to implement MiLogin integration, using SAML 2.0.

Providing multifactor authentication via text, phone call back, e-mail, or through the IBM Security Verify mobile application.

Remaining in compliance with HIPAA, IRS, PCI, FISMA, and NIST at all times.

The State’s role and responsibilities:

Monitoring KL&A compliance with all requirements related to the protection of the State’s information.

Working with KL&A to implement MiLogin integration, using SAML 2.0.

#### Security Accreditation Process

KL&A will work with the State through the State’s security accreditation process and ensure the secure application development life cycle (SADLC) requirements are met.  We will assist and provide information for completing the required System Security Plan (SSP), including the System Registration and Profile (SRP), Risk Assessment (RA), Plan of Action and Milestones (POAM), and obtaining the required Authority to Operate (ATO) for the solution.  KL&A has extensive experience and played a major role working in the State’s technical environment and within DTMB/Michigan Cyber Security (MCS) security policies, as demonstrated through the successful creation and acceptance of SSPs and obtaining ATOs on several systems that KL&A developed, and currently maintains, and supports.

KL&A’s role and responsibilities:

Ensuring compliance with all State IT policies, standards, and procedures (PSP).

Working with the State to meet SADLC requirements.

Assisting and providing information for the development, completion, and ongoing maintenance of the required SSP and obtaining the ATO.

Working with the State to create State-approved POAMs.

Working with and assisting the State in the performance of required application and infrastructure scans, as well as remediation and validation efforts.

Providing the State with a risk assessment of system issues.

Working with and assisting the State in completing infrastructure service requests and EASAs.

Working with the State to ensure all architecture and designs adhere to data security best practices and ensuring all DTMB and MCS security assessments and documents are completed.

The State’s role and responsibilities:

Hosting the solution on the DTMB infrastructure.

Validating all State IT PSPs are being met by KL&A.

Working with KL&A to meet SADLC requirements.

Leading the development, completion, and ongoing maintenance of the required SSP and obtaining the ATO.

Working with KL&A to create, review, and approve POAMs.

Performing required application and infrastructure scans and leading remediation and validation efforts for any high vulnerabilities discovered.

Approving acceptable risks.

Leading the completion of infrastructure service requests and EASAs.

Working with KL&A to ensure all DTMB and MCS security assessments and documents are properly completed and stored for future use and reference.

#### Unauthorized Access

KL&A will not access, nor allow access to, State systems without the State’s prior written authorization.  KL&A understands such authorization may be revoked by the State in writing at any time, that access to State systems will be solely in accordance with any awarded contract, and such access will not exceed the scope of the State’s authorization.  KL&A also understands all State-authorized connectivity or attempted connectivity to State systems shall be only through the State’s security gateways and firewalls and in compliance with the State’s security policies outlined in any awarded contract.

KL&A’s role and responsibilities:

Ensure access to State systems does not occur before receiving written authorization.

Ensure all State-authorized connectivity or attempted connectivity to State systems is only through the State’s security gateways and firewalls and in compliance with the State’s security policies.

The State’s role and responsibilities:

Provide written authorization to KL&A to access State systems.

Monitor KL&A’s access to State systems.

#### Security Audits

KL&A will maintain complete and accurate records of our data protection practices, IT security controls, and security logs related to State data, including but not limited to any backup, disaster recovery, or other policies, practices, or procedures related to State data and other relevant information.

KL&A understands the State has the right to review our data privacy and information security program before the commencement of services and as necessary, during the term of an awarded contract.  KL&A also understands the State may perform an on-site audit of our data privacy and information security program and we will make appropriate staff and relevant materials available during normal business hours, for inspection and audit by the State or an independent data security expert that is reasonably acceptable to KL&A.  KL&A further understands if a security audit is performed, the State may include penetration and security tests of externally hosted services and their housing facilities and operating environments, and KL&A will implement any required safeguards identified by the audit.

KL&A understands our obligations to the State and is committed to meeting all requirements within this section.  KL&A also understands the State may terminate any contract or Statement of Work due to failure by KL&A to meet the requirements specified within this section.

KL&A’s role and responsibilities:

Maintain complete and accurate records of our data protection practices, IT security controls, and security logs related to State data.

In the event of an on-site audit, make appropriate staff and relevant materials available, during normal business hours, for inspection and audit by the State or an independent data security expert.

Implement required safeguards identified by an audit.

The State’s role and responsibilities:

Review KL&A’s data privacy and information security program before the commencement of services and as necessary, during the period of an awarded contract if so desired.

Perform an on-site audit of KL&A’s data privacy and information security program if so desired.

#### Application Scanning

Using a State-approved scanning tool, KL&A will run static and/or dynamic application scans as required.  We will perform scan results analysis, provide scan results in a format acceptable by the State, remediate any high application vulnerabilities found, and validate that high application vulnerabilities have been properly remediated during the development and implementation of each major release, as well as regularly, during maintenance periods.  We typically use Veracode to perform both dynamic application security testing (DAST) and static application security testing (SAST).

KL&A’s role and responsibilities:

Performing required application scans and working with the State in completing remediation and validation efforts for any high vulnerabilities discovered.

Providing the State with a risk assessment of system issues.

The State’s role and responsibilities:

Working with KL&A in the performance of required application scans and leading remediation and validation efforts for any high vulnerabilities discovered.

Approving of acceptable risks.

#### Infrastructure Scanning

Per RFP# 220000001798 the MIDASH Solution will be hosted in the State of Michigan managed IT environment.  As such, infrastructure scanning is the responsibility of the State.

KL&A’s role and responsibilities:

Assisting with infrastructure scans, if needed, and working with the State in completing remediation and validation efforts for any high vulnerabilities discovered.

The State’s role and responsibilities:

Leading the performance of infrastructure scans and leading remediation and validation efforts for any high vulnerabilities discovered.

Approving of acceptable risks.

#### Nonexclusive Remedy for Security Breach

KL&A understands our obligations to the State and is committed to meeting all requirements with respect to the security of State data and confidential information.  KL&A also understands the State may terminate any contract due to failure by KL&A to meet the requirements specified in Schedule E – Data Security Requirements.

For a State Hosted Software Solution:

Definitions:

Application – Software programs that provide functionality for end-user and Contractor services

Development - Process of creating, testing, and maintaining software components

| Component Matrix | Disclose subcontractor name(s), if applicable. |
| --- | --- |
| Application | Not Applicable |
| Development | Not Applicable |

Bidder must identify any subcontractor(s) that it intends to use for the components in the table above. KL&A does not intend to use any subcontractors for the components in the table above. We will, however, subcontract OCM and training services, which are discussed in the applicable prompts later in this document. Please provide additional information if this matrix above does not adequately identify the division of responsibilities. Not Applicable

ADA COMPLIANCE

The State is required to comply with the Americans with Disabilities Act of 1990 (ADA) and has adopted standards and procedures regarding accessibility requirements for websites and software applications.  All websites, applications, software, and associated content and documentation provided by the Contractor as part of the Solution must comply with Level AA of the World Wide Web Consortium (W3C) Web Content Accessibility Guidelines (WCAG) 2.0.

Contractor must provide a description of conformance with WCAG 2.0 Level AA specifications by providing a completed PAT for the Solution.  If the Solution is comprised of multiple products, a PAT must be provided for each product.  In addition to PATs, Contractors may include a verification of conformance certified by an industry-recognized third-party.  If the Contractor is including any third-party products in the Solution, Contractor must obtain and provide the third-party PATs as well.

Each PAT must state exactly how the product meets the specifications.  All “Not Applicable” (N/A) responses must be fully explained.  Contractor must address each standard individually and with specificity; and clarify whether conformance is achieved throughout the entire product (for example – user functionality, administrator functionality, and reporting), or only in limited areas.  A description of the evaluation methods used to support WCAG 2.0 Level AA conformance claims, including, if applicable, any third-party testing, must be provided.  For each product that does not fully conform to WCAG 2.0 Level AA, Contractor must provide detailed information regarding the plan to achieve conformance, including timelines.

Bidder must provide a description of conformance with WCAG 2.0 Level AA specifications by providing a completed PAT for the Solution.  If the Solution is comprised of multiple products, a PAT must be provided for each product.  In addition to PATs, Bidders may include a verification of conformance certified by an industry-recognized third-party.  If the Bidder is including any third-party products in the Solution, Bidder must obtain and provide the third-party PATs as well.

Each PAT must state exactly how the product meets the specifications.  All “Not Applicable” (N/A) responses must be fully explained.  Contractor must address each standard individually and with specificity; and clarify whether conformance is achieved throughout the entire product (for example – user functionality, administrator functionality, and reporting), or only in limited areas.  A description of the evaluation methods used to support WCAG 2.0 Level AA conformance claims, including, if applicable, any third-party testing, must be provided.  For each product that does not fully conform to WCAG 2.0 Level AA, Bidder must provide detailed information regarding the plan to achieve conformance, including timelines.

Bidder must provide details of how they will meet these requirements.

BIDDER RESPONSE:

See KL&A’s response below in blue text.

### Bidder Response to ADA Compliance

KL&A acknowledges that the State is required to comply with the ADA and has established accessibility requirements for websites and software applications.  KL&A’s experience developing ADA-compliant applications and working with eMichigan for approval of our designs provides us with a clear understanding of the State’s expectations, policies, and procedures for confirming level AA conformance to the base-level WCAG 2.0 (2008) standards.  KL&A also incorporates additional success criteria for level AA in the published 2.1 (2018) and draft 2.2 (early 2021) versions of the WCAG.  There were 12 additional success criteria items in 2.1 and eight additional items in 2.2 to meet level AA.  As newer standards are published by the W3C, KL&A incorporates the new success criteria into our standards to ensure the systems we develop are current with the latest criteria.

KL&A has established standards and templates that ensure every web application we develop:

Is perceivable to all users, regardless of ability, through techniques such as applying alternative text to non-text elements, including icons and graphics.

Is adaptable and can be presented in different ways without losing information through the use of semantic markup that designates headings, regions, lists, emphasis, etc.; tabular data with cell-heading associations; text labels for input elements; tags that govern the navigation and reading order for blind or low-vision users; and autocomplete features to assist users with entering certain kinds of data.

Is distinguishable for low-vision, color-blind, or dyslexic users through techniques such as appropriate contrast, screen elements that do not rely on color to convey meaning, responsive design to allow for zooming in 200% or more without compromising readability or functionality or requiring horizontal scrolling, and design standards that provide sufficient line spacing, white space, left- or right-aligned text (as opposed to justified text), among others.

Is keyboard accessible to assist users of all abilities, including those who are blind, have low vision, or have difficulty with fine motor movements, with techniques such as:

Attributes that ensure users can navigate or tab through all screens and input fields,

Shortcuts that don’t conflict with browser or screen readers shortcuts, and

A dynamic focus that is never locked or trapped on a specific screen element.

Provides users with enough time to respond, regardless of ability, with techniques such as no timeouts or configurable timeouts, interim saving to minimize or prevent data loss if a timeout occurs, and timeout warning messages.

Avoids seizure or physical reaction by not using flashing animations.

Supports easy navigation with techniques such as proper heading structures and page regions/landmarks that allow users to bypass blocks, descriptive page titles, a logical and intuitive hierarchy of pages, links, and form elements, multiple ways to access each page, breadcrumbs to help users understand their location, and more.

Supports a variety of input modalities, such as pointer gestures for single-point activation, pointer cancellation, alternative text on buttons and other controls, adequate target sizes (minimum of 44 x 44 pixels), and multiple-input device support so users can tap, click, or use a keyboard.

Is readable using techniques such as language attributes and on-screen help text.

Is predictable through consistent navigation and control identification across all pages of the application, as well as minimal page changes when a user interacts with controls.

Provides input assistance through field validation, meaningful error text and suggestions for how to resolve an error, on-screen help text, and error prevention through confirmation prompts or undo options.

Is compatible with a wide variety of assistive technologies through validated HTML/XHTML, the use of Accessible Rich Internet Applications (ARIA), and other techniques.

Our development and testing teams use a variety of tools for validation and accessibility audits, such as:

Axe for in-browser accessibility testing

The W3C HTML/XHTML validator (http://validator.w3.org/) for markup validity

Chrome LightHouse and Dev Tools for accessibility audits and debugging

ChromeVox screen reader and JAWS screen reader to verify tab order and alternate text descriptions

WebAIM’s WCAG 2 Checklist (https://webaim.org/standards/wcag/checklist) to ensure compliance

WebAIM’s Contrast Checker (https://webaim.org/resources/contrastchecker/) to ensure a sufficient contrast when clients desire unique color themes

Chrome WAVE browser extension to evaluate web content for accessibility

All functionality created for the MIDASH Solution will be developed using our strict coding and design standards and will be approved by eMichigan to ensure ADA compliance moving forward.  KL&A will complete the required PAT for the solution and gather any necessary PATs from applicable third-party applications that are used in the solution.  KL&A plans to use the Agile/Scrum approach to development, which means that ADA compliance will be iteratively reviewed with each sprint and PATs submitted for each release.

KL&A roles:

KL&A business analysts to gather business and functional requirements, including user interface and accessible design requirements, and acceptance criteria.

KL&A development lead to ensure KL&A’s standards and templates comply with WCAG 2.0, level AA, and the State’s accessibility standards and to ensure the development team is adhering to KL&A’s standards and using the prescribed templates.

KL&A developers to ensure all new user interfaces are developed in compliance with KL&A’s and the State’s standards and to work with eMichigan through the SOM Web Application Review process.

KL&A quality analysts to test the web application against the requirements and acceptance criteria and, if applicable, create and maintain automated test cases.

Please note that these roles may be fulfilled by a single resource.  For example, many of our analysts fulfill both the business analyst and the quality analyst roles.

State roles:

MDHHS subject matter experts to provide input regarding business and functional requirements, approve screen mockups and navigation, and perform user-acceptance testing of newly developed functionality.

eMichigan team to evaluate and approve KL&A’s web application designs.

USER TYPE AND CAPACITY

Contractor Solution must meet the following expected number of Users and Concurrent Users. The User Groups and number of users are subject to change during initial phase of discovery.

| User Groups | How they will be using the solution | Number of Users | Number of Concurrent Users |
| --- | --- | --- | --- |
| SOM Staff | - General data entry - Canned reporting - Ad Hoc reporting - Custom reporting and data analysis - Dashboard management - Importing files and supporting documentation - Exporting files and supporting documentation - Case management and search - Client management and search - Field management and search - Workflow processing | 200+ | 30-50 |
| Business Application Administrator | - Roles and permission security management - Custom data field creation - Dashboard management - Approve/deny access - User profile management - System message management - System algorithm management - Audit logs access - Business rule management | 10-20 | 2-3 |
| SOM Manager | - Create work tasks and assignments - Assign work tasks and assignments - Canned reporting - Ad hoc reporting - Dashboard management - Custom reporting and data analysis - Client and case search | 15-20 | 2-5 |
| Client/Patient | - Apply for eligible benefits - Review personal health information - Request for assistance - Uploading of support documentation | 5000+ | 30-50 |
| Local Health Department | - General data entry - Canned reporting - Ad Hoc reporting - Custom reporting and data analysis - Dashboard management - Case management and search - Client management and search - Field management and search - Workflow processing - Uploading of support documentation | 300+ | 30-50 |
| Health Care Provider/Universities | - General data entry - User access request - Canned reporting - Uploading of support documentation - Client and case search | 125 | 25 |
| Pharmaceutical Partner | - General data entry - User access request - Canned reporting - Uploading of support documentation - Client and case search | 10 | 2-4 |
| Lab Partner | - Electronic file transfers - Manual data file uploads | 250 | 10-15 |
| Community Based Organization | - General data entry - Canned reporting - Ad Hoc reporting - Uploading supporting documentation - Case management and search - Client management and search | 50 | 25 |

Bidder must explain how it will be able to support the expected number of concurrent Users. Bidder must also explain whether the Solution can scale up or down without affecting performance.
BIDDER RESPONSE:

See KL&A’s response below in blue text.

Bidder must provide details regarding latency response time for (i.e., Generate Page Load, standardized reporting, ad hoc reporting).  The Bidder must identify what network connectivity or equipment will the State be required to have to meet the expected latency response time?

See KL&A’s response below in blue text.

### Bidder Response to User Type and Capacity

This section discusses how concurrent users and application scaling will be supported, latency response time, capacity planning, required network connectivity, and role-based user management.

#### How the Number of Concurrent Users will be Supported

KL&A has experience handling hundreds of State-employee users in applications that require concurrent actions on shared data.  We’ve also developed several applications that are used by the general public and can support thousands of users.  Concurrency is relatively easy to handle in an always-connected application by using transactions that are, by their nature, atomic.

#### Application Scaling

Load scalability for web applications can be a problem when the amount of user interaction varies greatly over short periods.

Vertical scalability is permissible within the limitations of a virtual shared application server, where load scalability can be managed for smaller applications by devoting more memory, CPU cores, or bandwidth to an application.

Horizontal scalability is another option where additional server application instances can be added to other hardware resources but requires deliberate design decisions.  Horizontal scalability provides instant and continuous availability, without being limited by hardware capacity.  It also provides built-in redundancy and is easy to size and resize as demand increases.

Vertical and horizontal scaling is usually performed by the system administrator in charge of the application.  Additionally, scalability will be emphasized during application development through many design patterns, such as:

Client-side applications that reduce the server load by making the client (mobile device or desktop) do more of the work.  So, more users can operate on a single application server as the client handles more logic and page rendering.

Restful APIs that emphasize stateless design and are a part of enabling a server application to be distributed.

Proper server-state management constraints; e.g., not allowing session or static variables to be updated, and configuring proper request lifecycle with transaction scope, will allow for distribution of server instances.

#### Latency Response Time

KL&A will conduct testing throughout development to verify that response times are within desired timeliness constraints.  KL&A will also use server logs and browser tools to verify load times and track request latency.  Using client-side application design offers the user interaction speed of a single-page application (SPA).  KL&A has experience optimizing the modularization of client-side components to maximize initial application load speed.  Application response time will be a focus throughout development.

When latency is inevitable due to long-running tasks, KL&A will consider using asynchronous processing.  By handing off long-running tasks to a service or batch processor, the user will receive instant feedback that the request has been received and it will then be processed in the background, leaving the presentation tier more available for on-demand requests.

#### Capacity Planning

KL&A’s technical architect will work directly with the State’s IT resources to determine the best path forward based on application requirements, performance testing results, and demand expectations.  During the initial design phase, the expected capacity needs will be reviewed and considered when determining the correct application scaling plan, such as vertical or horizontal.  As the project develops, performance will be continuously monitored using both application and database profilers to pinpoint existing and potential bottlenecks.

#### Required Network Connectivity and Equipment

Our solution will be hosted in a State of Michigan GovCloud environment (Azure or NGDI).

As requested in the RFP, KL&A will work with DTMB to establish the following five logical environments to which the frontend UI will be deployed:

DB Sandbox

Development-DEV

UAT/Training

TEST Prod

PROD

KL&A's solution will use three database environments:

Development

UAT/Staging

Production

We’ve provided a network diagram in our solution description attachment, please refer to file: 11_MDHHS_MIDASH_SoftwareDescription_FromKLA.docx.

#### Role-Based User Management

A robust security plan is central to any enterprise web application.  In this case, it is also imperative that the solution works with existing State of Michigan (SOM) authentication mechanisms.  To achieve both goals, our solution will make use of available role and group authentication mechanisms.  This will allow administrators to easily manage application access with a fine degree of control.  Our solution will integrate with the MiLogin Worker, Third Party, and Citizen portals, via SAML 2.0, for user authentication.

State staff will use the Worker portal,

Facility users (a.k.a., external users) who are affiliated with the various partners will use the Third-Party portal to take advantage of multifactor authentication, and

Clients will use the Citizen portal which will be configured to require multifactor authentication and identity proofing.

In addition to single sign-on (SSO), the MIDASH Solution will allow administrators to create roles and assign them to users.  This allows an administrator to not only restrict access to entire pages within the system but also allows an administrator to enable and disable certain functionality inside individual pages.  For example, MDHHS could have a role that provides users full access to update and create a particular kind of record; another role that allows users to view, but not modify or create that type of record; and other roles that prevent users from even seeing the record’s page.  All the systems that KL&A has developed for the State of Michigan include role-based security that provides administrators with maximum flexibility in securing application features.

Further, our solution will provide a feature that allows users to request security roles and facility affiliations, which will generate activities for the DHSP system administrator or facility administrator, depending upon the type of user, to approve, approve with modification, or deny the request.  A detailed explanation of our proposed user authentication and provisioning functionality is included in our solution description.  Please refer to file:

11_MDHHS_MIDASH_SoftwareDescription_FromKLA.docx.

#### Roles and Responsibilities

KL&A:

KL&A technical architect to determine infrastructure needs based on capacity planning, which includes defining expectations and analyzing results of performance and load testing.

KL&A technical architect to work with the State and other vendors as necessary to establish and maintain the appropriate infrastructure necessary to achieve capacity expectations.

State:

Business owners to work with KL&A to define capacity requirements and assist with user-acceptance testing.

Technical resources to work with KL&A’s technical architect and development team to implement the MIDASH Solution.

ACCESS CONTROL AND AUTHENTICATION

The Contractor’s solution must integrate with the State’s IT Identity and Access Management (IAM) environment as described in the State of Michigan Digital Strategy (1340.00.130.02 Acceptable Use of Information Technology (michigan.gov)), which consist of which consist of:

MILogin/Michigan Identity, Credential, and Access Management (MICAM).  An enterprise single sign-on and identity management solution based on IBM’s Identity and Access Management products including, IBM Security Identity Manager (ISIM), IBM Security Access Manager for Web (ISAM), IBM Tivoli Federated Identity Manager (TFIM), IBM Security Access Manager for Mobile (ISAMM), and IBM DataPower, which enables the State to establish, manage, and authenticate user identities for the State’s Information Technology (IT) systems.

MILogin Identity Federation.  Allows federated single sign-on (SSO) for business partners, as well as citizen-based applications.

MILogin Multi Factor Authentication (MFA, based on system data classification requirements).  Required for those applications where data classification is Confidential and Restricted as defined by the 1340.00 Michigan Information Technology Information Security Policy (i.e. the proposed solution must comply with PHI, PCI, CJIS, IRS, and other standards).

MILogin Identity Proofing Services (based on system data classification requirements).  A system that verifies individual’s identities before the State allows access to its IT system. This service is based on “life history” or transaction information aggregated from public and proprietary data sources. A leading credit bureau provides this service.

To integrate with the SOM MILogin solution, the Contractor’s solution must support SAML, or OAuth or OpenID interfaces for the SSO purposes.

Bidder must explain how they will meet the requirements for Access Control and Authentication.

See KL&A’s response below in blue text.

### Bidder Response to Access Control and Authentication

The MIDASH Solution will use the State of Michigan’s Single Sign-On implementation, MiLogin.  MiLogin is a web-based application that allows users to sign in once and have secure access to a variety of State of Michigan web applications without having to manage a different username and password for each web application.

Technically, MiLogin is a “Reverse Proxy” solution, which means that all requests between a client computer and the web application will be processed through MiLogin, adding an extra layer of security.  The solution will check every request for a token provided by MiLogin that exposes the username of the logged-in user.  That username will then be matched against the MIDASH Solution’s internal permissions database to determine the level of permissions the user has.

MiLogin supports MFA via a variety of methods, including text, phone call, email, or through the IBM Security Verify mobile application.  It also offers an Identity Proofing Federation service through Experian.

KL&A has substantial experience integrating Security Assertion Markup Language (SAML) with Microsoft Internet Information Services (IIS).  We have many State of Michigan applications in production that use SAML 2.0 for MiLogin integration with applications running on Microsoft IIS.

KL&A roles:

KL&A business analyst(s) to define access control requirements.

KL&A technical lead/security officer to lead the MiLogin integration effort and ensure that MiLogin is properly configured and maintained.

KL&A quality analyst(s) to test the MiLogin integration.

Please note that these roles may be fulfilled by a single resource.  For example, many of our analysts fulfill both the business analyst and the quality analyst roles.

State roles:

A DTMB technical resource to assist the KL&A team with defining requirements and providing information necessary to properly integrate with and configure MiLogin.

A DTMB and an MDHHS resource to perform user-acceptance testing on MiLogin integration and configuration.

DATA RETENTION AND REMOVAL

The State will need to retain all data for the entire length of the Contract unless otherwise direct by the State.

The State will need the ability to delete data, even data that may be stored off-line or in backups.

The State will need to retrieve data, even data that may be stored off-line or in backups.

Bidder must review and explain how the data retention, deletion and retrieval requirements will be met and describe its data management capabilities (storage limitations, duration, etc.).
BIDDER RESPONSE:

See KL&A’s response below in blue text.

### Bidder Response to Data Retention Policy

KL&A’s typical approach to the State’s data retention policy includes developing a centralized purge process/job, with configurable values for each entity/record type.  Additionally, in our case-management systems, when a case is purged, all data related to that case is also purged.

During the discovery and design phase, we will work with MDHHS and DTMB to determine if this approach is acceptable and, if necessary, customize the purge function design to meet DHSP’s business needs and policies.  We will ensure that each database table that requires a retention policy is configured properly and can be easily modified in the future.

For data stored in FileNet, we will use FileNet’s data retention capabilities.

Data in the system can only be deleted by authorized users, which will soft delete the data, meaning it will be removed from access through the user interface, but remain in the database until the data retention period is reached.  This provides the ability to restore data easily in case of accidental deletion.  However, if the State would prefer the data to be removed, we will ensure data is removed from the database when a user deletes the data.

KL&A will work with DTMB to assist with requests to delete or retrieve data stored offline or in backups.

KL&A roles:

KL&A business analyst and technical architect to conduct data retention and services analysis with MDHHS and DTMB and define the appropriate technical requirements.

KL&A technical architect to design the solution in compliance with MDHHS and DTMB data retention policy and defined requirements.

KL&A business analysts to test the solution and ensure State data is properly disposed of.

State roles:

MDHHS and DTMB to work with KL&A during data retention analysis activities.

MDHHS and DTMB to review and approve the KL&A data retention approach.

Identified resources to perform user-acceptance testing for the purge process to ensure that data is properly maintained or purged based on the policy and defined requirements.

END USER OPERATING ENVIRONMENT

The SOM IT environment includes X86 VMware, IBM Power VM, MS Azure/Hyper-V and Oracle VM, with supporting platforms, enterprise storage, monitoring, and management running in house and in cloud hosting provides.

Contractor must accommodate the latest browser versions (including mobile browsers) as well as some pre-existing browsers. To ensure that users with older browsers are still able to access online services, applications must, at a minimum, display and function correctly in standards-compliant browsers and the state standard browser without the use of special plugins or extensions. The rules used to base the minimum browser requirements include:

Over 2% of desktop and mobile & tablet site traffic, measured using Michigan.gov sessions statistics and

The current browser identified and approved as the State of Michigan standard

This information can be found at https://www.michigan.gov/browserstats. Please use the most recent calendar quarter to determine browser statistics.  For those desktop and mobile & tablet browsers with over 2% of site traffic, except Internet Explorer which requires support for at minimum version 11, the current browser version as well as the previous two major versions must be supported.

Contractor must support the current and future State standard environment at no additional cost to the State.

Bidder must describe the optimal technical environment based on the environment choices set forth above. 
BIDDER RESPONSE:

See KL&A’s response below, in blue text.  Under “Bidder Response to End-User Operating Environment,” there is one sub-topic that correlates to each prompt in this bidder box.

For our response to the optimal technical environment, please refer to “Optimal Technical Environment.”

Bidder must describe any State system access requirements that are necessary for the Bidder to perform its obligations on a timely basis, including but not limited to, physical or remote access to State networks, servers, or individual workstations.
BIDDER RESPONSE:

Refer to “State System-Access Requirements,” on page 43.

Bidder must describe if it can comply with the current environment and how it intends to comply with any future changes to the user environment.  And if not, describe what end user operating environment its Solution supports.
BIDDER RESPONSE:

Refer to “Current and Future State Environment Compliance,” on page 43.

Bidder must describe if it can support the original environment throughout the term of the contract.
BIDDER RESPONSE:

Refer to “Original Environment Support,” on page 43.

Bidder must describe how it communicates changes to its software and architecture.
BIDDER RESPONSE:

Refer to “Communication of Roadmap Changes,” on page 43.

Bidder must describe how customers collaborate with your organization in the decision-making process for upgrades, maintenance, and change control.

Refer to “Customer Collaboration,” on page 43.

Bidder must identify any plug-ins necessary for the proposed Solution to meet the system requirements of this request.

Refer to “Necessary Plug-Ins,” on page 44.

### Bidder Response to End-User Operating Environment

This section responds to each bidder prompt above.

#### Optimal Technical Environment

We are proposing a State-hosted solution that will leverage a GovCloud infrastructure (Azure or NGDI), which meets the demanding requirements of the US Federal Risk and Authorization Management Program (FedRAMP) and provides an environment with full redundancy and disaster recovery failover.

With regards to the end-user operating environment, users will access the solution through a web browser on an internet-connected device.  KL&A agrees to comply with the minimum browser support requirements set forth above, including support for:

Browsers used for over 2% of desktop, mobile, and tablet site traffic, measured using Sessions or Visitors, or

The current browser identified and approved as the State of Michigan standard.

Based on the information provided on www.michigan.gov/browserstats, KL&A will ensure that the MIDASH Solution will support the current and previous two versions of:

Chrome

Safari

Edge

Firefox

Samsung Internet

Android Webview

#### State System-Access Requirements

KL&A requires read-only access to both the database and application (via MiLogin) in Production to assist with bug triage.  KL&A requires read/write access for the database and application (via MiLogin) to all the lower environments (Dev, UAT, Pre-Prod, etc.) to assist the development process.  KL&A requires access to all reporting tools needed for MIDASH Solution (SSRS, PowerBI, Tableau, ArcView, etc.).

KL&A requires limited VPN access and tokens to any State-hosted integration endpoints needed to develop, test, and maintain the designed solution.

KL&A team members will also require physical access to applicable State buildings to attend/conduct any on-site meetings.  KL&A can also host meetings at our Okemos office.

#### Current and Future State Environment Compliance

KL&A will comply with the current and future environment throughout the life of the contract at no additional charge.  However, if there are future changes to the State of Michigan’s end-user operating environment, those changes will have to be regression tested against the MIDASH Solution to ensure uninterrupted application functionality.

#### Original Environment Support

KL&A will support the MIDASH Solution end-user operating environment throughout the term of the contract.

#### Communication of Roadmap Changes

Since we are proposing a custom solution, DHSP will have complete control over the project roadmap.  KL&A will work with DHSP’s executive leadership to plan the product roadmap collaboratively.  During the discovery phase, we will review business needs, objectives, and priorities, as well as technical dependencies and organizational change management requirements that should be considered in setting priorities.

#### Customer Collaboration

A core tenet of KL&A’s development methodology is customer collaboration.  Every step of the way, from requirements validation and elaboration, through joint application design sessions, sprint planning, sprint demonstrations, user-acceptance testing, and training, KL&A collaborates with our clients.  Further, we ask our clients to appoint a product owner who prioritizes the product backlog to ensure that KL&A is always working on the highest-priority items.

Additionally, we always encourage feature requests, which are tracked in our ticketing system, Jira.  Our team will review each request with MDHHS to determine if an impact analysis is warranted.  If so, the team will determine the effort, resources, time, and cost of the enhancement request.  In some cases, tradeoffs can be made to avoid additional costs.  If necessary, out-of-scope feature requests will be deferred to the agreed-upon change control process that is documented in the Project Management Plan deliverable.

For a detailed description of our:

Requirements validation process, refer to “Requirements Validation Methodology,” on page 119.

Scrum development methodology, refer to “Bidder Response to Agile Methodology,” on page 115.

User-acceptance testing process, refer to “Application Development,” on page 123.

Maintenance and support process, refer to “Bidder Response to Additional Products and Services,” on page 82.

#### Necessary Plug-Ins

No browser plug-in will be required for the MIDASH Solution.

SOFTWARE

Software requirements are identified in Schedule A – Table 1 Business Specification Worksheet.

Contractor must provide a list of any third-party components, and open source component included with or used in connection with the deliverables defined within this Contract.  This information must be provided to the State on a quarterly basis and/or if a new third-party or open source component is used in the performance of this Contract.

Look and Feel Standards 
All software items provided by the Contractor must adhere to the State of Michigan Application/Site standards which can be found at https://www.michigan.gov/standards.

Mobile Responsiveness
If the software will be used on a mobile device as define in Schedule A – Table 1 Business Specification Worksheet, the Software must utilize responsive design practices to ensure the application is accessible via a mobile device.

SOM IT Environment Access

Contractor must access State environments using one or more of the following methods:

State provided VDI (Virtual Desktop Infrastructure) where compliant.

State provided and managed workstation device.

Contractor owned and managed workstation maintained to all State policies and standards.

Contractor required interface with State systems which must be maintained in compliance with State policies and standards as set forth in Schedule E – Data Security Requirements.

From locations within the United States and jurisdiction territories.

Bidder must provide a detailed description of the Solution to be provided under the resulting Contract including, but not limited to, a detailed description of the proposed Software (name, type, version, release number, etc.), its functionality including the information architecture and functional design of the system, such as functionality maps, architectural maps, training materials, visual aids including screen shots, actions performed by the system, and any behind the scenes processing, optional add-on modules and plugins.  The level of detail provided will be such so that anyone is able to read it and understand how the software works.  Additionally, clearly define the Bidder’s services and the Solution’s ability to be rapidly configured or scaled as the State’s business or technical demands change.
BIDDER RESPONSE:

Under “Bidder Response to Software,” below this box, there is one sub-topic that responds to each prompt in the box.  For a detailed description of the solution, refer to “Detailed Description of the MIDASH Solution,” on page 46.

Bidder must identify any unique software requirements to fulfill the terms of the Contract.
BIDDER RESPONSE:

Refer to “Unique Software Requirements,” on page 46.

Bidder must describe any State system access requirements that are necessary for the Bidder to perform its obligations on a timely basis, including but not limited to, physical or remote access to State networks, servers, or individual workstations.
BIDDER RESPONSE:

Refer to “System Access Requirements,” on page 47.

Bidder must describe any custom software required to support internal SOM systems.
BIDDER RESPONSE:

Refer to “Custom Software Required to Support Internal SOM Systems,” on page 47.

Bidder must identify any third-party components, including open-source components included with or used in connection with the proposed Solution.
BIDDER RESPONSE:

Refer to “Third-Party and Open-Source Components,” on page 47.

Bidder must provide a list of all mobile devices that are compatible with the Solution.
BIDDER RESPONSE:

Refer to “Supported Mobile Devices,” on page 50.

Bidder must provide list of features that can be performed via a mobile device.
BIDDER RESPONSE:

Refer to “Features that Will Be Mobile Responsive,” on page 50.

Bidder must provide a detailed description of the Solution to be provided under the resulting Contract including, but not limited to, a detailed description of the proposed Software (name, type, version, release number, etc.), its functionality, optional add-on modules, Contractor’s services and the Solution ability to be rapidly configured or scaled as the State’s business or technical demands change.

Refer to “Detailed Description of the MIDASH Solution,” on page 46.

Refer to “Optional Add-On Modules,” on page 50.

Refer to “Contractor Services,” on page 51.

Refer to “Functional Scalability,” on page 51.

### Bidder Response to Software

KL&A is proposing a custom solution that will provide the DHSP with all the functionality it needs to be effective and efficient, hosted on the State’s infrastructure.  KL&A will, where possible, leverage existing code from other State modernization projects to save costs and time.  For example, KL&A can leverage features such as letter templating functionality for automated correspondence generation, work queue, and assignment functionality, lookup tables, audit history, functional entities, user role/permission management, and more.  The system will be designed collaboratively with business users.  MDHHS and DTMB staff will be involved in validating and elaborating requirements, designing the user interface, reviewing development incrementally, and performing acceptance testing, which reduces risk and ensures the solution will meet your needs exactly.

#### Detailed Description of the MIDASH Solution

To provide MDHHS with a clear vision of the proposed solution, KL&A has crafted a comprehensive narrative of the system’s functionality, along with some technical specifications that explain the architecture of the proposed solution.  Due to SIGMA file size limits, our detailed description of the MIDASH Solution is provided in a separate file.  Please refer to: 
11_MDHHS_MIDASH_SoftwareDescription_FromKLA.docx

Detailed responses to each requirement are provided in: 
21_MDHHS_MIDASH_ScheduleA-Table1-Specifications_FromKLA.docx

#### Unique Software Requirements

KL&A requires Hangfire for batch processing throughout the application.  Hangfire is part of our self-contained deployment and does not require specific software installed on the web server.

#### System Access Requirements

KL&A requires read-only access to both the database and application (via MiLogin) in Production to assist with bug triage.  KL&A requires read/write access for the database and application (via MiLogin) to all of the lower environments (Dev, UAT, Pre-Prod, etc.) to assist the development process.  KL&A requires access to all reporting tools needed for MIDASH Solution (SSRS, PowerBI, Tableau, ArcView, etc.).

KL&A requires limited VPN access and tokens to any State-hosted integration endpoints needed to develop, test, and maintain the designed solution.  Our team will use KL&A-provided and managed workstations that are maintained to all State policies and standards.

KL&A team members will also require physical access to applicable State buildings to attend/conduct any on-site meetings.  KL&A can also host meetings at our Okemos office.

#### Custom Software Required to Support Internal SOM Systems

KL&A may require a software scanning tool supported by the ECM team to scan documents and index them within FileNet (e.g., ScanDocuments, DataCapture) either directly or through the new MIDASH Solution.

#### Third-Party and Open-Source Components

This section describes the third-party and open-source components used to build the MIDASH Solution.  KL&A will review this list quarterly and make any necessary revisions.

Table 2. Third-Party Materials and Open-Source Components

| Package | License | Reason |
| --- | --- | --- |
| Angular | MIT | Enhanced HTML JavaScript Framework. |
| DotNetCore.NPOI | Apache V2 | Office document reading/writing. |
| EntityFramework | Apache V2 | Entity Framework is Microsoft's recommended data access technology for new applications. |
| FileNet | State provided | Content management system for storing unstructured data. |
| Hangfire | LGPL | Background worker framework that runs on the web server. |
| jQuery | MIT | JQuery is a fast and concise JavaScript Library that simplifies HTML document traversing, event handling, animating, and Ajax interactions for rapid web development. |
| .NET Core | Apache V2 | Web application framework, used for serving web application files and building a REST API. |
| Newtonsoft.Json | MIT | High-performance JSON library. |
| normalize.css | MIT | Normalize.css is a customizable CSS file that makes browsers render all elements more consistently and in line with modern standards. |
| Rxjs | Apache V2 | Observable library for JS. |
| Power BI | State provided | Analytics and reporting tools to generate and embed analytics dashboards, as well as to generate reports. |
| Select2.js | MIT | JQuery-based replacement for select boxes. It supports searching, remote data sets, and infinite scrolling of results. |
| Serilog | Apache V2 | .NET logging framework. |
| SignalR | Apache V2 | Web sockets library for real-time push notifications. |
| Sustainsys.Saml2.AspNetCore2 | MIT | SAML2P support for ASP.NET web sites. |

#### Look-and-Feel Standards

KL&A has developed and/or modernized numerous systems for the State of Michigan that are compliant with the State of Michigan’s look-and-feel standards, as well as with section 508 of the ADA.  We are familiar with the standards, as well as eMichigan’s compliance and validation processes.  KL&A has received eMichigan approval for numerous solutions that we’ve developed for the State.  We will continue to use the necessary templates and materials to demonstrate that the MIDASH Solution meets all applicable guidelines.

#### Mobile Responsiveness

KL&A has developed numerous applications for mobile use in a variety of technologies, including:

Native applications for iPhone and Android devices, such as:

Radiation Safety Mobile, a native iOS application developed for the State of Michigan Licensing and Regulatory Affairs (LARA) for inspectors to locate inspection sites on a map and have access to case documents.

Stryker Signature Profile Mobile, a native iOS application developed in Objective C.  This mobile application enables Stryker’s salespeople to demonstrate surgical drills with high-resolution, interactive graphics and videos and take orders with a shopping cart feature.

Responsive and/or progressive web applications, such as:

The Inspection, Notification, Tracking, Enforcement, and Licensing System (INTELS) developed for the Michigan Department of Agriculture and Rural Development (MDARD) to assist inspectors with capturing inspection information in the field.  This progressive web application even supports inspectors in offline mode.

The Here! responsive web application developed for the Ohio Department of Education to assist with improving attendance.  This engaging mobile app was built with Material, AngularJS, and Redux over a Firebase database.

The mobile component of the Railroad Information System (RRIS) developed for the Public Utility Commission of Ohio for capturing inspection information in the field.  This application was built in C# WPF with an SQLite database to run on Windows 10 mobile devices.

While KL&A is proficient with native app development toolsets, we’ve found that our clients prefer responsive or progressive web application technology for a variety of reasons.  These technologies are more cost-effective because they allow the use of a single web application on multiple devices (Android, iPhone, Windows) without having to manage and deploy separate mobile apps.  They are easier for end-users as users do not have to download, install, and update an app.  Finally, PWA apps better support offline operations with tighter operating system integration, should DHSP identify the need for offline operations in the future.

Based on the requirements in the RFP, KL&A plans to use a responsive design for the MIDASH Solution.  We will ensure all new functionality is responsive through the use of templates, coding standards, peer reviews, testing, and eMichigan approval processes.

##### Supported Mobile Devices

We will ensure that any functionality that we develop will operate on all modern, manufacturer-supported mobile devices and browsers, including, but not limited to:

Android;

iOS;

Windows;

Google Chrome;

Microsoft Edge; and

Apple Safari.

##### Features that Will Be Mobile Responsive

All system functionalities will be mobile responsive.  Our business analysts will create design mockups and work collaboratively with the DHSP business users and our development team to implement new front-end functionality in accordance with eMichigan’s look-and-feel standards.  For more detail about the joint application design process, refer to “Requirements Validation Methodology,” on page 119.

#### Optional Add-On Modules

Since we are proposing a custom solution based on the supplied requirements, there are no optional add-on modules.

#### Contractor Services

KL&A is also offering software development, project management, and implementation services that involve:

Validating the requirements included in this RFP and analyzing DHSP’s business processes and rules to ensure we have a clear and complete understanding of everything DHSP needs and desires of the new solution.  For a detailed description, refer to “Requirements Validation Methodology,” on page 119.

Assisting the State with standing up the hosting environments and completing the SSP process to gain the Authority to Operate (ATO).

Designing and developing ADA-compliant, mobile-responsive features.

Integrating the new MIDASH Solution with all the systems specified in the RFP.

Migrating data from CAREWare, eHARS, APHIRM, MiDAP, ScriptGuide Rx, MDSS (HIV and STI data only), HIV LMS, and Content Manager.

Producing all necessary SUITE documentation, user manuals, and training materials.

Providing comprehensive organizational change management (OCM) and training services to minimize resistance and prepare stakeholders for a smooth, seamless transition.

For the training and OCM services, KL&A has partnered with Springboard Consulting, a Prosci© certified company that specializes in OCM and training.  Springboard has completed numerous, successful high-profile, State of Michigan implementation projects for which it has provided these services.

Finally, KL&A is offering maintenance and support services.  We have a mature and robust maintenance and support division that takes over a system after go-live.  This team will maintain the system, provide technical support to DHSP users, repair reported defects, and design, develop, test, and implement any approved, post-production enhancements.  For more information about our maintenance and support process, refer to “Maintenance and Support,” on page 127.

#### Functional Scalability

In terms of rapidly implementing configuration changes or customizations, the KL&A implementation team will be fully dedicated to DHSP.  It will follow our Agile/Scrum methodology, where all required configuration tasks and customization user epic and user stories will be loaded into a product backlog, prioritized by DHSP, acted upon as quickly as possible, and implemented iteratively, allowing completed configuration tasks and customizations to be reviewed and user-acceptance tested by DHSP personnel.  With bi-weekly reviews of priorities, KL&A can provide DHSP with agility to pivot priorities if business needs change.  We also have a large staff of highly qualified personnel, which allows us to scale the implementation team size if tighter timelines are required.  For a detailed description of our Agile/Scrum methodology, please refer to “Bidder Response to Agile Methodology,” on page 115.

Even after the solution goes live and responsibility transitions to our maintenance and support team, there will still be resources dedicated to DHSP, ensuring that configuration changes or customizations will be promptly addressed.

Rest assured that KL&A will be a responsive vendor and follow our transparent, iterative approach to ensure DHSP’s needs are met promptly, and the resulting configurations and customizations are tested thoroughly for proper functioning.  Our goal is to deliver a solution that provides real value for DHSP and its customers at a competitive price.

#### Roles and Responsibilities

This section clarifies the roles and responsibilities related to ensuring that the MIDASH Solution is compliant with all State of Michigan look-and-feel standards, mobile responsiveness requirements, and ADA WCAG 2.0 requirements.

KL&A roles:

KL&A business analysts to gather business and functional requirements, including user interface and responsive-design requirements, and acceptance criteria.

KL&A development lead to ensure KL&A’s standards and templates comply with the State’s responsive-design standards and to ensure the development team is adhering to KL&A’s standards and using the prescribed templates.

KL&A developers to ensure all new user interfaces are developed in compliance with KL&A’s and the State’s standards and to work with eMichigan through the SOM Web Application Review process.

KL&A quality analysts to test the web application against the requirements and acceptance criteria and, if applicable, create and maintain automated test cases.

Please note that these roles may be fulfilled by a single resource.  For example, many of our analysts fulfill both the business analyst and the quality analyst roles.

State roles:

MDHHS subject matter experts to provide input regarding business and functional requirements, approve screen mockups and navigation, and perform user-acceptance testing of newly developed functionality.

eMichigan team to review and approve KL&A’s web application designs.

INTEGRATION

MDHHS envisions a phased approach for migrating away from the existing systems to the proposed solution. This approach would necessitate the creation of new functionality that works with existing data sources and functionality until all existing functionalities can be retired.

MDHHS anticipates that there are three types of integrations:

Integrations which will no longer be necessary due to the merging of the existing systems

Integrations which will be required to implement the new system

Integrations which will be developed to support the user functionality needed by the MiDASH system.

Integrations which will no longer be necessary dues to the merging of existing systems:

The following systems will be merged. New functionality will be required to interact with legacy functionality until all functionality is replaced by MiDASH.

CAREWare

eHARS

APHIRM

MiDAP

MDSS

HIV LMS

Anticipated Integrations which will be required to implement the new system:

MiLogin – Michigan will provide SSO services through standard web-service calls.

Rhapsody Service Bus - Enterprise service bus to handle HL7 requests

Health Enterprise Service Bus - Enterprise service bus for internal Michigan web service calls

Master Person Index – State of Michigan based identity management solution

State of Michigan shared services possibly including but not limited to FileNet, virus checkers, electronic signatures, text messaging and central print services.

MDHHS Database Security Application DSA

MDHHS receives or generates reports that are used to exchange data between systems. At a minimum the following functionality needs to be evaluated for recreation. Final determination of integrations will be those determined needed to achieve Minimum Viable Product (MVP).

STARLIMS web-based Laboratory Information Management System, by Abbott, that manages the primary laboratory activities of sample logging, tracking, resulting, and reporting of clinical specimens received from submitters throughout the State of Michigan for the diagnosis of disease, such as rabies and HIV.

Michigan Dental Program CSV File Inbound

Data to Care CSV File Inbound

HIV Lab Management System (LMS) - SAS Weekly Lab Import Inbound

Individual Information TLO - Public and Proprietary Information on Individuals in US SAS Annual Import of Personal Information Inbound

Routine Interstate Duplicate Review (RIDR)/Cumulative Interstate Duplicate Review (CIDR) - SAS Out of State Information Inbound

Medicaid - SAS Bi-Annual Treatment Address, Ph No, Medicaid Enrollee ID Inbound

Vital Statistics, NDI, SSDN, EDRS - SAS Death Data Inbound from 4 sources

CDC – STI Case Reporting MDSS to HL7 file, using MDSS export functions

File Transfer to Rhapsody (Detroit Medical Center) Inbound lab .csv file pushed to Rhapsody

ScriptGuide Rx Outbound File Transfer

HRSA Non-Utilizer Report SGRX Outbound file to MDHHS

HRSA Medicaid Match SGRX Outbound file to MDHHS

Inbound disenrollment file from MDHHS

ADAP Quarterly Report SGRX Outbound file - Active member breakdown by: demographics, Regimen Report, Drug Utilization, FPL Breakout, and Medicare Breakout, Detroit EMA (same breakdown)

MiDAP Drug Report SGRX Outbound file to MDHHS - Top drug label names by amount paid

MiDAP Top Pharmacies SGRX Outbound file to MDHHS - Top pharmacy chains

Duplicate Alternate Member IDs SGRX Outbound file to MDHHS

CDC Load - Structured Data

Bidder must describe the strategy it proposes to implement new functionality while integrating with existing data sources and functionality.
BIDDER RESPONSE:

Refer to our response below in blue text.

### Bidder’s Response to Integration

KL&A understands that the State wishes to take a phased approach, decommissioning legacy systems as the functionality they provide becomes available in the new MIDASH Solution while continuing to interface with internal legacy HIV applications or soon-to-be deprecated third-party/external systems until the entire new solution is fully implemented.  During Sprint Zero, the KL&A team will work with key stakeholders to define the order in which legacy system functionality and associated integrations will be implemented in the new solution.  Our team will conduct discovery sessions, perform gap analyses, review dependencies, and consider the criticality of each system and integration to make recommendations that will result in a smooth and efficient implementation.

Batch file formats, including fixed-width, CSV, SAS, SGRX, or others will be transmitted via the State of Michigan’s File Transfer Services (FTS), using SFTP and/or secure file transfer channels that are dictated by the integrating party, such as CDC or Rhapsody.

Web service integrations will be handled over HTTPS communications secured by TLS versions dictated by DTMB networking and security teams.  The format of web services that the MIDASH Solution consumes may be in SOAP (including HL7 messaging), REST, or similar fashions based on the integration, assuming it adheres to the transport protocol and security requirements.  The format of the web services that the MIDASH Solution produces will be in REST unless otherwise required by the consuming integrating party.

Additional integrations that may be handled via unique or proprietary means, such as direct database, enterprise data warehouse, ECM, reporting services, or miscellaneous enterprise services will be implemented based on the requisite transport, security, and format specifications dictated by the integration.

Below, we elaborate further upon each type of integration that DHSP has categorized.

Integrations that will no longer be necessary due to the merging of the existing systems

KL&A will work with the applicable stakeholders to identify a preferred order in which the individual systems should be merged into the MIDASH Solution.  This identification will be made with the consideration and support of MDHHS, DTMB, and any external or internal integrating partners to ensure a smooth transition for each subsystem into the new solution and that the order and timeline are appropriate for all parties involved.

KL&A will consider any integrations made between these merging systems while identifying which systems will be initially merged and which ones will remain online for each phase to ensure that these integrations are routed to/from the new solution instead of their soon-to-be deprecated counterparts.  Similarly, for any integrations with systems outside of the systems involved in the merge into the MIDASH Solution, each phase will also consider and, if necessary, route to/from the new solution instead of their deprecated counterparts.

If multiple systems are identified to be merged in the same phase, all integrations that remain relevant in the new solution will be reimplemented in the MIDASH Solution during the same phase in which the identified systems are merging.

For example, if ScriptGuide Rx integrates with one of the merging systems in a given phase and another of the systems to be merged in a future phase, that integration with the first merging system will have a coordinated update to reroute integration to or from the new MIDASH Solution during the same phase in which the first merging system is being implemented.  However, if both/all systems involved in ScriptGuide Rx integrations are merging into the new solution in the same phase, the integration(s) with ScriptGuide Rx will be included during that phase if still applicable—that is, some integrations between systems may become obsolete by the systems being implemented into a unified solution.

Integrations that will be required to implement the new system

In addition to facilitating any pre-existing integrations that may carry over, KL&A’s MIDASH Solution will warrant several new integrations that may not be present in the deprecated systems or will require enough rework to be considered a new integration in the new solution.  These integrations will be identified and developed alongside core system user stories as part of each phase of the project based on the requisite need of the system and business cases.  Integrations that are required for the new solution to function on a base level, such as MiLogin, DSA, and shared SOM enterprise services will be developed in the earliest phases to ensure the base solution can properly and securely function while meeting the needs of MDHHS and DTMB specifications.

Additional new integrations tied to specific applications that may be merging into the solution in a future phase will be handled during that phase of development.  For instance, if Rhapsody integrations are only necessary for systems that will be migrated in a later phase, then the new Rhapsody integrations will be developed during the implementation of those systems.

As with current integrations, any new integrations will still be identified and reviewed during the initial discovery and requirements gathering phases to ensure each phase of the solution’s roadmap includes all necessary integrations.

Integrations that will be developed to support the user functionality needed by the MIDASH Solution

As mentioned with previous integration type categories, any new or reimplemented integration in KL&A’s MIDASH Solution will be identified and considered during the initial definition of the minimum viable product (MVP) and will be scoped into each phase of the implementation as necessary per business user need.  Specifics of how each integration will be developed and implemented will be determined based on support integration formats, security constraints, integrating partner/system requirements, and business use cases.

MIGRATION

Contractor must migrate the data identified in the tables below. The database may be increased at the time of transition, if required by the State.

Contractor will need to migrate data from the following systems:

CAREWare

eHARS

APHIRM

MiDAP

MDSS (HIV and STI data only)

HIV LMS

The Contractor will need to integrate with MiLogin for user Identity, Credential and Access management. User accounts from existing systems will not be migrated.

Historical reports generated in the existing legacy systems will not be migrated.

Work in process in the existing legacy systems will need to be migrated to the corresponding task and workflow in the replacement systems as necessary so that cases continue to be appropriately processed.

The Contractor will be responsible for partnering with MDHHS in performing data analysis and data cleansing in order to successfully migrate legacy data to this new system.

The Contractor will be responsible for migrating legacy system data to the new proposed solution in a way that satisfies the Contractor’s proposed go-live strategy.

In addition to the six systems listed above, KL&A notes that this section indicates two additional systems from which data is to be migrated, including ScriptGuide Rx and Content Manager.

Contractor must migrate the data identified in the table below:

| CAREWare |
| --- |
| Current Technology | SQL |
| Data Format relative to the database technology used. | Standard tabular rows and columns of data elements. Consists of quantitative and qualitative data |
| Number of data fields to give Contractor awareness of the size of the schema. | 100+ |
| Volume of Data | 400GB Production 400GB QA/Test 2.4TB NAS |
| Database current size. | 400GB |
| Bidders must explain in detail how and what services are required to migrate the data from the current technology. BIDDER RESPONSE: KL&A will require access to a SQL Server backup file on a weekly to monthly basis and an up-to-date data dictionary with field and table descriptions. Subject matter experts must be available to participate in discovery and migration/conversion planning activities. Business users must be available to assist in user acceptance of validated data as part of a conversion iteration cycle (typically every two weeks). |  |
| Bidder must explain how it will be able to support the current and future growth of the Solution’s data. BIDDER RESPONSE: KL&A recommends the use of managed, high-availability, Azure SQL Server databases that are replicated in real-time to an independent Azure zone, which accomplishes two things: Provides disaster recovery in that data can be recovered from either zone if a disaster takes out a zone, and Real-time reporting without an impact on performance. Reporting and analytics using Power BI and other tools can be used without affecting the application performance of the production transactional database. With this approach, DTMB and KL&A can actively monitor performance and automate tuning with the Azure monitoring tool. |  |
| Bidder must also explain how the proposed Solution’s environment can scale up or down without affecting performance. Bidder must provide the cost for such migration in their cost proposal. BIDDER RESPONSE: KL&A recommends the use of a managed high-availability Azure SQL server database, configured in an elastic pool configuration, which allows for on-demand scaling for systems that have varying and unpredictable usage demands. The database can be scaled up and down at the vCore or DTU level with minimal downtime. |  |
| Contractor must review and explain how the solution will migrate data to their solution. BIDDER RESPONSE: The solution will import data into newly designed data models. KL&A will support data correction and data cleansing in collaboration with MDHHS, as described in the Data Migration/Conversion Plan that will be produced during Sprint 0 (a.k.a. Discovery). KL&A technical resources will work with MDHHS and DTMB to gain access to the eight sources targeted for migration as identified in the RFP. They will review the data and potentially hold technical joint application design sessions with identified subject matter experts to gather the details necessary for creating a Data Migration/Conversion Plan. The plan will describe the field mappings, conversion rules, and data definitions. Then the KL&A development team will build the conversion programs. To ensure quality, the team will load and transform staging data and examine the result. If necessary, the conversion programs will be refined and the whole process repeated until the results are transformed to an acceptable margin of error. Finally, identified MDHHS subject matter experts will review transformed data to provide user acceptance and approval. Then the data will be loaded into production. |  |

| Enhanced HIV /AIDS Reporting System (eHARS) |
| --- |
| Current Technology | MSSQL Server 2017 |
| Data Format relative to the database technology used. | Standard tabular rows and columns of data elements. Consists of quantitative and qualitative data |
| Number of data fields to give Contractor awareness of the size of the schema. | 115 Tables, 7 Views, 167 Procedures |
| Volume of Data | There are approximately 3.25 & 5 terabytes attached to the test and prod DB servers respectively, but these are shared environments. There are 120 gigabytes attached to both the test & prod app/web servers, 240 total. |
| Database current size. | 20 gigabytes |
| Bidders must explain in detail how and what services are required to migrate the data from the current technology. KL&A will require access to a SQL Server backup file on a weekly to monthly basis and an up-to-date data dictionary with field and table descriptions. Subject matter experts must be available to participate in discovery and migration/conversion planning activities. Business users must be available to assist in user acceptance of validated data as part of a conversion iteration cycle (typically every two weeks). |  |
| Bidder must explain how it will be able to support the current and future growth of the Solution’s data. KL&A recommends the use of managed, high-availability, Azure SQL Server databases that are replicated in real-time to an independent Azure zone, which accomplishes two things: Provides disaster recovery in that data can be recovered from either zone if a disaster takes out a zone, and Real-time reporting without an impact on performance. Reporting and analytics using Power BI and other tools can be used without affecting the application performance of the production transactional database. With this approach, DTMB and KL&A can actively monitor performance and automate tuning with the Azure monitoring tool. |  |
| Bidder must also explain how the proposed Solution’s environment can scale up or down without affecting performance. Bidder must provide the cost for such migration in their cost proposal. KL&A recommends the use of a managed high-availability Azure SQL server database, configured in an elastic pool configuration, which allows for on-demand scaling for systems that have varying and unpredictable usage demands. The database can be scaled up and down at the vCore or DTU level with minimal downtime. |  |
| Contractor must review and explain how the solution will migrate data to their solution. The solution will import data into newly designed data models. KL&A will support data correction and data cleansing in collaboration with MDHHS, as described in the Data Migration/Conversion Plan that will be produced during Sprint 0 (a.k.a. Discovery). KL&A technical resources will work with MDHHS and DTMB to gain access to the eight sources targeted for migration as identified in the RFP. They will review the data and potentially hold technical joint application design sessions with identified subject matter experts to gather the details necessary for creating a Data Migration/Conversion Plan. The plan will describe the field mappings, conversion rules, and data definitions. Then the KL&A development team will build the conversion programs. To ensure quality, the team will load and transform staging data and examine the result. If necessary, the conversion programs will be refined and the whole process repeated until the results are transformed to an acceptable margin of error. Finally, identified MDHHS subject matter experts will review transformed data to provide user acceptance and approval. Then the data will be loaded into production. |  |

| Advanced Public Health Information and Relational Mapping (Aphirm) |
| --- |
| Current Technology | SQL |
| Data Format relative to the database technology used. | unavailable |
| Number of data fields to give Contractor awareness of the size of the schema. | unavailable |
| Volume of Data | unavailable |
| Database current size. | unavailable |
| Bidders must explain in detail how and what services are required to migrate the data from the current technology. KL&A will require access to a SQL Server backup file on a weekly to monthly basis and an up-to-date data dictionary with field and table descriptions. Subject matter experts must be available to participate in discovery and migration/conversion planning activities. Business users must be available to assist in user acceptance of validated data as part of a conversion iteration cycle (typically every two weeks). |  |
| Bidder must explain how it will be able to support the current and future growth of the Solution’s data. KL&A recommends the use of managed, high-availability, Azure SQL Server databases that are replicated in real-time to an independent Azure zone, which accomplishes two things: Provides disaster recovery in that data can be recovered from either zone if a disaster takes out a zone, and Real-time reporting without an impact on performance. Reporting and analytics using Power BI and other tools can be used without affecting the application performance of the production transactional database. With this approach, DTMB and KL&A can actively monitor performance and automate tuning with the Azure monitoring tool. |  |
| Bidder must also explain how the proposed Solution’s environment can scale up or down without affecting performance. Bidder must provide the cost for such migration in their cost proposal. KL&A recommends the use of a managed high-availability Azure SQL server database, configured in an elastic pool configuration, which allows for on-demand scaling for systems that have varying and unpredictable usage demands. The database can be scaled up and down at the vCore or DTU level with minimal downtime. |  |
| Contractor must review and explain how the solution will migrate data to their solution. The solution will import data into newly designed data models. KL&A will support data correction and data cleansing in collaboration with MDHHS, as described in the Data Migration/Conversion Plan that will be produced during Sprint 0 (a.k.a. Discovery). KL&A technical resources will work with MDHHS and DTMB to gain access to the eight sources targeted for migration as identified in the RFP. They will review the data and potentially hold technical joint application design sessions with identified subject matter experts to gather the details necessary for creating a Data Migration/Conversion Plan. The plan will describe the field mappings, conversion rules, and data definitions. Then the KL&A development team will build the conversion programs. To ensure quality, the team will load and transform staging data and examine the result. If necessary, the conversion programs will be refined and the whole process repeated until the results are transformed to an acceptable margin of error. Finally, identified MDHHS subject matter experts will review transformed data to provide user acceptance and approval. Then the data will be loaded into production. |  |

| Michigan Drug Assistance Program (MiDAP) |
| --- |
| Current Technology | Microsoft SQL Server 2012 (SP4-GDR) (KB4057116) - 11.0.7462.6 (X64) Jan 5 2018 22:11:56 Copyright (c) Microsoft Corporation Enterprise Edition (64-bit) on Windows NT 6.3 <X64> (Build 9600) (Hypervisor) |  |
| Data Format relative to the database technology used. | Standard tabular rows and columns of data elements. Consists of quantitative and qualitative data |  |
| Number of data fields to give Contractor awareness of the size of the schema. | 72 tables 35 views 24 stored procedures |  |
| Volume of Data | 300 GB |  |
| Database current size. | 240 GB |  |
| Bidders must explain in detail how and what services are required to migrate the data from the current technology. KL&A will require access to a SQL Server backup file on a weekly to monthly basis and an up-to-date data dictionary with field and table descriptions. Subject matter experts must be available to participate in discovery and migration/conversion planning activities. Business users must be available to assist in user acceptance of validated data as part of a conversion iteration cycle (typically every two weeks). |  |
| Bidder must explain how it will be able to support the current and future growth of the Solution’s data. KL&A recommends the use of managed, high-availability, Azure SQL Server databases that are replicated in real-time to an independent Azure zone, which accomplishes two things: Provides disaster recovery in that data can be recovered from either zone if a disaster takes out a zone, and Real-time reporting without an impact on performance. Reporting and analytics using Power BI and other tools can be used without affecting the application performance of the production transactional database. With this approach, DTMB and KL&A can actively monitor performance and automate tuning with the Azure monitoring tool. |  |
| Bidder must also explain how the proposed Solution’s environment can scale up or down without affecting performance. Bidder must provide the cost for such migration in their cost proposal. KL&A recommends the use of a managed high-availability Azure SQL server database, configured in an elastic pool configuration, which allows for on-demand scaling for systems that have varying and unpredictable usage demands. The database can be scaled up and down at the vCore or DTU level with minimal downtime. |  |
| Contractor must review and explain how the solution will migrate data to their solution. The solution will import data into newly designed data models. KL&A will support data correction and data cleansing in collaboration with MDHHS, as described in the Data Migration/Conversion Plan that will be produced during Sprint 0 (a.k.a. Discovery). KL&A technical resources will work with MDHHS and DTMB to gain access to the eight sources targeted for migration as identified in the RFP. They will review the data and potentially hold technical joint application design sessions with identified subject matter experts to gather the details necessary for creating a Data Migration/Conversion Plan. The plan will describe the field mappings, conversion rules, and data definitions. Then the KL&A development team will build the conversion programs. To ensure quality, the team will load and transform staging data and examine the result. If necessary, the conversion programs will be refined and the whole process repeated until the results are transformed to an acceptable margin of error. Finally, identified MDHHS subject matter experts will review transformed data to provide user acceptance and approval. Then the data will be loaded into production. |  |

| ScriptGuide RX |
| --- |
| Current Technology | SQL |  |
| Data Format relative to the database technology used. | Standard tabular rows and columns of data elements. Consists of quantitative and qualitative data |  |
| Number of data fields to give Contractor awareness of the size of the schema. | Largest number of columns is 26 in one table. Others are much less. 11 Tables at this time. |  |
| Volume of Data | 48 MB |  |
| Database current size. | Not Available |  |
| Bidders must explain in detail how and what services are required to migrate the data from the current technology. KL&A will require access to a SQL Server backup file on a weekly to monthly basis and an up-to-date data dictionary with field and table descriptions. Subject matter experts must be available to participate in discovery and migration/conversion planning activities. Business users must be available to assist in user acceptance of validated data as part of a conversion iteration cycle (typically every two weeks). |  |
| Bidder must explain how it will be able to support the current and future growth of the Solution’s data. KL&A recommends the use of managed, high-availability, Azure SQL Server databases that are replicated in real-time to an independent Azure zone, which accomplishes two things: Provides disaster recovery in that data can be recovered from either zone if a disaster takes out a zone, and Real-time reporting without an impact on performance. Reporting and analytics using Power BI and other tools can be used without affecting the application performance of the production transactional database. With this approach, DTMB and KL&A can actively monitor performance and automate tuning with the Azure monitoring tool. |  |
| Bidder must also explain how the proposed Solution’s environment can scale up or down without affecting performance. Bidder must provide the cost for such migration in their cost proposal. KL&A recommends the use of a managed high-availability Azure SQL server database, configured in an elastic pool configuration, which allows for on-demand scaling for systems that have varying and unpredictable usage demands. The database can be scaled up and down at the vCore or DTU level with minimal downtime. |  |
| Contractor must review and explain how the solution will migrate data to their solution. The solution will import data into newly designed data models. KL&A will support data correction and data cleansing in collaboration with MDHHS, as described in the Data Migration/Conversion Plan that will be produced during Sprint 0 (a.k.a. Discovery). KL&A technical resources will work with MDHHS and DTMB to gain access to the eight sources targeted for migration as identified in the RFP. They will review the data and potentially hold technical joint application design sessions with identified subject matter experts to gather the details necessary for creating a Data Migration/Conversion Plan. The plan will describe the field mappings, conversion rules, and data definitions. Then the KL&A development team will build the conversion programs. To ensure quality, the team will load and transform staging data and examine the result. If necessary, the conversion programs will be refined and the whole process repeated until the results are transformed to an acceptable margin of error. Finally, identified MDHHS subject matter experts will review transformed data to provide user acceptance and approval. Then the data will be loaded into production. |  |

| Michigan Disease Surveillance Systems (MDSS) |
| --- |
| Current Technology | Oracle |  |
| Data Format relative to the database technology used. | Standard tabular rows and columns of data elements. Consists of quantitative and qualitative data |  |
| Number of data fields to give Contractor awareness of the size of the schema. | 200 case variables. 25 lab variables. 100 Field record variables. |  |
| Volume of Data | Prod App/Web Server 300 gigabytes Prod DB Control Domain - ~ 5.5 terabytes, shared with MCIR |  |
| Database current size. | 1 terabyte |  |
| Bidders must explain in detail how and what services are required to migrate the data from the current technology. KL&A will require access to an Oracle backup file on a weekly to monthly basis and an up-to-date data dictionary with field and table descriptions. Subject matter experts must be available to participate in discovery and migration/conversion planning activities. Business users must be available to assist in user acceptance of validated data as part of a conversion iteration cycle (typically every two weeks). |  |
| Bidder must explain how it will be able to support the current and future growth of the Solution’s data. KL&A recommends the use of managed, high-availability, Azure SQL Server databases that are replicated in real-time to an independent Azure zone, which accomplishes two things: Provides disaster recovery in that data can be recovered from either zone if a disaster takes out a zone, and Real-time reporting without an impact on performance. Reporting and analytics using Power BI and other tools can be used without affecting the application performance of the production transactional database. With this approach, DTMB and KL&A can actively monitor performance and automate tuning with the Azure monitoring tool. |  |
| Bidder must also explain how the proposed Solution’s environment can scale up or down without affecting performance. Bidder must provide the cost for such migration in their cost proposal. KL&A recommends the use of a managed high-availability Azure SQL server database, configured in an elastic pool configuration, which allows for on-demand scaling for systems that have varying and unpredictable usage demands. The database can be scaled up and down at the vCore or DTU level with minimal downtime. |  |
| Contractor must review and explain how the solution will migrate data to their solution. The solution will import data into newly designed data models. KL&A will support data correction and data cleansing in collaboration with MDHHS, as described in the Data Migration/Conversion Plan that will be produced during Sprint 0 (a.k.a. Discovery). KL&A technical resources will work with MDHHS and DTMB to gain access to the eight sources targeted for migration as identified in the RFP. They will review the data and potentially hold technical joint application design sessions with identified subject matter experts to gather the details necessary for creating a Data Migration/Conversion Plan. The plan will describe the field mappings, conversion rules, and data definitions. Then the KL&A development team will build the conversion programs. To ensure quality, the team will load and transform staging data and examine the result. If necessary, the conversion programs will be refined and the whole process repeated until the results are transformed to an acceptable margin of error. Finally, identified MDHHS subject matter experts will review transformed data to provide user acceptance and approval. Then the data will be loaded into production. |  |

| Human Immunodeficiency Virus Laboratory Management System (HIVLMS) |
| --- |
| Current Technology | SQL Server |  |
| Data Format relative to the database technology used. | Standard tabular rows and columns of data elements. Consists of quantitative and qualitative data |  |
| Number of data fields to give Contractor awareness of the size of the schema. | 100 Tables, 13 Views, 141 Procedures |  |
| Volume of Data | There are approximately 3.25 & 5 terabytes attached to the test and prod DB servers respectively, but these are shared environments. There are 120 gigabytes attached to both the test & prod app/web servers, 240 total. |  |
| Database current size. | 12 gigabytes |  |
| Bidders must explain in detail how and what services are required to migrate the data from the current technology. KL&A will require access to a SQL Server backup file on a weekly to monthly basis and an up-to-date data dictionary with field and table descriptions. Subject matter experts must be available to participate in discovery and migration/conversion planning activities. Business users must be available to assist in user acceptance of validated data as part of a conversion iteration cycle (typically every two weeks). |  |
| Bidder must explain how it will be able to support the current and future growth of the Solution’s data. KL&A recommends the use of managed, high-availability, Azure SQL Server databases that are replicated in real-time to an independent Azure zone, which accomplishes two things: Provides disaster recovery in that data can be recovered from either zone if a disaster takes out a zone, and Real-time reporting without an impact on performance. Reporting and analytics using Power BI and other tools can be used without affecting the application performance of the production transactional database. With this approach, DTMB and KL&A can actively monitor performance and automate tuning with the Azure monitoring tool. |  |
| Bidder must also explain how the proposed Solution’s environment can scale up or down without affecting performance. Bidder must provide the cost for such migration in their cost proposal. KL&A recommends the use of a managed high-availability Azure SQL server database, configured in an elastic pool configuration, which allows for on-demand scaling for systems that have varying and unpredictable usage demands. The database can be scaled up and down at the vCore or DTU level with minimal downtime. |  |
| Contractor must review and explain how the solution will migrate data to their solution. The solution will import data into newly designed data models. KL&A will support data correction and data cleansing in collaboration with MDHHS, as described in the Data Migration/Conversion Plan that will be produced during Sprint 0 (a.k.a. Discovery). KL&A technical resources will work with MDHHS and DTMB to gain access to the eight sources targeted for migration as identified in the RFP. They will review the data and potentially hold technical joint application design sessions with identified subject matter experts to gather the details necessary for creating a Data Migration/Conversion Plan. The plan will describe the field mappings, conversion rules, and data definitions. Then the KL&A development team will build the conversion programs. To ensure quality, the team will load and transform staging data and examine the result. If necessary, the conversion programs will be refined and the whole process repeated until the results are transformed to an acceptable margin of error. Finally, identified MDHHS subject matter experts will review transformed data to provide user acceptance and approval. Then the data will be loaded into production. |  |

| Content Manager |
| --- |
| Current Technology | HP Enterprise Content Manager |
| Data Format relative to the database technology used. | Currently individual .pdf files. |
| Number of data fields to give Contractor awareness of the size of the schema. | Individual .pdf files |
| Volume of Data | Over 36,000 individual .pdf files. |
| Database current size | 36,000 .pdf files with 109,000 additional images included in these 36,000 .pdf files. |
| Bidders must explain in detail how and what services are required to migrate the data from the current technology. KL&A will require access to a HP ECM backup file on a weekly to monthly basis and an up-to-date data dictionary with field and table descriptions. Subject matter experts must be available to participate in discovery and migration/conversion planning activities. Business users must be available to assist in user acceptance of validated data as part of a conversion iteration cycle (typically every two weeks). |  |
| Bidder must explain how it will be able to support the current and future growth of the Solution’s data. KL&A recommends the use of the Center for Shared Solutions (CSS) Enterprise Content Management (ECM) solution, IBM FileNet. Using FileNet will ensure that documents containing personal health information (PHI) and personally identifiable information (PII) will be stored within the State of Michigan’s infrastructure, compliant with the State’s software security plans, and meet all the criteria for compliance with the MIDASH Solution sensitive material requirements. With this approach, DTMB and KL&A will both be involved in monitoring performance and be able to make suggestions where appropriate when housing a large volume of documents. |  |
| Bidder must also explain how the proposed Solution’s environment can scale up or down without affecting performance. Bidder must provide the cost for such migration in their cost proposal. KL&A recommends the usage of the State’s maintained ECM solution due to having dedicated teams monitoring the solution. The ECM team would be responsible for scaling the infrastructure as necessary to prevent disruptions as they would affect multiple agencies across the State infrastructure. |  |
| Contractor must review and explain how the solution will migrate data to their solution. KL&A will import data into newly designed data models and will support data correction and data cleansing in collaboration with MDHHS, as described in the Data Migration/Conversion Plan that will be produced during Sprint 0 (a.k.a. Discovery). KL&A technical resources will work with MDHHS and DTMB to gain access to the eight sources targeted for migration as identified in the RFP. They will review the data and potentially hold technical joint application design sessions with identified subject matter experts to gather the details necessary for creating a Data Migration/Conversion Plan. The plan will describe the field mappings, conversion rules, and data definitions. Then the KL&A development team will build the conversion programs. To ensure quality, the team will load and transform staging data and examine the result. If necessary, the conversion programs will be refined and the whole process repeated until the results are transformed to an acceptable margin of error. Finally, identified MDHHS subject matter experts will review transformed data to provide user acceptance and approval. Then the data will be loaded into production. |  |

TRAINING SERVICES

A successful training program ensures that individuals have received and retained the information needed to perform their jobs with the change.  It also ensures that individuals have achieved a level of proficiency at performing their jobs with the change enabling them to quickly ramp back up to normal business operations performance.

There are approximately 250 State of Michigan users, 800-1000 external users and 5000 or more clients who will require training on the new system and processes.

The Contractor must provide role-based, administrator and end-user training for implementation, go-live support, and transition to customer self‐sufficiency as detailed below.  We will not consider a Train-the Trainer model.  The Contractor must provide all training.

| Internal and External Users | Contractor will need to provide role-based live virtual training. Training using a combination of learning modalities and tools, including live virtual, prerecorded and written. |
| --- | --- |
| Clients | Contractor will need to provide user guides, infographics, prerecorded video tutorials. Contractor will not provide live virtual training to clients. |
| Other Training: Online | Contractor will need to provide on-line help, technical support, user guides and prerecorded training modules as needed. |
| Training Materials | User Guides, Infographics, prerecorded training modules |

The Bidder must provide available training options and include details such as: typical class size, materials to be provided, class duration. The Bidder must provide a training plan for go-live support and transition to self-support, including options and details such as the number of dedicated personnel, staff location, hours available and duration of go-live support. BIDDER RESPONSE: See KL&A’s response below in blue text. Under “Bidder Response to Training Services,” below, there is one sub-topic that correlates to each bidder box in this section.

Bidder must provide details on, and examples of, clearly written instructions and documentation to enable State administrators and end-users to successfully operate the Solution without needing to bring in additional Bidder support. See KL&A’s response below in blue text.

Bidder must provide a response to the specific training requirements identified above. See KL&A’s response below in blue text.

### Bidder Response to Training Services

KL&A understands that a successful implementation requires training users and ensuring they have access to resources for reference after training is completed.  Training will be a key component of the organizational change management (OCM) strategy and plan.  We will subcontract Springboard Consulting to lead and provide training for role-based, live, virtual training and client-focused, pre-recorded training, using learning tools and techniques that provide a combination of learning modalities to accommodate various learning styles.  Springboard has over 20 years of experience in the OCM and training domain, with many successful projects to its credit.

#### Options, Class Size, Materials, and Resources

Available training options include:

User Training:

General user training—contractor-developed, self-paced online course(s) to provide basic information (who, what, why, and when) and general user training on how to navigate and perform simple tasks in the system.  We can also include practice simulations.  Self-paced online course(s) should take users no longer than 15 minutes to complete.

Typical class size: No limit for self-paced online courses

Materials: Self-paced training with a workbook

Class duration: Between 8-15 minutes

Resources: One full-time training lead and four to six trainers

Role-based training—contractor-developed and delivered, live, virtual training session(s) for identified administrators, system super-users, and role-specific end users.  Sessions will include presentation, demonstration, hands-on practice in the solution, as well as familiarization and practice using all contractor-developed support materials (printed and online).

Typical class size: 35-40

Materials: Workbook, training scenarios, job aids

Class duration: Approximately 90 minutes

Resources: One full-time training lead and four to six trainers

Go-Live support:

A help desk supported by contract trainers

Materials: Step-by-step “job aids” that include process steps, instructions, and screenshots of the system.  We will maintain these throughout the life of the project so that they are always up to date.

Resources: We recommend a minimum of two full-time contractor resources to support OCM and training needs during this period.

Transition to self-support:

A thirty (30) day post-implementation “aftercare” support plan will be implemented, with onsite office hours, virtual “Pop-up lab” sessions, and open online virtual meetings that users can join, as needed, with a centralized group email box for immediate support.

Typical class size: No limit for online aftercare support

Materials: Job aids and quick-sheet directions

Class duration: User discretion, 15 – 60 minutes

Resources: A minimum of two full-time contractor resources to support OCM and training needs is recommended during this period.

In addition to formal training, MDHHS users who participate in user-acceptance testing (UAT) will receive training before each UAT cycle, which results in a group of users who are very knowledgeable about the system and capable of sharing that knowledge across the organization.  The KL&A test lead will provide UAT preparation training.

#### Training Plan

The training lead and OCM team will work with the technical team and MDHHS to establish a training cadence that aligns the OCM strategy with technical implementation to ensure users are trained at the right times.  By synchronizing training with functional releases, users will be equipped with the knowledge they need, when they need it, so the concepts are fresh in their minds when it’s time to use the new system.

During sprint zero, the KL&A-Springboard training lead will develop a Training Plan (SEM-0703) that:

Spells out the scope and objectives of training;

Identifies roles and responsibilities;

Clarifies evaluation practices for determining if learning outcomes have been achieved;

Addresses training strategy;

Identifies required training resources, locations, and environments;

Identifies training dates and times; and

Specifies who will attend each section of training.

#### Past Experience that Demonstrates Springboard’s Capabilities

Springboard has provided training for systems at the State of Michigan over the past 9 years, including high-visibility systems such as:

The SIGMA system, implemented in 2017-2018 at MDHHS, required an extensive training program that included:

Online pre-recorded training,

Live in-person training for 25 participants per session, using a training environment,

Multiple classroom locations located in four regional state facilities,

Help desk training, and

A “pop-up” lab for one-on-one, post-go-live support conducted at field offices.

Ongoing multiple training programs from 2018 to 2021 to better utilize SIGMA based on Lean Process Improvements (LPI) and development of the Program Grants Liaison group to use SIGMA Grants Monitoring functionality.

Michigan Immunization Portal.  Springboard used human-centered design principles to guide the user interface development of the Portal.  It also created the end-user-focused Frequently Asked Questions document and video tutorial for citizens on how to find and download a pdf of their Immunization record via the Michigan Immunization Portal.

COVID-19 Vaccination Provider Enrollment initiative.  Springboard developed training materials, video tutorials, and multiple webinars to assist Health Care Providers with enrollment through the REDCap and Michigan Care Improvement Registry (MCIR) systems, which were required to be eligible to provide COVID-19 vaccinations.

#### Training Materials Examples

This section showcases a KL&A-produced training video, as well as materials used to support live training for the Vegetative Management System.  It also includes a Springboard-produced job aid.

##### Training Video Examples

For a solution that KL&A developed for Environment, Great Lakes & Energy (EGLE) called the Michigan Environmental Health and Drinking Water Information System (MiEHDWIS), we provided a series of training videos.  Each video explains how to use a specific feature or perform a specific task.  Videos for external users are published in a public YouTube channel, while videos for EGLE staff who are using the administrative features are published in a private YouTube channel.  The KL&A team created the administrative function videos.  Then EGLE training staff developed playlists tailored to specific job functions.  End-users then subscribe to the applicable playlists to access relevant videos.  They can also browse the entire video library.  We’ve found that most users prefer video as it is often easier to consume than text resources and provides visual context to assist with cognition.

While we would like to submit multiple MiEHDWIS training videos for evaluator review, they all exceed the SIGMA 6MB file size limit.  However, through Windows file compression, we were able to compress one of the shorter videos enough to submit with our proposal.  Please refer to file:

13_MDHHS_MIDASH_Sample-MiEHDWIS_EntityActionsDrawer_Video.zip

To unzip this file, right-click the filename and select Extract All and then follow the prompts.  These instructions reflect Windows 10 with no third-party compression tools installed.  This process may vary if you have a third-party compression tool, you are on a different version of Windows, or you are on another operating system.  Additionally, KL&A is happy to provide additional videos upon request.

##### Other Training Materials Examples

The Vegetative Management System (VMS) that KL&A is modernizing for the Michigan Department of Natural Resources (DNR) requires training users across the State of Michigan.  As such, the KL&A trainer uses a combination of materials, including a presentation to guide the training sessions in conjunction with product demonstrations and a User’s Guide.  When viewing the samples, you will notice that the presentation is merely a roadmap for the training session.  When the trainer reaches a training topic slide, they navigate to a training instance of the application to demonstrate the applicable functionality.  They also instruct users to turn to a specific page in the accompanying VMS User’s Guide.  The User’s Guide provides step-by-step instructions, along with practice scenarios.

Refer to the following files included with the proposal submission:

14_MDHHS_MIDASH_Sample-Training-VMS_5_Release_2_Day_1_FromKLA.pptx

15_MDHHS_MIDASH_Sample-Training-VMS_5_Release_2_Day_2_FromKLA.pptx

16_MDHHS_MIDASH_Sample-Training-VMS_5_Release_2_Close_FromKLA.pptx

17_MDHHS_MIDASH_Sample-Training-VMS-5.2_Manual_FromKLA.pdf

To make all training resources easily accessible, we developed a Training Manuals screen (shown in Figure 1).  It provides a mechanism for editing, deleting, and uploading additional materials so that the MDNR can maintain these materials after KL&A’s contract expires.

Figure 1. VMS Training Manuals Screen

KL&A can optionally provide a similar solution for the MIDASH Solution.  In addition to user and administrator guides, training videos could be posted to this location for easy access.

##### Job Aid Example

Springboard produced this job aid to help users after training.  Please refer to the file:

19_MDHHS_MIDASH_Springboard_JobAid_Example_FromKLA.pdf

TRANSITION RESPONSIBILITIES

Bidder must provide a detailed transition-in and transition-out plan in Schedule G – Transition In and Out Plan, including any roles or responsibilities expected of the State. The plan must demonstrate the steps to migrate between Bidder’s Solution and third-party Solutions. Please certify below that you have provided the requested response in Schedule G. BIDDER RESPONSE: See KL&A’s response below in blue text.

### Bidder Response to Transition Responsibilities

KL&A understands that transferring knowledge to our clients’ users and maintenance staff, or their designees, at the end of the contract is important to ongoing success.  Though KL&A has never, in 30 years of business, had a contract terminated, we understand that provisions must be in place for a smooth transfer of services should the State choose to terminate the contract early.  Whether the contract is terminated early or expires naturally, KL&A will ensure that the parties taking ownership of the MIDASH Solution are properly trained and have the necessary documentation to take over the development or maintenance of the system.

#### Transition-In and Transition-Out Plan

KL&A certifies that it has provided the requested response to 14. TRANSITION RESPONSBILITIES.

The prompt asks us to certify that we’ve provided the requested response in Schedule G, however, Schedule G is the Federal Provisions Addendum.  Schedule F is labeled TRANSITION IN AND OUT PLAN, therefore, we’ve labeled our Transition In and Out Plan as Schedule F.

Please refer to the file:  12_MDHHS_MIDASH_Transition-In-OutPlan_FromKLA.docx.

DOCUMENTATION

Contractor must provide all user manuals, operating manuals, technical manuals and any other instructions, specifications, documents or materials, in any form or media, that describe the functionality, installation, testing, operation, use, maintenance, support, technical or other components, features or requirements of the Software. Contractor must develop and submit for State approval complete, accurate, and timely Solution documentation to support all users, and will update any discrepancies, or errors through the life of the contract. The Contractor’s user documentation must provide detailed information about all software features and functionality, enabling the State to resolve common questions and issues prior to initiating formal support requests.

Bidder must provide details on, and examples of, documentation to meet the requirements set forth in this section. See KL&A’s response below in blue text.

### Bidder Response to Documentation

KL&A will provide all the documentation necessary for end-users and system administrators, as well as the technical staff who will assume maintenance responsibilities at the end of the contract.  Our training lead will author comprehensive, task-oriented manuals that explain how to use every feature and screen in the application, including system administration and configuration information.  The documentation will support training activities and provide users with user-friendly, self-help resources.

We have a variety of tools and approaches available.  For example, the Michigan Department of Natural Resources (MDNR) required training and documentation for the Vegetative Management System that would support geographically dispersed teams.  MDNR wanted a way for users to have access to training manuals from within the system, so we developed a Training Manuals component (Figure 2) that provides easy access to training materials and user guides.  It also provides a mechanism for editing, deleting, and uploading additional materials so that MDNR can maintain these materials long after KL&A’s contract expires.

Figure 2. VMS Training Manuals Screen

For a solution that KL&A developed for EGLE called the Michigan Environmental Health and Drinking Water Information System (MiEHDWIS), we provided a series of training videos.  Each video explains how to use a specific feature or perform a specific task.  Videos for external users are published in a public YouTube channel, while videos for EGLE staff who are using the administrative features are published in a private YouTube channel.  The KL&A team creates the administrative function videos.  Then EGLE training staff develop playlists that are tailored to specific job functions.  End-users can then subscribe to the applicable playlists to access relevant videos.  They can also browse the entire video library.  We’ve found that most users prefer video as video is often easier to consume than text resources and provides visual context to assist with cognition.

Our trainer will work with project stakeholders to develop a documentation approach that best supports MDHHS’ users.

Our trainer will update all end-user materials (documents or videos) with each sprint to ensure they are always current.  KL&A will also include a user-acceptance review of materials in each UAT cycle to ensure every feature is documented in a truly useful fashion with accurate and complete information.

Concerning project management and system engineering documentation, KL&A will follow the SUITE Agile Process Guide, producing and maintaining the necessary SUITE documents throughout the project, which is discussed in more detail in “Bidder Response to SUITE Documentation,” on page 114.

#### Examples of End-User Videos and Documentation

While we would like to submit multiple MiEHDWIS training videos for evaluator review, they all exceed the SIGMA 6MB file size limit.  However, through Windows file compression, we were able to compress one of the shorter videos enough to submit with our proposal.  Please refer to the file:

13_MDHHS_MIDASH_Sample-MiEHDWIS_EntityActionsDrawer_Video.zip

To unzip this file, right-click the filename and select Extract All and then follow the prompts.  These instructions reflect Windows 10 with no third-party compression tools installed.  This process may vary if you have a third-party compression tool, you are on a different version of Windows, or you are on another operating system.  Additionally, KL&A is happy to provide additional videos upon request.

For an example of an end-user guide that KL&A authored for the Michigan Department of State (MDOS) Out-of-State Resident Service (OSRS) Request Management System (RMS), see the file:

18_MDHHS_MIDASH_Sample-Manual-OSRS_RMS_UserGuide_FromKLA.pdf.

For easy access, this guide was made available from within OSRS.  All cross-references are hyperlinks, making it easy for users to navigate to specific topics.  The guide also includes a navigation pane that shows content headings hierarchically when the guide is viewed in Acrobat Reader.

Additionally, the samples provided for “Bidder Response to Training Services” include the VMS User’s Guide—refer to file:

17_MDHHS_MIDASH_Sample-Training-VMS-5.2_Manual_FromKLA.pdf.

ADDITIONAL PRODUCTS AND SERVICES

Bidder must describe additional Solution functionality, products or services that the State specifications do not address but are necessary to implement and support this solution. BIDDER RESPONSE See KL&A’s response below in blue text.

### Bidder Response to Additional Products and Services

MDHHS has requested 180 calendar days of warranty after implementation, as well as maintenance and support services that can be optionally extended for up to five (5) additional years after the five-year base contract.  This section describes our approach to maintenance and support services.

KL&A provides maintenance and technical support for many State of Michigan applications, including all the referenced projects in the Vendor Questions Worksheet response section of our proposal.

Maintenance and support include:

Answering questions regarding system functionality or processes;

Repairing defects identified during production operations; and

Resolving production problems resulting from user error that results in data errors.

We have a dedicated help desk that triages support calls, ensuring issues are routed to the appropriate personnel, and a substantial maintenance team that assumes responsibility for a system once the system is in production.  During development, maintenance and support are provided by the development team.

Our processes and tools are designed to ensure timely responses and effective resolutions that comply with the agreed-upon service levels.  The rest of this section describes the basic elements of our maintenance and support process, the roles and responsibilities involved in maintenance and support, and the help desk process phases.

#### Basic Elements

Our support process is built around the following assumptions:

Defects are triaged based on their impact on the customer’s operations.  We will classify defects in accordance with section 2.4 Service Level Table of SCHEDULE D - SERVICE LEVEL AGREEMENT attached to the RFP.  For convenience, we’ve replicated the information below.

Table 3. Defect Classification Required by 
SCHEDULE D - SERVICE LEVEL AGREEMENT
Provided with RFP# 220000001798

| Support Request Classification | Definition | Service Level Metric (Required Response Time) | Service Level Metric (Required Resolution Time) |
| --- | --- | --- | --- |
| Critical Service Error | (a) Issue affecting entire system or single critical production function; (b) System down or operating in materially degraded state; (c) Data integrity at risk; (d) Material financial impact; (e) Widespread access interruptions; or (f) Classified by the state as a Critical Service Error. | Contractor shall acknowledge receipt of a Support Request within thirty (30) minutes. | Contractor shall Resolve the Support Request as soon as practicable and no later than four (4) hours after Contractor's receipt of the Support Request. If the Contractor Resolves the Support Request by way of a work-around accepted in writing by the State, the support classification assessment will be reduced to a High Service Error. |
| High Service Error | (a) A Critical Service Error for which the State has received, within the Resolution time for Critical Service Errors, a work-around that the State has accepted in writing; or (b) Primary component failure that materially impairs Software’s performance; (c) Data entry or access is materially impaired on a limited basis; or (d) performance issues of severe nature impacting critical processes. | Contractor shall acknowledge receipt of a Support Request or, where applicable, the State's written acceptance of a Critical Service Error work-around, within twenty-four (24) hours. | Contractor shall Resolve the Support Request as soon as practicable and no later than two (2) Business Days after Contractor's receipt of the Support Request or, where applicable, the State's written acceptance of a Critical Service Error work-around. |
| Medium Service Error | An isolated or minor Error in the Software that meets any of the following requirements: (a) does not significantly affect Software functionality; (b) can or does impair or disable only certain non-essential Software functions; or (c) does not materially affect the State's use of the Software. | Contractor shall acknowledge receipt of the Support Request within two (2) Business Days. | Contractor shall Resolve the Support Request as soon as practicable and no later than ten (10) Business Days after Contractor's receipt of the Support Request. |
| Low Service Error | Request for assistance, information, or services that are routine in nature. | Contractor shall acknowledge receipt of the Support Request within five (5) Business Days. | N/A |

Typically, production applications will have a published release schedule for correcting system defects.  The frequency of the schedule may vary depending on the stability of the system and the interaction with any development activities.  Target service levels are:

Mature applications (low volume of defects) —quarterly releases

New applications (higher volume of defects)—bi-monthly releases

Applications within development efforts—releases will be integrated with development releases where possible

KL&A recognizes that the resolution times set forth in the Contract Terms require more frequent releases than our standard release scheduling guidelines.  KL&A will work with MDHHS and DTMB to meet the State’s requirements.

Telephone support will be available 8 AM through 5 PM EST, Monday through Friday.

Online support, through Jira, is available 24 hours per day, seven days per week.

KL&A will assign experienced and knowledgeable staff to support operations, including primary, secondary, and tertiary staff assignments.

#### Roles and Responsibilities

Issues reported to the help desk will be entered into Jira, our defect tracking and sprint management system.  Jira has a web interface that supports access from any location that has an internet connection.  The following illustration shows who will interact with Jira.  Following the illustration is a table that indicates the responsibilities of each organizational unit that will use Jira.

Figure 3. Organization Units that Interact with Jira

| Organization Unit | Responsibilities | Tasks |
| --- | --- | --- |
| Client User | Initiate defect Close defect | Logs defect Assists in priority determination Tests and accepts defect solution |
| Help Desk Coordinator | Initial contact with the client for defect management Overall defect management | Works with client to log and triage defect Monitors service levels for overall maintenance activity |
| KL&A Support Staff | Defect analysis, correction, and resolution | Analyzes the root cause of the defect Applies change Tests change Moves fix to production |
| KL&A Project Manager | Overall defect planning and management for supported application | Assigns defect to release schedule Monitors and manages progress Informs client of progress |

#### Help Desk Process Phases

We have organized the Help Desk process into three phases:

Phase 1: Planning

Phase 2: Defect Triage, Logging, and Assignment

Phase 3: Defect Repair & Closeout

##### Phase 1: Planning

At the start of each fiscal year, KL&A will establish a release schedule and assign support staff, which is captured in a Maintenance Plan.

The release schedule will be phased based on the number of defects anticipated (based on history, the life cycle of the project, and any accompanying development efforts).

MIDASH Solution maintenance will be assigned to specific staff.  Staff will be assigned based on the following criteria:

Primary—has detailed knowledge of the application, the client, and the supporting technology

Secondary—has knowledge of the application

Tertiary—has knowledge of the application or the supporting technology

MIDASH Solution maintenance may have multiple candidates for each support level.  Support staff may be rotated based on schedule and needs.

KL&A will provide a copy of the Maintenance Plan at the beginning of each fiscal year.

Phase Deliverables:

Annual Maintenance Plan with resources identified

##### Phase 2: Defect Triage, Logging, and Assignment

Users can call the help desk or enter a defect directly into Jira.  If they call the help desk, the help desk coordinator will log the defect.  Jira is configured to alert the appropriate personnel when a new ticket is created or when an existing ticket is updated.

Within the contractually allotted times (One to three hours depending upon classification), a qualified maintenance and support resource will review and triage the ticket.  The triage process is a disciplined analysis of the problem’s impact to determine whether the problem can be part of a scheduled maintenance release or if it requires more immediate attention.

Jira will serve as the communication tool between the end-user, the support analyst, the maintenance and support manager, and the project manager.  Every update to a ticket will generate an email to all appropriate parties.  In addition to communication, Jira tracks all information pertaining to the analysis and repair of the defect, including the status of the repair, the time spent on the repair, customer acceptance of the repair, and several other service-level metrics.

Phase Deliverables:

Defect assigned to support staff or assigned to a release

##### Phase 3: Defect Repair and Closeout

The final phase of the process involves identifying and developing the solution to the defect, testing the solution, and migrating the defect repair to production.

Our maintenance team will test the repair internally and update all related documentation, then deploy the repair to the test environment.  KL&A will facilitate UAT to confirm that the issue is resolved to the satisfaction of the State.  Once the release is user accepted, KL&A deploys the repair to production.  Once the repair is deployed, the reporter of the issue will close the Jira ticket.

Phase Deliverables:

Tested solution moved to production

All applicable SEM and end-user documentation updated

Closed Jira ticket

CONTRACTOR PERSONNEL

Contractor Contract Administrator.  Contractor resource who is responsible to (a) administer the terms of this Contract, and (b) approve and execute any Change Notices under this Contract.

| Contractor |  |
| --- | --- |
| Name Address Phone Email | Justin Shaulis, KL&A Partner 28081 Southfield Road Lathrup Village, MI 48076-2816 Office: 248-559-7910 Fax: 248-559-8066 Mobile: 517-803-3217 j.shaulis@kunzleigh.com |

Contractor Security Officer.  Contractor resource who is responsible to respond to State inquiries regarding the security of the Contractor’s Solution.  This person must have sufficient knowledge of the security of the Contractor Solution and the authority to act on behalf of Contractor in matters pertaining thereto. Contractor must inform the State of any change to this resource.

| Contractor |  |
| --- | --- |
| Name Address Phone Email | Shaun Giddings 28081 Southfield Road Lathrup Village, MI 48076-2816 Office: 248-559-7910 Fax: 248-559-8066 Mobile: 248-330-1665 s.giddings@kunzleigh.com |

Bidder must provide a detailed proposed staffing plan broken down for each milestone/phase (i.e., which resource roles, number of resources for each role, hours for each resource, expected tasks, etc).
BIDDER RESPONSE:

See our response below in blue text.

### Bidder Response to Contractor Personnel

Highly skilled, experienced personnel is a fundamental component of KL&A’s success.  We employ a rigorous interview process that includes real-world exercises to ensure that the people we hire are capable of producing the highest quality solutions.  KL&A is also committed to providing an excellent working environment, with a flexible and vibrant culture that keeps our employees happy and attracts new talent.  This means that we have a large team of highly qualified personnel that are passionate about what they do and love working for KL&A.

KL&A’s team comprises fully vetted, certified project managers, business analysts, system analysts, system architects, full-stack developers, user experience designers, testers, quality assurance analysts, trainers, and technical writers.  This abundance of skills, talent, and passion achieves innovative synergy.

Many of our staff possess multi-faceted skill sets that allow them to perform activities associated with multiple job descriptions.  For example, many of our project managers have technical backgrounds that support their ability to perform business and system analyst activities in addition to project management activities; our business analysts can and do regularly perform system integration testing and on-site training, in addition to traditional business analysis activities; many of our developers can code in multiple languages for different platforms, build and maintain databases, and assess and implement security provisions.  This allows us to be extremely flexible with regard to project staffing requirements.

Each of our projects is overseen by a project manager, most of whom are Project Management Institute (PMI) certified.  Projects are also typically staffed with one or more business/quality assurance analysts (BA/QAs) who:

Elicit, analyze, and document business processes, business needs, and business constraints, including user pain points, to develop comprehensive requirements, user epics, and user stories;

Facilitate joint application design sessions with project stakeholders;

Develop system and user documentation;

Write test case;

Execute various types of testing, and

Facilitate user acceptance testing (UAT).

Many of our BA/QAs have development backgrounds and specialize in user experience design to aid development with design activities, ensuring a solution that is elegant and efficient.  We also have a large development staff who have experience with a variety of technologies and who pride themselves on continuous learning.

What does all of this mean to MDHHS?  MDHHS can expect a dedicated, skilled, and experienced team that will collaborate with project stakeholders every step of the way to deliver a modern, user-friendly MIDASH Solution.

The remainder of this section provides a brief description of each key resource, followed by a resource allocation breakdown that shows the number of each resource type to be engaged each month of the proposed project timeline.

#### Contractor Personnel

This section briefly describes each of KL&A’s key resources qualifications and the type of work they will provide.  For more detail on resource skills and experience, including project history, please refer to their completed resume template forms and KL&A-branded resume in the file:

08_MDHHS_MIDASH_Attachment1-Resumes-FromKLA.docx.

##### Project Manager

Travis Tompkins is a well-rounded certified technical project manager with a software development background.  He began his career at KL&A as a software engineer, designing, developing, and maintaining web applications for the State of Michigan.  Mr. Tompkins’ knowledge in web-based design extends his capabilities in software development, ranging from integrating new hardware to developing applications based on business logic and client needs.  Mr. Tompkins can adapt to any new environment very quickly to implement new software with any language or database.

Over the past eight years, Mr. Tompkins has continued a project management role, managing over twenty State of Michigan agile projects.  Mr. Tompkins has overseen project scheduling, release planning, user acceptance testing, and release execution.  Also, as the current maintenance and support manager, Mr. Tompkins has scheduled and managed all enhancement and new system activities for multiple projects, concurrently.

As the project manager, Mr. Tompkins will be responsible for:

Managing all defined KL&A responsibilities in the scope of services

Developing the Project Management Plan and project schedule, updating as needed

Serving as the point person for all project issues

Coordinating and overseeing the day-to-day project activities

Escalating project issues, risks, and other concerns

Reviewing all project deliverables and providing feedback

Proactively proposing/suggesting options and alternatives for consideration

Using change control procedures

Preparing project documents and materials

Facilitating sprint planning and retrospective

Owning and assigning action items

Reporting project status to the DTMB PM and MDHHS product owner(s)

Assessing and mitigating risks

Finding and removing roadblocks

Facilitating communication between roles for every aspect of the project

Keeping release/project information consolidated, organized, and up to date

Driving the cross-functional team at all levels

Driving the execution of sprints

##### Security Lead

Mr. Giddings is a DevOps engineer with ten years of information technology systems, network, and security experience.  He has managed environments ranging from dozens of users with a few servers and networking appliances to environments of over 10,000 users and dozens of servers and several dozens of networking appliances.  At KL&A, he specializes in Microsoft Azure infrastructure hosting.  Mr. Giddings’ passion for cloud infrastructure, automation, and data security drives him to improve his experience in cloud-based technology.

As the security lead, Mr. Giddings will be responsible for the overall security of system data, including:

Working with the team to ensure all architecture and designs adhere to industry data security best practices and the State of Michigan’s standards

Ensuring all MDHHS and DTMB security assessments and documents are completed

Designing and developing web services for secure data sharing

Performing data security risk assessments and developing mitigation strategies

Performing any necessary scans and penetration testing to ensure data security

##### HIV/STI Functional Lead

Mr. Sanborn is a full-stack developer with over 20 years of programming, web development, database design, analysis, and systems architecture experience.  He has worked in and around cutting-edge technology his entire career, staying current on the latest developments in server and client-side systems.  His diverse technology experience paired with a degree in physics research form the foundational toolset for high-level problem solving and implementation.  Mr. Sanborn is passionate about deeply understanding issues and finding solutions that best fit the clients’ needs.

As the HIV/STI functional lead, Mr. Sanborn will be responsible for:

Performing Agile functions such as assisting the scrum master, DHSP-appointed product owner, and the KL&A technical team with Scrum ceremonies

Working with DHSP to understand business processes and rules to define, elaborate, and/or validate functional and technical requirements

Contributing HIV-systems development experience to assist the team with understanding the HIV technology landscape

Effectively conveying information to audiences of all skill levels and improving transparency

Building trust with clients to elicit desired functionalities from business and functional requirements via joint application design (JAD) sessions

Utilizing user-centered design methodologies to solve technical problems

Developing functionality according to the specifications in the user stories

Creating and maintaining process maps and data flow diagrams

Documenting and tracing requirements through the system development lifecycle

Using MS Excel, Word, PowerPoint, and Visio to perform various business analysis activities

Supporting the OCM and training team as necessary

##### Business Analyst Lead

Ms. McEvilly is an experienced Business Analyst / Application Architect / Senior Systems Analyst / Developer – PL/SQL Specialist.  Her strong skill set has been proven and expanded through her analysis, design, and implementation of large- and medium-scale projects.  She has been effective in multiple project roles, as she began her career as a developer, and has gained extensive experience in complex database and system design.  Ms. McEvilly has worked in both a traditional systems development methodology, as well as Agile development, and is comfortable in both environments.

She has many years of experience in both financial systems and Medicaid/claims-related applications.  Her expert analytical skills allow her to solve complex design issues.  During her long tenure with Kunz, Leigh and Associates, Ms. McEvilly has implemented software for several State of Michigan agencies.  She is comfortable leading design sessions and working directly with business users to provide the analysis and collaboration needed for successful project implementation.

As the business analyst lead, Ms. McEvilly will be responsible for overseeing the business analysis activities, including:

Performing Agile functions such as assisting the scrum master, DHSP-appointed product owner, and the KL&A technical team with Scrum ceremonies

Working with DHSP to understand their business processes and rules to define, elaborate, and/or validate functional and technical requirements

Analyzing and developing user stories, including acceptance criteria and test scenarios

Effectively conveying information to audiences of all skill levels and improving transparency

Building trust with clients to elicit desired functionalities from business and functional requirements via joint application design (JAD) sessions

Utilizing user-centered design methodologies to solve technical problems

Creating mockups and wireframes to convey functionality to stakeholders and the development team

Creating and maintaining process maps and data flow diagrams

Assisting DHSP with prioritizing the product backlogs

Documenting and tracing requirements through the system development lifecycle

Using MS Excel, Word, PowerPoint, and Visio to perform various business analysis activities

Delegating work to and supporting business analysts

Supporting the OCM and training team as necessary

##### Human-Centered Design (HCD) / User Experience (UX) Design Lead

Tylor Hoekstra is a UX/UI specialist and business analyst with eight years of software development, project management, user-centered/accessible design, and usability research experience.  He has led teams that produced several successful academic research proposals and university departmental websites.  He founded, managed, and trained a group of students who formed a college innovation team that created and maintained several vital functions for the College of Arts & Letters at Michigan State University.  At KL&A, he specializes in planning and designing accessible user interfaces for online applications and websites.

Additionally, Mr. Hoekstra has experience analyzing and working with existing software systems and clientele to help improve usability and performance.  He has the skills necessary to organize and conduct joint application design (JAD) sessions with clients, during which system requirements and user stories are defined.  He often is tasked with exploring and understanding the business process flows and writing various forms of technical documentation, including functional and end-user documentation.  Mr. Hoekstra also creates test plans, writes test cases, performs functional and system testing, and facilitates user acceptance testing.

As HCD/UX design lead, Mr. Hoekstra will be responsible for overseeing the HCD/UX design activities, including:

Using UI/UX design methodologies and best practices to design and develop user-centric, responsive, and accessible interfaces

Creating high-quality mockups and wireframes to convey functionality to stakeholders and the development team

Designing technical solutions with maximum usability, scalability, and efficiency in mind

Collaborating with business analysts, developers, and various end-users to design a solution that provides an optimal user experience

Designing applications that comply with WCAG 2.0 AA standards and SOM look-and-feel standards

Testing and validating the UI/UX for consistency of design and flow

Ensuring that the solution performs appropriately and scales gracefully in multiple browsers and on various platforms

Using Angular or similar modern JavaScript/Typescript frameworks (Ex. React, Vue) to improve frontend functionality

Using HTML/CSS/JavaScript to implement a consistent design

##### Agile Team Lead / Technical Lead / Solution Architect

Tim Golisch is a senior software developer with over 30 years of experience designing and building enterprise-level solutions in the government, insurance, financial, medical, and defense industries.  He leads teams to implement patterns and technologies from the ground up, at a corporate scale.  His extensive background includes object-oriented and functional languages, embedded controllers, “Internet of Things” (IoT), enterprise integration patterns, extensive experience with relational database systems and reporting, and a variety of front-end technologies.  Mr. Golisch is a Certified Scrum Master (CSM) that specializes in designing solutions that are highly scalable, interoperable, and sustainable.  He is passionate about continually learning new platforms and tooling.

Mr. Golisch will be allocated 100% to this project, fulfilling two roles.  As the agile team lead and technical lead/solution architect, Mr. Golisch will be responsible for:

Leading daily scrums and working to address barriers to the progress of the team

Leading cross-functional teams of subject matter experts, developers, and business analysts

Collaborating with MDHHS to assess and validate the technical, business, and functional requirements

Grooming and maintaining backlogs

Facilitating vision, release, and iteration planning

Providing direction to the overall development team

Ensuring development best practices and standards are being followed

Supporting the software engineers with activities such as code reviews

Supporting the teams with business analysis and quality assurance activities, when needed

Supporting the KL&A project manager by providing status information

Assisting with documentation development

Facilitating meetings

##### Integration Lead / Data Migration / Production Support Engineer

Mr. Torres is a dedicated, senior software engineer with over 20 years of development experience, eleven (11) of which he supported State of Michigan web-based, database, and web-server applications.  Mr. Torres has experience developing applications for a variety of public and private industries including insurance, government, utilities, banking, manufacturing, and retail.  He is supporting and enhancing a dozen web, database, and server applications for the State of Michigan.  He can work on any piece of the IT puzzle and excel as a complex problem solver who thrives on completing releases on time and error-free for happy customers.

Mr. Torres will be allocated 100% to this project, across three roles.  As the project progresses, his focus will shift from one role to the next, starting with integration/interface lead responsibilities, moving into data migration/conversion lead responsibilities, and finally production support engineer responsibilities.  Mr. Torres will be responsible for:

Designing and documenting the integrations and interfaces for the MIDASH Solution

Assisting with developing the integration roadmap

Analyzing business requirements and collecting the details required for integrations implementation

Engaging other technical team members in the design, delivery, and deployment of the solution

Strategizing and planning data migration and conversion, while considering risks and potential impacts

Auditing existing data systems and deployments and identifying errors or areas for improvement

Gathering, analyzing, and processing client data during data migrations

Profiling and mapping data

Providing critical technical recommendations/solutions for complex problems

Developing data conversion scripts that ensure clean data and validating migrated data

Tracking and reporting client feedback through the appropriate channels

Reporting on and adhering to project milestones and service level agreements

Proactively detecting, troubleshooting, and resolving all issues affecting production applications

Working with users to analyze, research, and resolve customer support issues

Coordinating with and escalating to development and external teams where necessary

Conducting analysis, research, and resolution of customer support cases

##### Test Lead

Mr. Steffy is a Test Manager with over 17 years of experience leading test teams; defining testing approaches; determining test data requirements; creating test plans for all types of testing, including functional and black box testing, white box testing, system testing, regression testing, load testing, user acceptance testing (UAT), and business-to-business and end-to-end testing for multi-system solutions; creating and executing test scripts; and tracking defects and confirming fixes.  His previous experience includes help desk administration, business and system analysis, and project management, all of which provide him with a diverse skillset and cross-functional knowledge that makes him an exceptional test manager.  He regularly interfaces with business users to elicit testing and data requirements to develop use cases, facilitate UAT, facilitate multi-party testing, and collaboratively analyze test results and root causes.  Additionally, Mr. Steffy has conducted technical demonstrations, training, and workshops, including testing methods within an Agile environment, mobile software testing approaches, retrospective dos and don’ts, leveraging unit testing throughout the software development life cycle for UAT testing, and requirements gathering best practices.  He’s worked in both the private and public sectors, serving state and federal government agencies on large-scale enterprise applications, such as TechSmith’s enterprise-wide content management system (CMS) that generated annual sales of over $20M and serviced over 300,000 unique users per month.  He also managed the Business Partner Readiness (BPR) activities with 23 major health plans and the entire State of Michigan Medicaid Provider Network to ensure that all systems and providers were ready for the switch to ICD-10 coding of medical claims.

As the test lead, Mr. Steffy will be responsible for organizing, leading, and overseeing all testing activities, including:

Developing test plans, test cases, and test scripts

Overseeing the testing team to ensure complete test coverage for all required types of testing

Conducting UAT kickoff meetings and training users on UAT practices and tools.

Facilitating sprint and release UAT activities

Working with MDHHS and DTMB to regularly triage UAT defects

Delivering testing metrics data to the KL&A project manager for inclusion in weekly status reports

Triaging defects during the warranty and maintenance and support phases of the contract

Overseeing defect resolution activities during the DDI and warranty phases of the contract, ensuring services levels are met

##### Organizational Change Management (OCM) Lead

April Callis-Birchmeier has over 20 years of experience leading change initiatives on many large-scale implementation projects for private and public sector clients.  She is a Certified Prosci Change Practitioner, a Certified Change Management Professional (CCMP), and a Certified Project Management Professional (PMP).  Ms. Callis-Birchmeier is the owner and principal of Springboard Consulting and has been working with the State of Michigan since 2013 by developing and leading the organizational change strategy on multiple projects, including the MDHHS SIGMA implementation and the implementation of the Affordable Care Act - Healthy Michigan Plan.  Throughout her career, Ms. Callis-Birchmeier has worked with individuals involved at every level of a project, from individual end-users to project sponsors, to develop and execute change management strategies that ensure successful project implementations.  She is also an active member and leader of the change management industry, having authored her book called “READY, Set, Change! Simplify and Accelerate Organizational Change.”

As the organizational change manager (OCM) lead, Ms. Callis-Birchmeier will be responsible for overseeing and leading all OCM activities, including:

Developing and executing the Organizational Change Management Strategy and Plan

Working with the KL&A PM to integrate and align the project and change management plans

Conducting a stakeholder analysis and business readiness assessments

Performing an impact/gap analysis of all internal and external stakeholder groups

Coaching and supporting executive leaders and managers, when requested

Developing and implementing a Communication Strategy and Plan

Developing a Resistance Management Plan

Establishing and monitoring organizational and individual-based OCM goals and milestones

Providing training and coaching to Change Champion Network participants

Developing and implementing a Sustainability and Transfer of Ownership Plans

Facilitating weekly OCM status meetings to review progress on OCM-specific activities, evaluate stakeholder and user engagement, and identify any risks and issues

##### Training and Business Readiness Lead

Amelia Mimi Brown has over a decade of experience providing training services to private and public sector organizations, including serving as the lead trainer for end-user training on the State of Michigan’s SIGMA implementation project.  She has facilitated and led a variety of training programs including leadership development, communication, change management, and financial systems training.  Ms. Brown has experience using experiential learning, video, and virtual learning methodologies to deliver product-specific training, as well as conducting live, classroom training within a training environment.  She has tremendous experience speaking to groups of varying sizes and experiences.  Described as a natural problem-solver, Ms. Brown uses innovation and creativity to perform needs analysis and then design, develop, deliver, and evaluate training initiatives.  Ms. Brown possesses a solid understanding of adult learning styles, curriculum development, and training methods that motivate and inspire.

As the training and business readiness lead, Ms. Brown will be responsible for overseeing all training activities, including:

Working with the KL&A PM, OCM Lead, MDHHS and DTMB to develop and execute the Training Strategy and Plan and ensuring that all activities are appropriately integrated and on schedule

Providing direct supervision of the training team

Ensuring the quality of the training materials and the successful execution of the instructor-led training sessions

Translating business logic and technology into user manuals and training guides for non-technical, end-users

Coordinating with business users and development teams to gain thorough business and functional knowledge to create effective training manuals and other end-user documentation

Effectively conveying information to audiences of all skill levels and improving transparency

#### Resource Allocation Breakdown

The table below provides an overview of the anticipated resources that KL&A will need to successfully complete the MIDASH Solution project.  It is broken down by resource type and months to illustrate the total quantity needed for each resource type throughout the project.  On average, each full-time resource will spend 160 hours per month on the project.  For example, looking at the table, the agile team lead is allocated at 0.5, so he will spend 80 hours per month from the first month until the 23rd month, while the project manager will spend 160 hours per month for the entire project.

For a detailed breakdown of the tasks involved in the project, please refer “Bidder Response to Milestones and Deliverables,” on page 140, and our preliminary WBS/Schedule, which is in the file: 20_MDHHS_MIDASH_WBS-Schedule-Detail_FromKLA.pdf.

Figure 4. Resource Allocation Breakdown by Role and Month

| Anticipated Resource Type | Month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |
| Project Manager | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| HIV/STI Functional Lead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |
| Agile Team Lead | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  |
| Technical Lead / Solution Architect | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  |  |
| Test Lead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |
| Training and Business Readiness Lead |  |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |
| Production Support Engineer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0.33 | 0.33 | 1 | 1 | 1 | 1 | 1 |
| HCD / User Experience (UX) Design Lead | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |
| Organizational Change Management (OCM) Lead | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  |  |  |
| Security Lead | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  |  |
| Data Migration / Conversion Lead |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.33 | 0.33 |  |  |  |  |  |
| Integration/Interface Lead |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.33 | 0.33 |  |  |  |  |  |
| Business Analyst Lead | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Business Analysis | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |
| Certified Scrum Master |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |
| Configuration Manager |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |
| Developer | 1 | 1 | 1 | 12 | 12 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 13 | 13 | 2 | 2 | 2 | 2 | 2 |
| Lead Developer |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |
| OCM Support | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 |  |  |  |
| Project Coordinator | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |
| Testers |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  |  |
| Trainers |  |  |  |  |  |  |  |  |  |  |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  |  |  |

CONTRACTOR KEY PERSONNEL

Contractor will provide the following Key Personnel:

Contractor Project Manager

Contractor HIV/STI Functional Lead

Contractor Agile Team Lead(s) (Scrum Master(s) or equivalent)

Contractor Technical Lead / Solution Architect

Contractor Test Lead

Contractor Training and Business Readiness Lead

Contractor Production Support Engineer

Contractor HCD / User Experience (UX) Design Lead

Contractor Organizational Change Management (OCM) Lead

Contractor Security Lead

Contractor Data Migration / Conversion Lead

Contractor Integration/Interface Lead

Contractor Business Analyst Lead

CONTRACTOR PERSONNEL REQUIREMENTS

Background Checks. Contractor must present certifications evidencing satisfactory Michigan State Police Background checks, ICHAT, and drug tests for all staff identified for assignment to this project. In addition, proposed Contractor personnel will be required to complete and submit an RI-8 Fingerprint Card for the National Crime Information Center (NCIC) Finger Prints, if required by project. Contractor will pay for all costs associated with ensuring their staff meets all requirements.

Offshore Resources.

Bidder must acknowledge it will not use offshore resources in the performance of this contract. BIDDER RESPONSE: KL&A is not proposing to use offshore resources in the performance of the MIDASH Solution work.

Disclosure of Subcontractors.  If the Contractor intends to utilize subcontractors, the Contractor must disclose the following:

The legal business name; address; telephone number; a description of subcontractor’s organization and the services it will provide; and information concerning subcontractor’s ability to provide the Contract Activities.

The relationship of the subcontractor to the Contractor.

Whether the Contractor has a previous working experience with the subcontractor.  If yes, provide details of that previous relationship.

A complete description of the Contract Activities that will be performed or provided by the subcontractor.

Geographically Disadvantage Business Enterprise Sub-Contractors:  If the Contractors plan to utilize Subcontractors to perform more the 20% of the deliverables under this Contract, at least 20% of that Subcontractors work must be awarded to Michigan-based Geographically Disadvantaged Business Enterprises (GDBE).  Contractor will submit a plan detailing all Subcontractors to be used, including the percentage of the work to be done by each.  Contractor must inform the State to the name and address of the GDBE, the percentage of the work they will complete, the total amount estimated to be paid to the GDBE, and provide evidence for their qualifications as a GDBE.  If Contractor cannot find GDBE Subcontractors to meet this requirement they must provide reasoning and justification to receive an exemption  from this requirement from the State.  (Existing business relationships will not be an approved reason for this.)

Bidder to confirm review of the above requirement and confirm in writing that Bidder agrees without exception.  If Bidder does have an exception, please explain in detail the exception.
BIDDER RESPONSE:

KL&A has read and agrees to the terms specified in this section.

### Bidder Response to Disclosure of Subcontractor

| Bidder must provide detailed information as requested in the above requirement(s). |  |
| --- | --- |
|  | BIDDER RESPONSE: |
| The legal business name, address, telephone number of the subcontractor(s). | Springboard Consulting, LLC 3753 Clark Road Bath, MI 48808 (517) 281-7614 |
| A description of subcontractor’s organization and the services it will provide and information concerning subcontractor’s ability to provide the Contract Activities. | Springboard Consulting, LLC (Springboard) is KL&A’s strategic partner for the organizational change management (OCM) and training components of the MIDASH project. Springboard is a Michigan-based, woman-owned consultancy that specializes in preparing people for change using a people-focused approach to ensure successful project/system implementations. Springboard ensures organizations are prepared with the training, tools, and templates needed to reach their goals and experience the benefits of change. Springboard brings over 20 years of experience leading change initiatives for private and public sector clients, including the State of Michigan. |
| The relationship of the subcontractor to the Bidder. | KL&A and Springboard’s relationship is new, having only recently entered into a teaming agreement specifically for the MIDASH RFP. |
| Whether the Bidder has a previous working experience with the subcontractor. If yes, provide the details of that previous relationship. | Although KL&A does not have formal experience working with Springboard, KL&A has experience working alongside Springboard on several State of Michigan projects. During those engagements, KL&A was extremely impressed with the level of quality and dedication that Springboard represented, which is why KL&A believes they will bring tremendous value to the MIDASH project by delivering high-quality resources and services. |
| A complete description of the Contract Activities that will be performed or provided by the subcontractor. | As part of the MIDASH project, Springboard will be responsible for providing OCM and training resources who will manage and lead the project’s training and change management. Springboard will manage and lead all training services necessary for the MIDASH project, which will include: Working with the State to finalize the training strategy and plan, Developing all necessary training materials, Conducting the various role-based training in their desired/identified delivery format (i.e., live virtual, prerecorded, or written), and Leading any training specific to OCM activities (e.g., Change Champion Network training). Springboard will also manage and lead all OCM services necessary for the MIDASH project. The Springboard team will develop an OCM strategy and plan that is specific to the MIDASH project, and they will be responsible for carrying out that plan, which will include the various tasks, meetings, and activities surrounding: Executive leadership and middle manager engagement and support Stakeholder (internal and external) engagement and support Solution and stakeholder alignment Business readiness Change champion network engagement and support Communication management Milestone performance Sustainment and transfer of ownership |
| Of the total bid, the price of the subcontractor’s work. | 15% |

STATE RESOURCES/RESPONSIBILITIES

The State will provide the following resources as part of the implementation and ongoing support of the Solution.

State Contract Administrator.  The State Contract Administrator is the individual appointed by the State to (a) administer the terms of this Contract, and (b) approve and execute any Change Notices under this Contract.

State Contract Administrator

Name Phone Email

Program Managers.  The DTMB and Agency Program Managers (or designee) will jointly approve all Deliverables and day to day activities.

DTMB Program Manager

Name Phone Email

Agency Program Manager

Name Phone Email

MEETINGS

At start of the engagement, the Contractor Project Manager must facilitate a project kick off meeting with the support from the State’s Project Manager and the identified State resources to review the approach to accomplishing the project, schedule tasks and identify related timing, and identify any risks or issues related to the planned approach.  From project kick-off until final acceptance and go-live, Contractor Project Manager must facilitate weekly meetings (or more if determined necessary by the parties) to provide updates on implementation progress.  Following go-live, Contractor must facilitate monthly meetings (or more or less if determined necessary by the parties) to ensure ongoing support success.

The Contractor must attend the following meetings, at a location and time as identified by the state, at no additional cost to the State:

Contractor OCM Lead must facilitate weekly meetings with the support from State OCM lead and OCM Analyst assess stakeholder and user engagement, and identify any risks or issues related to the planned approach.

Contractor OCM Lead must be willing and able to schedule meetings with State OCM team upon request.

OCM meetings should support and align with a flexible agile project management approach that places an emphasis on stakeholders reaching the necessary levels of awareness, desire, knowledge, and ability before transitioning to the next release/iteration/sprint, as organizational outcomes are the result of individual change.

The State anticipates needing the following additional meetings:

| Type | Description / Purpose | Responsibility | Audience | Method | Frequency |
| --- | --- | --- | --- | --- | --- |
| Sponsor Status Meeting or Steering Committee | To discuss issues, change requests, issues, risks and overall status for the project that need to be known by Sponsors | Project Manager | Leadership Team | Group Meeting Email Project Storyboard Report | TBD |
| Project Management Status Report (Project Storyboard) | To relay ongoing project status, list open issues, risks, milestones and accomplishments since last status | Project Manager | Project Sponsors Business Owner Stakeholders | PPM Tool Status Report is accessed online or is distributed by the PM via email | TBD |
| Stage Exit Meeting | To discuss successful completion of the SUITE SEM Stages and to receive approval to proceed to the next stage | Project Manager | See Role and Responsibility List Project Manager Project Sponsors PMO Representative DTMB Sponsor(s) | Group Meeting | End of each SUITE SEM Stage |
| Project Team Status Meeting | To discuss issues, change requests, issues, risks and overall project status | Project Manager | Project Team Members | Group Meeting Email | Weekly |
| Project Technical Team Meeting | To discuss technical issues and activities for the project. | Technical Lead | Developers Project Manager (as needed) Other Resources (as needed) | Group Meeting Email | As needed |
| Agile Scrum – Stand-up | To Discuss: - What I did completed yesterday - What I am plan on completing today - What are my roadblocks | Scrum Master | Project Team Members (technical and sponsors) | Brief stand-up meeting | Daily |

All meetings will be detailed in the Suite Project Management Plan.

Bidder must describe how they will meet the meeting requirements set forth above and note any exceptions for successful implementation and ongoing support of the Solution. BIDDER RESPONSE: See KL&A’s response below in blue text. If Bidder has an alternative planned approach for project meetings provide details, including purpose, roles and responsibilities, and proposed frequency. BIDDER RESPONSE: See KL&A’s response below in blue text.

### Bidder Response to Meetings

Collaboration and transparency are core tenants of KL&A’s methodology.  We will conduct several types of meetings throughout the project, as described in Table 4, below.  KL&A will work with MDHHS and DTMB to establish a time and place for these meetings.  We can host them virtually, on-site at our Okemos office, or at a State building.

Table 4. Meetings KL&A will Regularly Conduct Throughout the Project

| Meeting Types | Purpose | Frequency | Attendees |
| --- | --- | --- | --- |
| Kickoff meeting | To bring together project stakeholders to review and agree-upon approach, work breakdown structure, schedule, milestones, deliverables, known risks and issues, mitigation strategies, escalation protocols, change control processes, and formats and frequency for various reports and communications. | Once at the beginning of the project | Stakeholders to be identified during contract negotiation |
| Discovery/joint application design sessions (JADs) | To bring together applicable stakeholders for validating and elaborating requirements and collaboratively designing the user interface. JADs are scheduled as needed. | As needed, throughout the project | Stakeholders to be identified during contract negotiation and/or kickoff meeting |
| Sprint planning sessions | To collaboratively plan the work that will be completed in the sprint. Work is pulled off the top of the prioritized Product Backlog. | Once per sprint | KL&A development team and MDHHS product owner(s) |
| Sprint review/demo sessions | To demonstrate new functionality developed in the sprint, gaining MDHHS feedback before the functionality is migrated to the QA or testing environment. | Once per sprint | KL&A development team and identified MDHHS stakeholders |
| Daily scrums | For each team member to report what they did yesterday, what they are doing today, and any impediments they are experiencing. This serves forward momentum and fast resolution of impediments. | Daily | KL&A development team |
| Sprint retrospectives | To discuss what went well and what did not go well. The team collaboratively decides on action plans to correct or avoid identified problems and sets norms based on previous action plans that were effective. This continuous reflection improves team cohesiveness and velocity. | End of each sprint | KL&A development team |
| UAT kickoff sessions | To clarify what is being tested and by whom and to answer any questions UAT testers may have. | Before each sprint UAT cycle and to release UAT | KL&A test manager & identified MDHHS UAT testers |
| Defect triage sessions | To review defects reported during UAT or production use for verifying impact, categorizing defect classification, and prioritizing their position in the product backlog per the MDHHS product owner’s wishes. | Several times per week during UAT cycles | KL&A test manager and MDHHS product owner(s) |
| OCM meetings | To work with applicable MDHHS and DTMB project stakeholders to gather the various information needed to assemble the OCM strategy and plan. | As needed, throughout the project | KL&A OCM lead, KL&A OCM support team, State OCM team, and any other identified MDHHS and DTMB stakeholders |
| Weekly OCM meetings | To work with the State OCM team to: Identify, review, and schedule OCM-specific tasks and activities Evaluate stakeholder and user engagement Identify any risks and issues with the planned approach | Weekly | KL&A OCM lead, State OCM team, and any other identified MDHHS and DTMB stakeholders |
| Weekly status meetings | To review project status, work completed, upcoming work, risks and issues, and any other topic requiring MDHHS and DTMB’s attention. | Weekly | KL&A project manager and identified MDHHS and DTMB stakeholders |
| Monthly status meetings | To review: Maintenance release planning and the defects to be included in the next scheduled maintenance releases; Completed defects since the last meeting; Progress of any new development contracted during the maintenance period; and Service levels for compliance with Service Level Agreement. | Monthly after go-live | KL&A project manager and identified MDHHS and DTMB stakeholders |
| Sponsor meetings | To review project status, change requests, risks, issues, and any other topic requiring the project sponsor's attention. | As needed | KL&A project manager and identified MDHHS and DTMB stakeholders |
| Ad hoc meetings | To discuss any issue requiring collaboration between one or more parties. | As needed | KL&A project manager and/or KL&A OCM lead, and applicable parties from MDHHS or DTMB |

KL&A will include a comprehensive Communication Plan in the Project Management Plan deliverable that identifies when, where, and who is to participate in each type of meeting.

PROJECT CONTROL & REPORTS

Once the Project Kick-Off meeting has occurred, the Contractor Project Manager will monitor project implementation progress and report on a weekly basis to the State’s Project Manager the following:

Progress to complete milestones, comparing forecasted completion dates to planned and actual completion dates

Accomplishments during the reporting period, what was worked on and what was completed during the current reporting period

Indicate the number of hours expended during the past week, and the cumulative total to date for the project.  Also, state whether the remaining hours are sufficient to complete the project

Tasks planned for the next reporting period

Identify any existing issues which are impacting the project and the steps being taken to address those issues

Identify any new risks and describe progress in mitigating high impact/high probability risks previously identified

Indicate the amount of funds expended during the current reporting period, and the cumulative total to date for the project.

Bidder must describe specific reports the Contractor will provide after contract execution and during the lifecycle of the contract, including all required scheduled reporting and details around the how and when metrics are captured/validated. See KL&A’s response below in blue text.

### Bidder Response to Project Control & Reports

After the project kickoff, regular meetings will begin as described in “Bidder Response to Meetings,” beginning on page 107.  Weekly status meetings will transpire in which the KL&A project manager will report the following:

Progress to complete milestones, comparing forecasted completion dates to planned and actual completion dates

Accomplishments during the reporting period, what was worked on and what was completed during the reporting period

Number of hours expended during the past week, the cumulative total hours to date for the project, and whether the remaining hours are sufficient to complete the project

Tasks planned for the next reporting period

Existing issues that are impacting the project and the steps being taken to address those issues

New risks and progress in mitigating high-impact/high-probability risks previously identified

Funds expended during the current reporting period and the cumulative total spent to date for the project

The KL&A PM will develop the weekly status report based on metric data tracked in the following applications:

Microsoft Project—KL&A uses Microsoft Project to track actual milestone delivery against planned timelines.

Jira—we use Jira to track the product backlog, sprint progress, team velocity, test cycle progress, application defects and resolutions, and enhancement requests.  It provides all the metrics necessary for verifying that KL&A is meeting the required service levels.  For example, it can show how many defects were opened in a given period, how long between the time a defect was opened and when the first response notes were entered, and when the defect was repaired, tested, migrated, and closed.  Please note that in addition to status reports, project stakeholders can log into Jira any time of the day or night to see any of this information.

Risk and issue tracking logs—KL&A uses an internal Project Portfolio Management (PPM) tool for tracking risks/mitigation strategies and project issues/resolutions and we will work with the DTMB project manager to ensure that risks and issues are also entered into the State’s PPM tool.  This system provides all the necessary metrics for reporting project performance and adherence to quality assurance practices.

The monthly status report that will begin after go-live will be maintenance-oriented, reporting the progress and contents of maintenance releases, planning for upcoming releases, and service-level metrics such as the timeliness of defect resolution and defect counts by classification.  All this information will come from Jira.

The format of each report type will be reviewed at the kickoff meeting to gain MDHHS and DTMB approval and will be used throughout the project.  The KL&A PM will ensure that the reporting requirements are captured in the Project Management Plan deliverable.

OCM CONTROL & REPORTS

Once the Project Kick-Off meeting has occurred, the Contractor OCM Lead will monitor user engagement progress and report on a weekly basis to the State’s OCM Lead the following:

Progress to complete milestones, comparing forecasted completion dates to planned and actual completion dates

Accomplishments during the reporting period, what was worked on and what was completed during the current reporting period

Identify any existing issues which are impacting the project and the steps being taken to address those issues

Identify any new risks and describe progress in mitigating high impact/high probability risks previously identified

Bidder must describe specific OCM reports the Contractor will provide after contract execution and during the lifecycle of the contract, including all required scheduled reporting and details around the how and when metrics are captured/validated.
BIDDER RESPONSE:

See our response below in blue text:

### Bidder Response to OCM Control & Reports

After the project kickoff, regular meetings will begin as described in “Bidder Response to Meetings,” beginning on page 107.  Weekly status meetings will transpire in which the KL&A OCM Lead will report the following:

Progress to complete milestones, comparing forecasted completion dates to planned and actual completion dates

Accomplishments during the reporting period, what was worked on and what was completed during the reporting period

Existing issues that are impacting the project and the steps being taken to address those issues

New risks and progress in mitigating high-impact/high-probability risks previously identified

The KL&A OCM lead will develop the weekly status report based on metric data tracked in the following applications:

Microsoft Project—KL&A uses Microsoft Project to track actual milestone delivery against planned timelines.

Risk and issue tracking logs—KL&A uses an internal Project Portfolio Management (PPM) tool for tracking risks/mitigation strategies and project issues/resolutions and we will work with the DTMB project manager to ensure that risks and issues are also entered into the State’s PPM tool.  This system provides all the necessary metrics for reporting project performance and adherence to quality assurance practices.

In addition to weekly risks and issue tracking logs, the OCM lead will conduct surveys and focus groups to assess the achievement of OCM milestones by conducting strategic surveys to measure the response to change activities at five points in the project/change timeline:

After First Communication

After Manager Coaching

After Training

After Go-Live

After Celebrating Success

This milestone-based report will provide insight into any change barrier points and provide the opportunity to chart the responses to measure effectiveness and determine how best to provide mitigation activities.

The format of each report type will be reviewed at the kickoff meeting to gain MDHHS and DTMB approval and will be used throughout the project.  The KL&A OCM lead will ensure that the reporting requirements are captured in the Project Management Plan deliverable.

PROJECT MANAGEMENT

The Contractor Project Manager will be responsible for maintaining a project schedule (or approved alternative) identifying tasks, durations, forecasted dates and resources – both Contractor and State - required to meet the timeframes as agreed to by both parties.

Changes to scope, schedule or cost must be addressed through a formal change request process with the State and the Contractor to ensure understanding, agreement and approval of authorized parties to the change and clearly identify the impact to the overall project.

The State will be following an Agile methodology for this project.  The Contractor must also follow an Agile methodology for this project.

SUITE Documentation

In managing its obligation to meet the above milestones and deliverables, the Contractor is required to utilize the applicable State Unified Information Technology Environment (SUITE) methodologies, or an equivalent methodology proposed by the Contractor.

SUITE’s primary goal is the delivery of on-time, on-budget, quality systems that meet customer expectations.  SUITE is based on industry best practices, including those identified in the Project Management Institute’s PMBoK and the Capability Maturity Model Integration for Development.  It was designed and implemented to standardize methodologies, processes, procedures, training, and tools for project management and systems development lifecycle management.  It offers guidance for efficient, effective improvement across multiple process disciplines in the organization, improvements to best practices incorporated from earlier models, and a common, integrated vision of improvement for all project and system related elements.

While applying the SUITE framework through its methodologies is required, SUITE was not designed to add layers of complexity to project execution. There should be no additional costs from the Contractor, since it is expected that they are already following industry best practices which are at least similar to those that form SUITE’s foundation.

SUITE’s companion templates are used to document project progress or deliverables. In some cases, Contractors may have in place their own set of templates for similar use. Because SUITE can be tailored to fit specific projects, project teams and State project managers may decide to use the Contractor’s provided templates, as long as they demonstrate fulfillment of the SUITE methodologies.

The Bidder is required to review http://www.michigan.gov/suite and demonstrate how each PMM/SEM requirement will be met. Bidders wishing to use their own documents must submit an example of the document that will be substituted. If the Bidder deems a document to be non-applicable, please provide reasons for the determination. The State reserves the right to give final approval of substituted documents and items marked as non-applicable. BIDDER RESPONSE: Refer to “Bidder Response to SUITE Documentation,” on page 114.

The Bidder must describe and provide details how they will meet the requirements of an Agile implementation. BIDDER RESPONSE: Refer to “Bidder Response to Agile Methodology,” on page 115.

### Bidder Response to SUITE Documentation

KL&A has reviewed http://www.michigan.gov/suite and intends to use an Agile approach, Scrum, that adheres to the State of Michigan SUITE Agile Process Guide.  Having developed many systems for the State of Michigan, KL&A is intimately familiar with SUITE.  We have successfully demonstrated our ability to create and maintain standard SUITE PMM and SEM documentation to support our Agile software development and implementation activities throughout all our State of Michigan projects, including those highlighted in the Vendor Questions Worksheet.

For the MIDASH Solution, KL&A will produce the following SUITE PMM and SEM document deliverables:

Project Charter (PMM-0101)

Project Management Plan (PMM-0102)

Project Status Reports, Project Change Requests, Issue and Risk Logs

Project Closure Report (PMM-0104)

Agile Product Backlog

Maintenance Plan (SEM-0301)

Software Configuration Management Plan (SEM-0302)

Requirements Traceability Matrix (SEM-0401)

Requirements Specification (SEM-0402)

Functional Design Document (SEM-0501)

System Design Document (SEM-0604)

Test Plan (SEM-0602)

Test Cases (SEM-0606)

Test Closure Report (SEM-0607)

Data Migration and Conversion Plan (SEM-0601)

Transition Plan (SEM-0701)

Installation Plan (SEM-0702)

Training Plan (SEM-0703)

Sprint Review and Approvals (SEM-0185)

### Bidder Response to Agile Methodology

KL&A is a recognized leader in the development and implementation of software applications, as well as the transformation of legacy systems into new technologies.  We provide full software development lifecycle (SDLC) services, using the Scrum development framework.  The Scrum framework employs iterative development cycles, called sprints, with the goal of getting functional software in the hands of users within weeks or months, rather than years.  Sprints are generally two weeks long but may be adjusted based on the State’s needs.  Each sprint encompasses all phases of the SDLC: requirements analysis/prioritization, design, development, testing, and release.

Figure 5. Illustration for Agile Scrum Process

Major benefits of Scrum include:

Functioning software at the end of each sprint, with which users can interact and test.  Feedback can be acted upon in the next sprint, ensuring that each function fully satisfies our clients’ business needs and meets their users’ expectations.

The ability to re-prioritize work as development occurs.  In the ever-changing world of enterprise and government regulations, priorities may shift for a variety of reasons.  Scrum provides the flexibility to assess and modify priorities at the beginning of each sprint.

Incremental testing that eliminates long test cycles before implementation and minimizes the risk of defects reaching end-users.  Testing of the newly developed features, as well as system integration testing, occurs at the end of each sprint.

Reduced need for formal training.  Business users receive product demonstrations before a feature is released; they test the feature in a user-acceptance test (UAT) cycle; and they can use the feature, while other features are being developed.  When the fully functional system is completed, the users are already familiar with all features implemented throughout the preceding iterations of development.

Figure 6. KL&A Associates Conducting a Collaborative Planning Session

KL&A believes that collaboration with our clients is the key to developing outstanding applications that exceed expectations.  Every step of the way, from assessment, planning, and design, through testing, implementation, and training, we involve our clients.  Throughout the project, we conduct requirements validation and elaboration workshops and joint application design sessions with business users, subject matter experts, and other project stakeholders.  These activities occur at the beginning of the project to validate or define the scope of the project and to develop a list of high-level requirements, referred to as the “product backlog.”  We also conduct these collaborative sessions at the beginning of each sprint to define the work that will be completed in the sprint and to clarify how the design will meet the selected requirements.

Toward the end of each sprint, we conduct product demonstrations of new or modified functionality to elicit feedback that can be implemented before the release of the sprint.  We thoroughly test the new or enhanced features and the system to ensure quality, after which we facilitate UAT to ensure that the features meet business needs.  We also provide end-user manuals and on-site training.

Throughout the project, we develop a variety of project artifacts to communicate and document the project scope, design, progress, and completion.  These artifacts typically include:

Business analysis documents, such as flow diagrams of existing business processes and proposed re-engineered processes, data definitions, data mapping crosswalks, UML diagrams, vision documents, screen mockups, and requirements specifications;

Project planning documents, such as project charters, project management plans, project schedules, work breakdown structures, status reports, and risk reports and mitigation plans;

Development documents, such as security and architecture assessments, and system, interface, and functional designs;

Testing/quality assurance documents, such as comprehensive test plans, test cases, test results, and traceability matrices;

End-user documents, such as user guides, system administration guides, training plans, and training materials; and

Project closeout documents, such as implementation plans and transition plans.

The following sub-sections provide a clear picture of how KL&A intends to execute this project to the satisfaction of the MDHHS.

#### Sprint Zero

Sprint zero begins after the project kickoff and encompasses project initiation, planning, requirements validation and elaboration, environment provisioning, and initial application design phases.  At the beginning of sprint zero, KL&A will meet with project stakeholders from MDHHS and DTMB to gather the necessary information to produce a Project Charter and a Project Management Plan.  The initiation portion of sprint zero will include the following activities:

Establishing project communication and status reporting guidelines.

Performing an initial risk and issues assessment, agreeing upon mitigation strategies, and defining the agreed-upon risk and issue tracking tool.

Validating the business, functional, and technical requirements provided in the RFP# 220000001798.  KL&A will conduct discovery sessions with key stakeholders and subject matter experts to ensure that we have a complete and valid list of requirements.

Walking through the WBS and project schedule to verify all parties agree with the project dates, timelines, milestones, and deliverables.

Solidifying change management procedures.

Working with DTMB to complete the SSP process and earn security accreditation.

Requirement elaboration and application design also begin during sprint zero and continues throughout the project.  The KL&A project team will facilitate discovery and joint application design (JAD) sessions with business users and other subject matter experts to clarify business rules and processes, gather input for user-interface design, and other information necessary to decompose the requirements into user epics and user stories.  The team will also work collaboratively to define acceptance criteria in each user story that will drive testing activities.

This decomposition happens in Jira so that the user epics and user stories can be linked to the business, functional, and technical requirements, beginning the traceability that will ultimately show that each requirement has been developed, tested, and accepted by MDHHS users.  The project team will:

Decompose the highest-priority user epics into user stories to prepare for the first sprint planning sessions.

Develop the initial System Design, Enterprise Architecture Security Assessment (EASA), and the System Security Plan.

Develop the initial Functional Design.

Develop a high-level Test Plan that specifies the types of testing to be performed, who will do the testing, when, in which environment, etc.

The iterative nature of the Scrum approach requires these activities to be continuously performed throughout the project and the corresponding deliverables to be updated with each sprint.

#### Requirements Validation Methodology

In RFP# 220000001798, MDHHS provided a substantial list of requirements that allowed KL&A’s technical team to craft an efficient solution and determine a fixed-price cost.  However, some requirements may be missing; some requirements may no longer be valid by the time the project begins; others may require clarification and additional detail.

KL&A uses the Scrum framework of the Agile methodology to deliver software iteratively.  This process demands an iterative approach to requirements validation, thus providing the development team with enough information to work continuously while providing MDHHS with the agility to change priorities as the project progresses.

The project will begin with a discovery and planning phase called sprint zero in which the team will work with MDHHS to confirm/plan a release schedule that identifies, at a high level, when specific functionality will be released.  Release planning will consider MDHHS’s business priorities, as well as structural dependencies necessary to develop code in the most efficient manner.

The release schedule will drive the order of the requirements validation and elaboration process.  Once the release schedule is decided, the business and quality analysts will begin the requirements validation and elaboration process on the highest-priority requirements.  They will continue this process throughout the project.  That is, they will work on a group of selected requirements, generating the detail needed for development activities to commence.  They continue the process, working on block after block of requirements until all the requirements have been validated and elaborated.

Figure 7, below, depicts our requirements validation and elaboration process, which comprises a series of meetings we call joint application design (JAD) sessions.

Figure 7. Requirement Validation & Elaboration Process

##### Discovery JADs

The first JADs are discovery sessions in which the team will work with MDHHS business users and other stakeholders to review workflows and map requirements to those workflows to identify gaps and opportunities for automation.  The team begins loading all the business, functional and technical requirements into Jira, our product backlog, sprint planning and management, and defect tracking tool.  Jira provides functionality for:

Reviewing and approving requirements, epics, and user stories;

Tracking development and testing activities;

Tracking defects; and

Linking all these elements together to provide detailed traceability information.

##### Functional JADs

Once the team has validated business, functional, and technical requirements for a block of functionality, they move into functional JADs where the team works collaboratively with business users to break the requirements down into epics and user stories.  For example:

A Business Requirement: The system shall allow users to manage contacts.

The Epic: As a user with the correct permission, I need a user interface to manage contacts so that I can ensure up-to-date information is available for all users who are working on cases.

User Story 1: As a user with the appropriate permissions, I need the ability to create a contact record, so that I can attach it to a case.

User Story 2: As a user with the appropriate permissions, I need the ability to edit a contact’s record, so that I can correct inaccurate or outdated information.

User Story 3: As a user with the appropriate permissions, I need the ability to delete a contact record that is not associated with an existing case, so that I can remove an incorrect record.

The team will also create screen mockups to facilitate the functional JADs that allow users to see the functional design and provide feedback.  Mockups will be updated to reflect feedback and they will be associated with the applicable user stories to provide the developers with a clear vision of the required functionality.

##### Technical JADs

The team moves on to technical JADs in which they capture field specifications and acceptance criteria.  The acceptance criteria follow the pattern of given, when, and then, where:

Given communicates conditions necessary for testing the functionality;

When communicates specific actions the user will take; and

Then communicates the expected result of each action.

Acceptance criteria communicate to the development team all the details necessary to build the functionality and they serve as the basis for all testing activities.  This approach has yielded high-quality code with very low defect counts.

##### User Story Review and Approval Process

KL&A will provide identified MDHHS stakeholders with access to Jira.  We use Jira to manage user story review and approval, among other project activities.  Figure 8, below, shows a sample User Story Review Board in Jira.

Figure 8. Jira User Story Review Board

As the team is working through the JADs, they will begin adding user stories that will appear in the Draft column of the project’s Story Review Board (Figure 8).  Each story will contain a link to the applicable business or functional requirement(s).

Once a user story is completed, the authoring BA will move it to the Internal Review column.  Another KL&A BA will peer-review the story to verify that it complies with our established best practices, ensuring that it is clear and complete.  If there are any issues with the story, the reviewer will work with the authoring BA to get the issues remedied.

When the user story passes all internal quality checks, the peer reviewer will move it to the Ready for SOM Review column.  During a specified review period, an identified MDHHS stakeholder will move the story to the In Review column while they are reviewing it.  This serves to communicate to all stakeholders the progress of the review for every story.  When they are done reviewing, they will take one of three actions:

If the MDHHS reviewer approves the story and all related artifacts (e.g., mockups, field specifications, business rules, etc.), they will move it to the Approved column.

If the MDHHS reviewer wants minor modifications, they will move it to the Approved with Comments column.  The authoring BA will work with the person who made the comments to get the story updated.  The revised story will be collaboratively reviewed in a sprint planning session, then moved to the Approved column by the MDHHS product owner.

If the MDHHS reviewer feels the story misses the mark completely, they will add comments and move the story back to the Draft column.  Due to the iterative and collaborative JAD process, this is very unusual, but KL&A provides a mechanism for this situation.

Once the stories are approved, they are officially in the product backlog, ready and waiting to be added to a development sprint.

#### Application Development

The first development sprint will commence on October 21, 2022.  For the development of the base application, KL&A is proposing 24, 10-day sprints to develop the requirements contained in RFP# 220000001798.  Each sprint executes as follows:

Backlog grooming—the product owner, an appointed MDHHS representative, will review the backlog to verify the highest-priority items are at the top of the list.

Sprint planning—the KL&A team will conduct a sprint planning session in which they select as many of the highest-priority user stories as can be developed in the two-week timeframe.

Development/testing—the developers begin work.  Daily, they record their progress in Jira, which displays real-time sprint burn-down charts that we can make available to MDHHS as needed.  The developers test their code before handing it off to the business/quality analyst (BA/QAs) for functional and system integration testing.  Testing in tandem with development allows for maximum compression of activities, resulting in faster delivery.

Sprint review/demo—toward the end of the sprint, the KL&A project team will conduct a sprint review meeting in which they demonstrate the new functionality developed during the sprint.  This provides an opportunity to field MDHHS feedback.  Feedback within the scope of the approved user story, depending upon the associated work, will either be acted upon before the end of the sprint or at the beginning of the next sprint.  Any feedback that requires an increase in scope or change to the originating requirement, will be deferred to the change control process for further evaluation by the appropriate parties.

User acceptance—after each sprint and before each release, the KL&A test coordinator will facilitate user-acceptance testing (UAT) based on the acceptance criteria captured in each user story.  Sprint UAT is focused on user stories, while release testing is more holistic, focusing on user epics and the ability to use all the functionality in the release to accomplish job functions.  Appointed MDHHS business users will perform UAT.  Testing will be executed on-site at MDHHS, in the KL&A-provided quality assurance test environment for sprint UAT and release UAT.  MDHHS testers will access the UAT test cases in Jira, where they can pass or fail the test cases and open defect tickets that are linked to the applicable test cases.  Jira provides traceability through a series of links from the test case to the user stories to the user epic to the original business, functional, and technical requirement, providing full traceability.  The KL&A test coordinator will work closely with the MDHHS test manager to monitor and manage testing efforts, with several defect triage meetings each week.

Test cases that are failed due to malfunctioning code, or code that does not meet the requirements, will generally be remedied in the next sprint based on the direction of the MDHHS test manager.  Any other feedback born from UAT will be evaluated for project impact and either added to the backlog or deferred to the change control process.

When all UAT test cases show a passed status, the release will be considered user accepted.

At the end of each sprint, the KL&A project team will also update all applicable deliverables, such as the functional and system design documents, user manuals, training materials, etc.

#### Implementation

KL&A will take an iterative approach to implementation.  We plan to release the core system functionality first, after which, in rapid succession, we will release migrated system functions and data.  For more detail, please refer to “Bidder Response to Milestones and Deliverables,” on page 140.

For each scheduled release that is user accepted, the KL&A team will work with eMichigan to gain approval for production release and will execute the DTMB Request for Change (RFC) process to deploy the MIDASH Solution release to production.

#### Testing

In addition to quality assurance practices that are designed to avoid creating defective code, KL&A has established comprehensive testing best practices that allow us to verify the proper functioning of code, as well as the satisfaction of the associated requirements before releasing the code to production.

We employ both automated and manual testing to strike a balance between efficiency and quality.

##### Automated Testing

KL&A follows a mature DevOps process that incorporates quality and continuous integration into the development process.  Unit test coverage of a system creates a foundation for verifying logical refactors or updates of the existing code base, as well as rejecting changesets when new features introduce incompatibility.  Depending on the technology stack of the system, unit tests are written in a variety of languages to properly cover the source code under test.

When a system has sufficient code coverage of unit tests, the DevOps pipeline for the system can then automatically run the complete test suite to ensure stability and regression of the system’s logical units and algorithms.  This will improve the overall quality of the system by flagging potential issues and preventing those changesets from getting deployed to an otherwise stable environment.

Unit test suites can be executed at various stages of a DevOps chain, including immediately upon commits of new changes, during the integration phase of all current functionality, at regularly scheduled intervals, and as part of final production builds.  Executing at multiple stages ensures code quality is maintained.

##### Manual Testing

KL&A builds testing into the process from the very beginning of the software development lifecycle.  During requirement validation and elaboration, our team will work with MDHHS stakeholders to develop clear and complete acceptance criteria for every user story, which will be reviewed and approved by MDHHS stakeholders.  The acceptance criteria will drive all testing activities.

As with all other aspects of Scrum, testing is also iterative.  KL&A’s business and quality analysts will perform functional and system testing for each sprint to ensure each user story functions properly and meets the defined acceptance criteria.

Once the KL&A team has completed testing, they will facilitate user-acceptance testing (UAT) of the functions developed during the sprint.  UAT cycles generally begin with a UAT kickoff meeting in which the KL&A test manager will go over the Test Plan with MDHHS-identified testers for the sprint cycle, ensuring everyone knows what they are testing, how to record defects, and when the testing cycle is to begin and end.  If a UAT tester finds an issue, they will open a defect ticket in Jira and link it to the applicable user story.  The ticket will go into the backlog for triage and prioritization.

The KL&A test manager will work with the appropriate MDHHS stakeholders several times a week to triage reported UAT defects.  This includes:

Working with the person who reported the issue to gather any additional information necessary to diagnose the problem;

Comparing the defect to the acceptance criteria to determine if it is in-scope or requires escalation to the change control process; and

Working with the MDHHS product owner to set the priority of the ticket, which will drive the resolution timeframe.

In addition to sprint UAT cycles, the team will facilitate release UAT cycles in which users will test at the epic level to validate blocks of functionality.  This test cycle allows users greater context to determine if the business requirement is satisfied by the group of user stories.  For example, during one sprint UAT cycle, a user might test the ability to add a customer contact; in the next UAT cycle, they might test the ability to merge duplicate contact records, and so forth.  In the release UAT, they would test all aspects of contact management to ensure they can handle all business scenarios with the supplied user interface.

KL&A intends to use a release cycle similar to the following illustration.  This cycle depicts four sprints per release, which may vary depending upon MDHHS’s needs and the amount of code required to achieve a minimum viable product.

Figure 9. Release Mechanics Illustration (Repeated for Each Release)

Toward the end of each two-week sprint, KL&A will demonstrate the new or updated functionality to identified MDHHS stakeholders.  Feedback will be mutually evaluated to determine when it should be acted upon.  Feedback that expands user story scope may require change control or the addition of a new user story.

At the end of each two-week sprint, after the product demonstration, the sprint code that is developed in the KL&A development environment will be promoted to the sprint UAT environment.  While MDHHS users are testing a given sprint, the development team will be working on the next sprint.  Any issues found during sprint UAT will be documented in Jira tickets and regularly triaged and prioritized for inclusion in a future sprint planning session; for example, sprint 1 issues will typically be fixed in sprint 3.  However, high-impact defects, such as those that block other testing activities will be resolved within the current sprint.

In Figure 9, above, four sprints make a release.  Though the release schedule may be different for the MDHHS MIDASH Initiative, it will be conceptually similar, so we will use this example to explain the mechanics of a release.  After the fourth sprint is pushed to UAT, the development team will take 5 days to fix any outstanding defects from sprints 1-3 and build the official UAT release.  Defects found in sprint 4 UAT will be fixed during the 15-day, formal UAT cycle in which all functionality is tested for final acceptance.  Since all functions developed over the preceding sprints are tested again, this formal user-acceptance testing also acts as a regression test, ensuring the proper functioning of all code developed over the previous sprints.  During this 15-day release UAT cycle, defects are repaired and re-tested immediately.  To ensure there is plenty of time to fully validate all functionality after any necessary repairs are made, the schedule will include 5 days for MDHHS to approve the UAT.  Once UAT is approved, KL&A will promote the code to the production environment.  Please note that KL&A will work with MDHHS to set a specific schedule of events.

KL&A will also work with eMichigan throughout the release cycle to ensure system designs are compliant with the eMichigan look-and-feel standards and ADA standards.  We will facilitate the eMichigan audit and approval during the 15-day release UAT cycle.

At the end of UAT, the KL&A test manager will make the necessary updates to the Requirement Traceability Matrix and the Test Closure Report (SEM-0607) for approval and sign-off on test activities, as well as to all end-user and system administrator documentation.

#### Closeout

After the final release, project closure activities will commence, and the project will transition to warranty.  During project closeout, final versions of all project deliverables that are iteratively maintained throughout the project will be submitted to MDHHS, in addition to a Project Closure Report (PMM-0104).  MDHHS will review the Project Closure Report, per the agreed-upon milestone review process which will be documented in the Project Management Plan.  If MDHHS requests updates, KL&A will incorporate the provided feedback and resubmit.  Once MDHHS feedback is incorporated, MDHHS will provide project closure approval in writing.

#### Warranty Period

KL&A will provide, free of charge, a 180-calendar day warranty period that begins after the final production release.  Warranty includes support and repair of production defects as prioritized by the MDHHS product owner.  Our warranty process is very similar to our maintenance and support process, except for warranty work is completed by the project team, instead of the maintenance team.

#### Maintenance and Support

KL&A believes the State is expecting the maintenance and support phase to start at the end of the warranty period and to be optionally renewed by the State on an annual basis.  For more details about the way KL&A administers maintenance and support, refer to “Bidder Response to Additional Products and Services,” on page 82.

#### Tools

KL&A uses a robust set of tools that have proved to maximize efficiency and customer satisfaction, including:

Table 5. KL&A's SDLC Tools

| Tool | Purpose/Description |
| --- | --- |
| Balsamiq Mockups | To quickly create user-interface designs that aid JAD activities. Mockups can be interactive to provide a sense of navigation. |
| Microsoft Visio | - To capture business processes in functional flowcharts (swim lane diagrams). |
| Microsoft Office Professional | For spreadsheet, document, and presentation development in commonly accepted formats. MS Office will be used by the PM and BAs to provide the document deliverables and weekly status reports as required in solicitation RFP# 220000001798. |
| Microsoft Project | To develop the WBS and comprehensive project schedule and to track project progress, including actual versus planned work. |
| Jira | A web-based tool used to: Manage the product backlog; Plan and manage sprints; Plan and manage testing activities; Track defects and repairs; Track enhancement requests; Maintain traceability information from requirements, through user epics and user stories to test cases and UAT defects; and Produce project status, test results, and service-level reports. KL&A will provide identified MDHHS stakeholders with access to Jira. |

Though these are KL&A’s preferred tools, if the State requires the use of other tools, KL&A will comply.  Our team of professionals has experience with a variety of SDLC tools.

#### Deliverable Review Process

Because some deliverables must be approved before development can commence, timely feedback and approval of deliverables can be critical to ensuring project schedule dates are met.  KL&A proposes the following review process for each formal deliverable that is identified in the project schedule.  Following the flow diagram is a detailed description of each step.

Figure 10. Milestone/Deliverable Review Process Flow

The deliverable review process flows as follows:

| Step | Description |
| --- | --- |
| 1.0 & 1.1 | When the deliverable is ready for review, KL&A will initiate the review process. |
| 2.0 & 2.1 | The reviewers have 5, 10, or 15 days, depending upon the length of the deliverable, to review the deliverable and produce a list of comments that are recorded in a Deliverable Comment Form (DCF). If there are multiple reviewers, a designated person will consolidate individual DCFs into a single DCF for ease of processing. |
| 3.0 & 3.1 | KL&A will review the comments and provide an initial disposition (Yes/No/Partial) for each comment. |
| 3.2 | KL&A will facilitate a comment review session with reviewers to verify accepted comments and clarify rejected or partially accepted comments. |
| 3.3 & 3.4 | KL&A will incorporate agreed-upon comments to produce the next revision of the deliverable. |
| 4.0 | The reviewer will review the updated portions of the deliverable to confirm that the agreed-upon changes were implemented as expected. |
| 4.1 & 4.2 | The reviewer will either: - Accept the revised deliverable—no further revisions are required - Reject the revised deliverable and supply comments (2.1) explaining the reason for rejection. The flow repeats from 2.1 through 4.2 until a final, approved revision is achieved. |
| 4.3 | Once a final approved revision is achieved, MDHHS will provide a Deliverable Acceptance Letter that KL&A will submit with its invoices. |

To capture and track deliverable review comments, the responses to the review comments, and the resolutions for accepted comments, the Deliverable Comment Form (DCF) contains agreed-upon fields.  Figure 11, below, is a preliminary DCF.

Figure 11. Deliverable Comment Form (DCF)

#### Change Control

The purpose of a Change Control Plan is to describe the process involved in identifying, escalating, and managing project changes.  A project change is defined as something that is outside the documented and approved project scope or is a change to project requirements, project schedule, or project cost (including resource effort).  A project change requires approval for additional resources, funding, or modifications to the project schedule.  The change control process defines how to handle project changes that present either a negative or positive impact on deliverables, schedule, budget, and/or resources.  The State of Michigan’s enterprise PPM tool, utilized by the State PM, is the repository for all project changes.

##### Change Control Roles and Responsibilities

Project Sponsor

The project sponsor does not directly participate in change control activities but serves as a point of escalation as required.  The project sponsor has sole decision-making authority to approve changes to the total project budget, schedule, deliverables, and resources.

KL&A Project Manager

The KL&A project manager is responsible for bringing change requests to the change control board (CCB) for its review and decision.  Upon approval of a change request, the KL&A project manager becomes responsible for overseeing the change and making appropriate modifications to appropriate project artifacts.

Change Control Board

The CCB meets regularly to review and approve or reject proposed project changes.  The KL&A project manager may convene a special session for reviewing a specific change request(s) as required.  The makeup and formality of the CCB will depend on the size and complexity of the project.

Project Team Members

Project team members are empowered to initiate change requests.  Members serve as subject matter experts and are responsible for analyzing, documenting, and estimating the impacts of change requests on schedule, budget, resources, scope, and quality.

##### Change Control Governance

This section discusses the objectives of the change management process, the criteria for CCB review, and a detailed description of the process.

###### Objectives of the Change Management Process

Accurately document and track all project issues, risks, and change requests.  Change requests often originate as unresolved issues or unmitigated risks.

Ensure review and action on change requests by the CCB.

Communicate decisions/resolutions to the appropriate stakeholders.

###### Criteria for Review at CCB Meetings

If any of the following events occur, the item should be brought forward for discussion at the next regularly scheduled or special CCB meeting:

Changes to the approved Project Charter or Project Management Plan;

Changes or additions to milestones in the project schedule;

Changes to contract deliverables;

Changes to approved requirements or functional designs; and

Increases in costs, including resource effort hours.

##### Process Description

Project changes are proposed in the form of a change request that is entered into the State’s enterprise PPM tool.  Change requests are started by a change request initiator who provides as much information as possible to document and initiate the request.  The change request contains information such as a brief description, impact, alternatives, detailed description, final recommendation, and other pertinent information.  The KL&A project manager (PM) will assign a change request person responsible as the “owner” of the change request, who is responsible for gathering project impacts regarding project costs and the project schedule.

The change request person responsible researches the requirements and impact of the change.  This information is reviewed by the KL&A PM and MDHHS subject matter experts to assess the change request feasibility and identify potential issues.  This information will be communicated and discussed at the CCB meeting in which a decision will be made to approve or reject the change.  Upon CCB approval, the KL&A PM will incorporate the change(s) into the existing schedule for tracking and management.  The KL&A PM will also document the status of the change request and maintain a log of all decisions.  Note that the State’s enterprise PPM tool, utilized by the State PM, will support the change request process.

##### Steps and Actions

| Step | Action | Responsibility / Agent |
| --- | --- | --- |
| 1. | Identify and document change requests | Change request initiator |
| 2. | Assign change request person responsible | KL&A PM |
| 3. | Collect and document project impacts, including changes to costs and schedule | Change request person responsible |
| 4. | Validate that the change request is in the State’s enterprise PPM tool | State PM |
| 5. | Review change request details for feasibility | KL&A PM and State PM |
| 6. | Facilitate CCB review / make decisions | KL&A PM/CCB members |
| 7. | Communicate decision and closure | KL&A PM |
| 8. | Update appropriate schedules and documents | KL&A PM |
| 9. | Update status and close the change request in the PPM tool | State PM |

##### Capturing and Monitoring Project Changes

The KL&A PM and CCB members will strive to limit project changes, always keeping in mind that the quality and relevance of deliverables are key elements of success.  As indicated above, the State’s enterprise PPM tool is the repository for all project changes.

Note that the DTMB Enterprise Change Control Process must be followed for all changes to any application production environment.  Details of this process are outside the scope of this document.  Please refer to DTMB Technical Standard 1370.00.01.

##### Communicating Project Changes

CCB meeting minutes, including decisions related to change requests, will be circulated to project sponsors and State executives.  Project team members will be notified by email regarding the disposition of change requests.

Software Development Documentation

In addition to documentation required as part of the State SEM and PMM (Systems Engineering Methodology and Project Management Methodology), any software developed utilizing an agile methodology must include the following at the end of each sprint or for waterfall methodology at the end of each development iteration as part of the SEM-0185 (Sprint or Project Increment Release Review and Approval):

A formal demonstration of the work completed during the sprint. The demonstration will be accompanied by a written narrative describing which user stories were completed in the sprint as well as the remaining user stories to be included in the product.

A completed Quality Assessment Surveillance Plan QASP as described by 18f. (https://derisking-guide.18f.gov/qasp/)  The QASP will include at a minimum:

| Surveillance Metric | Performance Standard | Acceptance Standard | Method of Assessment |
| --- | --- | --- | --- |
| Code Coverage | Code delivered under the order must have substantial test code coverage and a clean code base. | Minimum of 75% test coverage of all code | Combination of manual review and automated testing |
| Properly Styled Code | GSA 18F Front-End Guide For SOM application developed after 5/31/2018 SOM Digital Standards Digital Guidelines | 0 linting errors and 0 warnings | Combination of manual review and automated testing |
| Accessibility | Web Content Accessibility Guidelines 2.0 standards Michigan ADA Standards | 0 errors reported using an automated scanner, and 0 errors reported in manual testing | Combination of manual review and automated testing |
| Deployed | Code must successfully build and deploy into staging environment | Successful build based upon agreed processes | Combination of manual review and automated testing |
| Documented | All dependencies are listed and the licenses are documented. Major functionality in the software/source code is documented. Individual methods are documented inline using comments that permit the use of documentation-generation tools. A system diagram is provided | Combination of manual review and automated testing, if available | Manual review |
| Security | OWASP Application Security Verification Standard 4.0, Level 2 | Code submitted must be free of medium- and high-level static and dynamic security vulnerabilities | Contractor to utilize state approved static application scanning tool (App Scan) and also for Apex dynamic scanning. Pilot: This scan will be done after hardening sprints. |
| User Research | Usability testing and other user research methods must be conducted at regular intervals throughout the development process (not just at the beginning or end) | Artifacts from usability testing and/or other research methods with end users are available at the end of every applicable sprint, in accordance with the Contractor’s research plan | Manual review |

Bidder must describe how they will meet the requirements set forth above and note any exceptions for successful implementation and ongoing support of the Solution.
BIDDER RESPONSE:

See our response below in blue text.

### Bidder Response to Software Development Documentation

KL&A’s approach to software solutions development follows a disciplined Agile approach to the Agile methodology, including several key rituals and practices that are employed for all engagements.  These practices include, at a minimum, Sprint Planning and Sprint Demonstration for every development sprint cycle.  Figure 12, below, shows a complete visualization of KL&A’s Agile Process.

Figure 12. Agile/Scrum Process

KL&A will involve the necessary parties from the development, business analysis, and quality assurance teams, as well as identified key stakeholders and product owners from DHSP and DTMB in the Sprint Planning and Sprint Demonstration meetings.

A Spring Planning meeting will occur at the beginning of every Sprint and involve collaboratively deciding which user stories will be developed within the Sprint.  The appointed DHSP product owner will work with the KL&A team to prioritize the backlog of work.  Being able to review and adjust priorities every two weeks provides agility to easily accommodate changing business needs.

At the end of every Sprint, the KL&A team will demonstrate the functionality developed during the Sprint, allowing us to gather immediate feedback.  The KL&A team will also review the sprint boards and backlog to summarize the completed user stories and remaining backlog.  From the project’s tracking system, typically Jira, our team will generate progress reports that show information such as a summary of completed user stories, burndown charts that show Sprint velocity, and remaining work.

Outside of Sprint Planning and Sprint Demonstration, KL&A will provide routine updates to the solution’s Quality Assessment Surveillance Plan (QASP), indicating adherence to the performance and acceptance standards per metric activity, as well as the method in which each metric activity was performed.  The surveillance metrics will include, at a minimum, those indicated by the 18F de-risking guide and by KL&A’s internal standards.  Table 6, below explains how KL&A will apply and assess each 18F surveillance metric.  These metrics will be assessed and reported on in QASP format, as well as regularly by project and technical leadership in the form of recurring status touchpoints with State stakeholders and product owners.

Table 6. QASP 18F Surveillance Metrics

| Surveillance Metric | Application and Assessment Method |
| --- | --- |
| Code Coverage | KL&A’s solution development will employ a combination of written unit, automated end-to-end, and functional/manual testing to verify source code is adequately covered by test cases upon initial delivery of each build, as well as ensure future regression issues are caught and mitigated easily during Sprint activities. Code coverage will be verified upon successful check-in of code, build, and manual review of deployed system changes. KL&A will strive to meet 100% code coverage where applicable but recognizes not all code will always reach 100% coverage, especially when features are being developed across multiple user stories and sprints. To allow for this margin, KL&A will allow for no less than 75% coverage to be acceptable for a given user story and will continually attempt to increase coverage as the codebase grows and iterates over time. |
| Properly Styled Code | KL&A’s solution development will employ and enforce strict code-style tools and guidelines, such as TSLint and Prettier, to ensure that the developed source code is well organized, structured, and maintained. KL&A will reject any changesets that do not meet 100% code style guidelines, including zero reported errors and warnings upon every successful code check-in to the source code management (SCM) repository and build using continuous integration/continuous delivery (CI/CD) pipelines. All developer environments will include linting and code-style tools to ensure strict adherence at all times. In addition to KL&A’s development guidelines for code style and linting, the MIDASH Solution will adhere to all applicable 18F Frontend and SOM Digital Guidelines and Standards. |
| Accessibility | KL&A’s experience developing ADA-compliant applications and working with the State’s eMichigan group for approval of our designs provides us with a clear understanding of the State’s expectations, policies, and procedures for confirming level AA conformance to the base-level WCAG 2.0 (2008) standards. KL&A also incorporates additional success criteria for level AA in the published 2.1 (2018) and draft 2.2 (early 2021) versions of the WCAG. In addition to routine eMichigan reviews, KL&A’s solution will adhere to Web Content Accessibility 2.0 and Michigan’s ADA standards through the application of automated screen reading, scanning, and verification tooling reviewed by both KL&A’s functional and technical teams and the State of Michigan. |
| Deployed | KL&A’s solution will use automated continuous integration/continuous delivery (CI/CD) pipelines for building and deploying to each managed environment of the MIDASH Solution, including Sandbox, Development, UAT, Training, and Production—with Production requiring sign-off, RFC approval, and coordination with State staff. Each build, regardless of the target environment, will pass requisite test coverage, code style, accessibility, and security checks to be considered complete. Deployments will be facilitated by a combination of KL&A and DTMB staff, as dictated by administrative policies and procedures per environment and server classification. Completed deployments will be first validated by KL&A to ensure successful delivery before expecting DHSP to perform any subsequent validation or testing, depending on the environment and target activity. |
| Documentation | KL&A’s solution will employ a combination of custom-developed software and third-party libraries and dependencies. All third-party dependencies will be maintained by package management systems, such as npm and NuGet, and provide complete listings of all direct dependencies and sub-dependencies for routine review by State DTMB staff as necessary. If requisite dependencies require any form of license, KL&A will ensure proper licensing and renewal are documented and communicated to State partners. Dependencies and libraries aside, KL&A’s custom-developed software packages and source code, both manually written and auto-generated, will adhere to code style guidelines and best practices, including ample inline and class/file-level comments and documentation. Additionally, the MIDASH Solution will be fully documented in accordance and partnership with DTMB’s architects in the form of EASA network diagrams, system security plan (SSP) data flow and system diagrams, and site maps whenever networking or significant application changes are implemented. |
| Security | KL&A’s MIDASH Solution will adhere to all applicable security standards and guidelines set forth by DTMB’s Cybersecurity department, security architects, and established best practices. These will include, but not be limited to, the OWASP Application Security Verification Standard 4.0, Level 2, and any additional enforcements made by KL&A’s architecture and security teams. The MIDASH Solution’s source code will undergo frequent static and dynamic application security tests (SAST and DAST), utilizing DTMB’s designated scanning tools, such as IBM App Scan and Apex. Additionally, KL&A’s solution will be routinely scanned using server-level security scanning tools such as Tenable, AppDynamics, or Dynatrace based on DTMB’s preference and application of scanning technologies. KL&A will be responsible for participating in regular remediation and mitigation planning of any identified vulnerabilities and determining any false positives found during development to ensure there are no medium- or high-level issues present before and after UAT and Production deployments. |
| User Research | KL&A’s approach to solution development includes frequent usability studies and testing facilitated by UX/UI designers and business analysts from KL&A and key product owners from the State of Michigan. These studies may be performed as office visits with end-users or via collaborative discussions in joint application design (JAD) sessions that are held throughout the entire software development lifecycle (SDLC) of the engagement. Initial usability and performance metrics will be gathered and presented as baseline data in conjunction with subsequent metrics, following key implementation points to provide documented evidence that functionality is meeting or exceeding expectations as desired. |

Milestones/Deliverables for Implementation

The State’s proposed milestone schedule and associated deliverables are set forth below.

| Milestone Event | Associated Milestone Deliverable(s) | Schedule |
| --- | --- | --- |
| Project Planning | Project Kickoff | Contract Execution + 10 calendar days |
| Sprint Zero | Discovery | Contract Execution + 90 calendar days |
| Sprints & Releases | Development, Testing, Incremental Acceptances | Contract Execution + 15 calendar months |
| Final Release & Go-Live | Final Acceptance | Contract Execution + 15 calendar months |
| Post Production Warranty | Included in the cost of Solution. | Production + 180 calendar days |
| Production Support Services | Ongoing after Final Acceptance | Ongoing |

Bidder may propose alternative timeframes and deliverables, but Bidder must provide an explanation as to why the State’s schedule and associated deliverables is not feasible. BIDDER RESPONSE: See KL&A’s response below in blue text.

Bidder must provide a Work Breakdown Structure (WBS) that corresponds with the milestone dates set forth above (or with Bidder’s alternatively proposed schedule). The WBS must be detailed enough to identify all State and Contractor responsibilities. BIDDER RESPONSE: See KL&A’s response below in blue text.

Bidder must describe how they will meet the requirements set forth above and note any exceptions for successful implementation and ongoing support of the Solution. BIDDER RESPONSE: See KL&A’s response below in blue text.

### Bidder Response to Milestones and Deliverables

This section addresses each paragraph in the prompts above.  It explains the proposed timeline, work breakdown structure (WBS), and project schedule that we will use to ensure a successful project that meets MDHHS’s needs and is delivered on time and within budget.

#### Proposed Timeline

KL&A is proposing an alternative timeline in which the MIDASH Solution will be delivered in three (3) distinct phases:

Phase 1 - Discovery (Sprint Zero)

Phase 2 - Base Application

Phase 3 - Interfaces, Data Migration, and Decommission

Our preliminary WBS/project schedule, developed in Microsoft (MS) Project and based on a State of Michigan work calendar in which weekends and all defined State holidays are treated as non-working time, will begin on October 3, 2022.

The anticipated contract beginning date listed in the RFP falls on a Saturday, so we selected the following Monday to start the project.

The following figure provides an overview of our proposed implementation timeline:

Figure 13. Proposed Implementation Timeline

The project will start with a 20-day project initiation period in which the Project Charter will be produced and approved, and the project kickoff meeting will be held with key MDHHS and DTMB stakeholders.

Upon completion of the project kickoff meeting, Phase 1 – Sprint Zero will begin.  Project planning will commence, including the creation of the Project Management Plan, project schedule, SUITE tailoring, and preliminary versions of the OCM strategy and plan.

In parallel to the start of project planning, discovery and JAD sessions with MDHHS and DTMB subject matter experts will commence, in which the following activities will occur:

Requirements analysis and validation, including requirements gap analysis and report;

Preliminary release planning, and preliminary product backlog development;

State hosting environment provisioning, application scaling analysis, and validation; and

Creation of all preliminary SUITE system development deliverables.

Phase 2 will begin in parallel with phase 1 and will consist of twenty-four (24) development and test sprints for building the MIDASH Solution base application, integrating with MiLogin, completing the security accreditation process and obtaining the ATO, completing eMichigan reviews and ADA compliance, maintaining and updating SUITE system development deliverables, creating training materials and documentation, executing training and UAT, and performing production cutover activities.  The Phase 2 MIDASH Solution base application will go live on 12/19/23.

Phase 3 will begin in mid-June 2023 and will consist of eight (8) monthly system releases.  Each release will comprise integration, data migration/conversion, and decommissioning tasks.

This phase will begin with a discovery and planning period in which the team will work with subject matter experts from MDHHS and DTMB to set the priority and order of decommissioning of the eight (8) major systems that will be migrated to the MIDASH Solution, allowing the team to finalize the release plan.

Each system release will consist of nine (9) development and test sprints for completing required interfaces and data migration, and ultimately decommissioning activities of the corresponding legacy system.  Additionally, each system release will include maintaining and updating SUITE system development deliverables, creating/updating training materials and documentation, executing training and UAT, and performing production cutover activities.

The following table provides an overview of our proposed system release timeline:

Table 7. Proposed System Release Timeline

| Release | Dev/Test Start | Dev/Test Finish | UAT Start | UAT Approval | Go-Live |
| --- | --- | --- | --- | --- | --- |
| System 1 | 6/12/23 | 10/16/23 | 11/3/23 | 11/29/23 | 12/21/23 |
| System 2 | - 7/14/23 | - 11/17/23 | - 12/11/23 | - 1/16/24 | - 1/30/24 |
| System 3 | 8/14/23 | 12/20/23 | 1/16/24 | 2/14/24 | 2/29/24 |
| System 4 | 9/12/23 | 1/25/24 | 2/14/24 | 3/7/24 | 3/29/24 |
| System 5 | 10/6/23 | 2/21/14 | 3/12/24 | 4/2/24 | 4/24/24 |
| System 6 | 11/2/23 | 3/19/24 | 4/8/24 | 4/29/24 | 5/21/24 |
| System 7 | 12/5/23 | 4/16/24 | 5/6/24 | 5/28/24 | 6/19/24 |
| System 8 | 12/19/23 | 4/30/24 | 5/20/24 | 6/11/24 | 7/3/24 |

This is KL&A’s proposed timeline based on our experience developing and implementing systems for the State of Michigan, as well as based on a velocity we believe will be sustainable for the State of Michigan.  While a more aggressive timeline is certainly possible, our past projects have taught us that it can place undue stress on all team members, including MDHHS and DTMB subject matter experts.  KL&A is open to accelerating the project timeline, however, it would require additional staff on the KL&A side and additional time commitments from MDHHS and DTMB.  Accelerating the project implementation timeline may also result in an overall project cost impact, depending on the number of additional resources that are required.  Unfortunately, the law of diminishing returns is a real phenomenon in which adding resources does not necessarily mean a proportional increase in project velocity.  Larger project teams require greater communication that can introduce inefficiencies across the team.  These inefficiencies are ultimately what result in an impact on the overall project cost.

Finally, this is a preliminary schedule that reflects the overall level of effort.  However, discovery may uncover opportunities to release a minimum viable product earlier, with additional iterative releases, or to modify the cadence of migration releases.  We will review our preliminary schedule with MDHHS and DTMB during the discovery period to determine if any modification would add value.

#### Work Breakdown Structure (WBS) & Project Schedule

KL&A has included in our submission a comprehensive WBS/project schedule, in portable document format (PDF).  The schedule provides a view of all releases, tasks, deliverables, and milestones.  The resources column identifies State and KL&A responsibilities.  Please refer to:

20_MDHHS_MIDASH_WBS-Schedule-Detail_FromKLA.pdf

ORGANIZATIONAL CHANGE MANAGEMENT

Decades of research tells us that around 70% of initiatives requiring large-scale change have failed to achieve expected benefits largely because there was no strategy to ensure and measure achievement of user adoption of changes needed to meet the initiative’s objectives.   Organizational Change Management (OCM) is the practice that focuses on user adoption.

Contractor must develop and deliver an organizational change management strategy and plan that includes the following:

Executive Leadership and Middle Manager Engagement and Support

Stakeholder (Internal and External) Engagement and Support

Solution and Stakeholder Alignment

Business Readiness

Change Champion Network Engagement and Support

Communication Management

Measurement

Sustainment and Transfer of Ownership

Executive Leadership and Middle Manager Engagement and Support

Research tells us that the number one success factor for large-scale change initiatives is highly active and visible executive leadership.

Describe how Bidder will support executive leaders and managers in performing their critical roles within the context of the initiative
BIDDER RESPONSE:

See the blue response text below.

### Bidder Response to Executive Leadership and Middle Manager Engagement and Support

Springboard Consulting’s organizational change management (OCM) team (OCM Team), KL&A’s strategic partner for MIDASH training and OCM, will work closely with executive leadership and middle managers by providing them with the tools and techniques needed to communicate about and support the change initiative.

The OCM Team has proprietary tools that will be used items to ensure leaders are prepared to discuss information, such as the Engaging Leaders Brief and a weekly briefing format that ensures that executive leaders, change sponsors, and cascading sponsors and managers know what is being shared, which activities to support, and any “keep your eye on” items. The format also includes communication, activities, and celebrations for the upcoming week.  In addition, one key message per week is shared with all leaders to ensure sponsorship alignment and holistic, cohesive communication from leadership.

Additionally, the OCM Team will educate executive leaders and managers about the level of importance their roles have on the project’s overall success and what it means to be an active and visible leader. They will also educate leaders about the change process and how they can effectively lead change using a unified approach. This education will be provided using a workshop-style format to enable deep learning and experience in strategies and tactics to spotlight sponsors and support the change with positive change activities.

Developing a coalition of cascading sponsors provides support for stakeholders from all levels of leadership and amplifies the executive sponsor’s messaging. The OCM Team recommends this cascading approach to enhance the change process for stakeholders as they receive information from senior leaders about the strategic goals of the transformation as well as learn about the impact the change will have on their job role or responsibilities from their direct supervisor.

The Springboard Consulting OCM Team has extensive experience successfully providing this level of executive leadership and management support for several clients. They have even presented this information at different Association of Change Management Professionals (ACMP) and Project Management Institute (PMI) global events.

Stakeholder (Internal and External) Engagement and Support

Describe how stakeholders will be engaged throughout the initiative and post implementation to ensure awareness, buy-in, knowledge, and sustained ability to perform their jobs with the change. This includes contractor’s ability to successfully engage with DHSP as applicable to the initiative, including how stakeholder resistance will be identified and mitigated.
BIDDER RESPONSE:

See the blue response text below.

### Bidder Response to Stakeholder Engagement and Support

Stakeholder adoption is essential for project success.  Identifying those who are impacted by the change and using a stakeholder analysis to determine the extent of change necessary from both internal and external stakeholders will be a critical activity in building engagement. Stakeholders must be aware of the change effort and recognize the level of change needed for adoption.

The OCM team will conduct a variety of stakeholder activities such as identifying key stakeholders; communicating the relevant and relatable story of change with key messages; providing business transition workshops; conducting training to provide the knowledge, skills, and abilities to perform their roles in the future state; and recognizing and addressing resistance with a robust response. All of which will contribute to overall stakeholder satisfaction and change adoption.

The Springboard Consulting OCM Team’s deep experience in the design of stakeholder identification and assessment tools will prove beneficial to the MIDASH project. The team will also call on their excellent facilitation skills with individuals from internal and external stakeholder groups to recognize and record what stakeholder groups will gain from this change, what they will lose through this change, and what the stakeholder groups fear about this change. These tools will enable the next steps in building stakeholder engagement through communication to targeted groups, business process redesign sessions and transition workshops, training and development of skills and abilities, post-live support, ongoing training with other knowledge transfer, and sustainability activities.

Resistance to change is inevitable and though resistance can be perceived as undesirable, stakeholder engagement includes a resistance management plan to address the loss and fear which can accompany change. Therefore, the OCM Team will work with DHSP to develop a resistance management plan that provides a path to assist resistant stakeholders with the journey to the future state to realize the benefits of the change.

Solution and Stakeholder Alignment

A successful project 1) delivers a system that meets the needs of users and 2) ensures individuals are able to perform their jobs proficiently with the change.  It is expected that technical development and stakeholder preparation occur together as a comprehensive solution.

Describe how Bidder will align technical development and stakeholder preparation to deliver both the technical and people sides of a complete solution.
BIDDER RESPONSE:

See the blue response text below.

### Bidder Response to Solution and Stakeholder Alignment

Having developed and implemented IT solutions for over 30 years, KL&A can attest to the fact that implementing a best-in-class technical solution is simply not enough to ensure its effectiveness in meeting a project’s objectives. The people side (change management) and the technical side (project management) each play a critical and equal role in achieving an initiative’s objectives and declaring overall success. While the project team is responsible for delivering a technical solution that meets the needs of the users, the OCM Team is responsible for delivering users who have successfully adopted behaviors consistent with the future state.

Integration and alignment of the project management and change management plan will be extremely beneficial for stakeholders. The alignment of the solution with the stakeholders is created by ensuring stakeholders are given the opportunity to provide input during design and planning sessions, are included in discussions addressing business process redesign, and are provided with the opportunity to participate in activities such as user acceptance testing, pilot session(s), and training development.

Advocating for the end-users and stakeholders will be a key responsibility of the project’s organizational change management (OCM) lead, along with integrating the project and change plans to ensure the solution has incorporated the stakeholder perspective.  KL&A’s proposed OCM lead has deep experience facilitating the integration of project and change teams through scheduling project plans and serving as a conduit to connect the PM, OCM, and technology teams. She is the principal consultant of Springboard Consulting, KL&A’s strategic partner for MIDASH training and OCM, and is a Certified Project Management Professional (PMP) and Certified Change Management Professional (CCMP).

Business Readiness

Business Readiness is closely linked and often overlaps with Organizational Change Management.  However, Business Readiness focuses on operational and tactical aspects of preparing the organization to successfully use a new system and other required changes; whereas Organizational Change Management focuses on ensuring individuals are ready to perform their jobs and engage with DHSP with the change.

Describe how Bidder will meet and sustain the business-focused operational and tactical readiness aspects of a successful initiative.
BIDDER RESPONSE:

See the blue response text below.

### Bidder Response to Business Readiness

To realize the benefits of change, the OCM Team must evaluate the change impact and business readiness for change begin before developing change management strategies and plans to ensure a comprehensive analysis of potential gaps in readiness are included in the strategic goals and plans. Establishing business readiness goals and milestones early in the evaluation of impact and assessment will also determine how the DHSP will know when readiness goals have been achieved and the workforce is prepared for the transformation.

As a result of the planning work, the OCM Team will develop a detailed understanding of the adaptation stakeholders must make in mindset and behavior for the transformation to occur. The team will also gain practical insight into how stakeholders will need to work differently to operate effectively in the future state. Guiding stakeholders from the current state to the future state by identifying, with subject matter experts, which business process workstreams are impacted by the change is a critical business readiness milestone.

The OCM Team will develop metrics that will be applied at the organizational level and individual level to examine awareness and participation in change activities as well as assess barriers to change activities. These metrics may include conducting transitional workshops to redesign business processes, working alongside the training team to identify learning and development requirements, or building out detailed plans for strategic communication.

Change Champion Network Engagement and Support

DHSP has established a Change Champion Network for the MIDASH initiative.  The Change Champion Network is currently made up of 18 DHSP staff and will be expanded to include 50-100 external users.  The Change Champion Network is critical to the success of the MIDASH initiative as Change Champions have organizational knowledge, cultural understanding, technical skills, business acumen, etc. that is beneficial to promote successful, sustained adoption of the new system and processes.

Describe how bidder will train, coach, support, engage with and utilize the Change Champion Network to support the objectives of the initiative.
BIDDER RESPONSE:

See the blue response text below.

### Bidder Response to Change Champion Network Engagement and Support

A change agent program, such as the Change Champion Network, is an essential component in organizational change and transformation, and the establishment of this network by DHSP lays the foundation for project success. Change agents, such as the Change Champions, provide a communication bridge between internal and external stakeholders/business units and the project/leadership team.

Expanding the Change Champion Network to incorporate external stakeholders and end-users, along with continuing to develop the goals of the network, is essential to the success of the change. Additional trusted and influential individuals must be recruited to join the network and participate in an onboarding process to define roles, clarify responsibilities, and develop an understanding of the organizational culture and change impact.

The OCM team will be committed to educating executive leaders and sponsors about the importance of their role in the change network and will work with them to accomplish the goals and objectives of that role. The OCM team will also reach out to leaders of each area to help them identify the person with the right skills and characteristics to serve as a Change Champion change agent.

The OCM team will conduct training for the Change Champion Network participants, which may include sessions in:

Leading Successful Change

Recognizing and Reducing Resistance

Secrets of Sponsor Success

Foundations of Human-Centered Design

Change Communication

Springboard Consulting, KL&A’s strategic partner for MIDASH training and OCM, will work with the network and/or leadership to identify any additional training topics needed for the MIDASH project.

Communication Management

Communication is more than delivering information.  Communication is a tool to achieve desired behaviors and outcomes.

Describe how Bidder will use communication activities, tools, and methods to achieve desired behaviors and outcomes required for a successful initiative.
BIDDER RESPONSE:

See the blue response text below.

### Bidder Response to Communication Management

Building trust with the stakeholder population involves transparency and frequent communication.  Stakeholders will have more desire to support change if they are made aware of the change in advance, understand how the change will improve their lives, and are informed on how and when the changes will occur. Therefore, the OCM Team will work with DHSP to develop a Communications Management Plan.

The overall objective of a Communications Management Plan is to promote the success of a project by meeting the information needs of project stakeholders and to outline the goals of the communications efforts to reach and inform each group. During the evaluation and assessment phase of the change effort, the OCM Team will take a detailed inventory of communication to identify existing communication channels and vehicles. These available channels and vehicles will then be incorporated into the detailed plans for strategic communication to ensure employees are prepared to adopt new processes, roles, and technology.

The development of the communication plan and activities will include identifying the appropriate level of communication needed for each project stakeholder. The plan will also identify:

What information should be distributed

Frequency of communications

Vehicle of communications

Key messaging

Milestones

Communication tools such as a project website, frequently asked questions, email, newsletters, webinars, presentations, brochures, outreach plans, handbooks, press releases, town-hall events, interactive QR codes, and additional communication tools will be deployed according to the communication plan and as needed in response to the planned communication effort.

Measurement

A successful Organizational Change Management strategy identifies the individual milestones needed to be achieved so that users can perform their jobs proficiently with the change and/or engage with DHSP to obtain needed information and services.

Describe individual milestones Bidder believes are necessary for a successful change initiative, how achievement of those milestones will be measured, and how gaps in achieving the required milestones will be mitigated.
BIDDER RESPONSE:

See the blue response text below.

### Bidder Response to Measurement

Milestones necessary for a successful change initiative include:

Awareness of the change and recognition of the impact and benefit of the change by leaders, stakeholders, and end-users.

Engagement of sponsors and leaders supporting the change with active and visible behavior.

Communication, early and often, through various channels with key messages shared by managers and supervisors to internal stakeholders as well as messaging for external stakeholders from the appropriate leader.

Development and delivery of business-process, human-centered focused training, as well as ongoing, post-live support.

Reduction of resistance through resistance management activities and an agile approach to reiterate the benefit of the change.

Transition of sustainability activities to business owners to ensure adoption is sustained.

To assess the achievement of these milestones, the OCM Team will conduct surveys with two groups of stakeholders – one comprised of a consistent group of stakeholders, and one comprised of a random group of stakeholders. These strategic surveys will be used to measure the response at five points in the project/change timeline:

After First Communication

After Manager Coaching

After Training

After Go-Live

After Celebrating Success

The questions asked in the surveys will remain consistent to provide a way to chart results over the life of the project and incorporate focus group anecdotal evidence. Using a Likert scale to measure positive responses and identify barrier points assist in determining how best to provide mitigation activities such as additional communication, training, or resistance reduction and adjusting activities as the project evolves.

Sustainment and Transfer of Ownership

Describe how Bidder will support users post-implementation to ensure sustained adoption of change and how Bidder will transition ownership of organizational change management activities and artifacts to DHSP.
BIDDER RESPONSE:

See the blue response text below.

### Bidder Response to Sustainment and Transfer of Ownership

Since change management does not end at go-live, the OCM Team will provide post-implementation support where they will continue to measure success, identify and fill gaps, reinforce learning, and establish and promote reward and recognition as deemed appropriate for the organization. The OCM team will develop an OCM Transition Plan that will be part of the project Transition In/Out Plan that will outline the ongoing activities needed to support end-users and stakeholders and how the operational units will continue to support efforts while working toward sustainability.

The OCM team will also work with DHSP business owners to establish a Governance Plan to ensure sustainability and continuous improvement.  Once the organization is operating effectively and the change program is transitioned to the DHSP to manage long-term, the organization will continue to monitor sustainability by engaging with stakeholders, and periodically measure, track, and improve performance as the organization and the system continue evolving.

ADDITIONAL INFORMATION

The State reserves the right to purchase any additional services or products from the Contractor during the duration of the Contract.