## Q1
| Project Kickoff | Sprint 0.1 | Sprint 0.2 | Sprint 0.3 | Sprint 0.4 | Sprint 0.5 | Sprint 0.6 | Phase 2 Sprint 1 | Phase 2 Sprint 2 | Phase 2 Sprint 3 | Phase 2 Sprint 4 | Phase 2 Sprint 5 | Phase 2 Sprint 6 | Phase 2 Sprint 7 | Phase 2 Sprint 8 | Phase 2 Sprint 9 | Phase 2 Sprint 10 | Phase 2 Sprint 11 | Phase 2 Sprint 12 | Phase 2 Sprint 13 | Phase 2 Sprint 14 | Phase 2 Sprint 15 | Phase 2 Sprint 16 | Phase 2 Sprint 17 | Phase 2 Sprint 18 | Phase 2 Sprint 19 | Phase 2 Sprint 20 | Phase 2 Sprint 21 | Phase 2 Sprint 22 | Phase 2 Sprint 23 | Phase 2 Sprint 24 | Phase 2 Sprint 25 | Phase 2 Sprint 26 | Phase 2 Sprint 27 | Phase 2 Sprint 28 | Phase 2 Sprint 29 | Phase 2 Sprint 30 | Phase 2 Acceptance | Phase 3 Sprint 31 | Phase 3 Sprint 32 | Phase 3 Sprint 33 | Phase 3 Sprint 34 | Phase 3 Sprint 35 | Phase 3 Sprint 36 | Phase 3 Sprint 37 | Phase 3 Sprint 38 | Phase 3 Sprint 39 | Phase 3 Sprint 40 | Phase 3 Sprint 41 | Phase 3 Sprint 42 | Phase 3 Sprint 43 | Phase 3 Sprint 44 | Phase 3 Sprint 45 | Phase 3 Acceptance | Warranty | Maintenance & Support - Yr 3 | Maintenance & Support - Yr 4 | Maintenance & Support - Yr 5 | Maintenance & Support - Yr 6 | Maintenance & Support - Yr 7 | Maintenance & Support - Yr 8 | Maintenance & Support - Yr 9 | Maintenance & Support - Yr 10 | TOTAL
Key Resources | [63 empty] | 0
Contractor Project Manager |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 1040 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 21840
Contractor HIV/STI Functional Lead |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [15 empty] | 3680
Contractor Agile Team Lead(s) (Scrum Master(s) or equivalent) |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [15 empty] | 1840
Contractor Technical Lead / Solution Architect |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [15 empty] | 1840
Contractor Test Lead |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [15 empty] | 3680
Contractor Training and Business Readiness Lead | [13 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [14 empty] | 2880
Contractor Production Support Engineer | [34 empty] | 25.6 | 40 | 40 |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 80 | 80 | 80 | 80 | 80 |  | 1040 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 18585.6
Contractor HCD / User Experience (UX) Design Lead |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [15 empty] | 3680
Contractor Organizational Change Management (OCM) Lead |  | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 |  | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | [15 empty] | 2944
Contractor Security Lead |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [15 empty] | 368
Contractor Data Migration / Conversion Lead | [6 empty] | 38.4 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 27.2 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | [15 empty] | 1385.6
Contractor Integration/Interface Lead | [6 empty] | 38.4 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 27.2 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | [15 empty] | 1385.6
Contractor Business Analyst Lead |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 1040 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 21840
0
Non-Key Resources | [63 empty] | 0
Contractor Project Coordinator |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [15 empty] | 3680
Contractor Tester #1 | [12 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [15 empty] | 2800
Contractor Tester #2 | [34 empty] | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [15 empty] | 1040
Contractor Scrum Master | [11 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [15 empty] | 2880
Contractor Configuration Manager | [11 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [15 empty] | 2880
0
Contractor Developer #1 |  | 80 | 80 | 80 | 80 | 80 | 80 | [56 empty] | 480
Contractor Developer #2 |  | 80 | 80 | 80 | 80 | 80 | 80 | [56 empty] | 480
Contractor Business Analyst Lead |  | 80 | 80 | 80 | 80 | 80 | 80 | [56 empty] | 480
Contractor Business Analyst #1 |  | 80 | 80 | 80 | 80 | 80 | 80 | [56 empty] | 480
Contractor Business Analyst #2 |  | 80 | 80 | 80 | 80 | 80 | 80 | [56 empty] | 480
Contractor Business Analyst #3 |  | 80 | 80 | 80 | 80 | 80 | 80 | [56 empty] | 480
Contractor Business Analyst #4 |  | 80 | 80 | 80 | 80 | 80 | 80 | [56 empty] | 480
0
Contractor Lead Developer #1 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Lead Developer #2 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Developer #3 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Developer #4 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Developer #5 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Developer #6 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Developer #7 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Developer #8 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Developer #9 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Developer #10 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Business Analyst #5 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Business Analyst #6 | [13 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2400
0
Contractor Integration/Interface Developer #1 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
0
Contractor Data Migration / Conversion Developer #1 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
Contractor Data Migration / Conversion Developer #2 | [7 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | [19 empty] | 2880
0
Production Support Engineer #1 | [40 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 1040 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 18800
Production Support Engineer #2 | [40 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 1040 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 2080 | 18800
0
Contractor Organizational Change Management (OCM) #1 |  |  |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [10 empty] | 3920
Contractor Organizational Change Management (OCM) #2 | [38 empty] | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [14 empty] | 880
Trainer #1 | [34 empty] | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [10 empty] | 1440
Trainer #2 | [34 empty] | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [10 empty] | 1440
Trainer #3 | [34 empty] | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [10 empty] | 1440
Trainer #4 | [34 empty] | 80 | 80 | 80 |  | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | [10 empty] | 1440
0
TOTAL | 0 | 1192 | 1192 | 1272 | 1272 | 1272 | 1348.8 | 1912 | 1912 | 1912 | 1912 | 2072 | 2152 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2312 | 2712 | 2712 | 2712 | 160 | 2792 | 2792 | 2952 | 2952 | 2952 | 2952 | 1752 | 1752 | 1752 | 1752 | 960 | 800 | 800 | 800 | 800 | 240 | 5200 | 10400 | 10400 | 10400 | 10400 | 10400 | 10400 | 10400 | 10400 | 193468.8
[55 empty] | 110268.8 | 83200

## Q2-7
Item | Question | Response
2 | Which tools or services are you planning to use for data conversion? | As stated in the RFP, there a few different types of data sources currently used at MDHHS that are encompassed within the solution (Oracle, SQL Server, SQL, HP Content Manager). The tools we plan to use and our process for doing so for each of the source databases is to transfer the information via direct database to database connection if appropriate or export/import the data (based on CSV or applicable output file types) to a Migration area for data verification and transformation before moving to the final state (data location). Document content will be transferred using custom developed scripts to the Filenet ECM as described in our response.
3 | What will be your procedure and storage solution for Transactional, Operational, and Analytical data? Will all types be stored together or stored separately? If so, how? | KL&A's MIDASH solution will utilize multiple schemas, views, procedures, and tables for storing and working with all types and forms of data, including transactional, operational, and analytical within a combined database system. For instance, views specific for reporting will be managed in a separate schema and pull directly from primary operational data. Data will be accessed, queried, and maintained from the various input and analytical sources as needed within the same databases per environment. Databases will be separated between environments to ensure that data integrity and security is maintained and there is a logical barrier between users and applications of the solution utilizing the MIDASH data.
4 | Considering the current database size information provided in the RFP Migration section, how much storage do you estimate needing for go-live? | Given the stated volumes of data for each current individual database system noted in the RFP, as as well as accounting for the unknown size of the data in the APHIRIM system, KL&A recommends the Production databases to be allocated between 1750GB and 2TB of disk. This allocation is assuming that the data being converted from the MDSS system is truly occupying a whole terabyte. If this is inaccurate, or the APHIRIM data is found to be quite large, updated allocations will need to be determined based on appropriate sizes validated from MDHHS and DTMB. The Test environments may be allocated less, likely 500GB to 1TB, based on determined need and usage of Production-like data for use in QA/UAT environments and testing purposes.
5 | Please describe your data analysis, reporting, and dashboard development process | KL&A will work closely with the DHSP staff and user groups to ensure the MIDASH data model and corresponding reporting views are built according to adequate business use and need. This will be conducted through Joint Application Design (JAD) sessions, and usability studies and discussions with individual end user groups as needed. Similarly, the widgets and content displayed in the various dashboard elements for each type of user will be custom tailored to meet their needs with a combination of graphs/charts, filters, list views, and data entry to provide access to relevant and necessary metrics and data points.
6 | Please describe your data mapping and modeling approaches for reporting and analysis. | Based on the reporting / analysis tools selected by MDHHS (Tableaux, Power BI, ect.), KL&A will develop generic views to support the development of user managed reports. For formal reporting, KL&A will work with the users to develop the necessary reports through Joint Application Design (JAD) sessions.
7 | Please describe the editability functions, report development (for federal requirements and ad hoc reports) from both community partners, portals, and MDHHS administrative roles/perspectives. | KL&A has extensive experience in providing all three reporting types to our clients. Please see below for a full description on how we plan to provide these to the MIDASH team: 1. Canned Reporting: These reports will be designed during a JAD session and developed in a State approved reporting tool such as SSRS, Power BI, or Tableau. The format of these reports, such as pdf, excel, csv, etc. will be considered during the design and can be chosen at runtime where appropriate. Canned reports will have dynamic parameters applied to each in order to prompt users to drill down the corresponding output to the scope of records the user is looking to view. A separation of duties and access restrictions will be implemented by using user roles and groups associated to report records that will limit which reports are available for different user types to view and run. 2. Ad-Hoc Reporting: The MIDASH solution will have a variety of search screens that produce lists of filterable, sortable records. Search screens will allow for the lists to be exported to csv files for users to further manipulate as they desire. In certain screens, such as case dashboards or specific search screens, users will be able to save custom search filters for use to quickly reference and re-run them in the future for additional ad-hoc export reporting. There will be implicit filters in place based on user's access levels and roles to limit which types of records are available to be view or export. Additional access restrictions may be enforced by user role in order to access each search screen as well as individual export functionalities to limit what types of users will be able to perform those actions and see the associated data. 3. Custom Reporting: KL&A will work with the users to design views that can be used for custom User created reports using tools such as Power-BI. The format of these reports, such as pdf, excel, csv, etc. will be considered during the design and can be chosen at runtime where appropriate. This functionality will only be available to internal State workers who have access and knowledge of the reporting tooling in order to build custom reports. For all types of reporting, KL&A will implement pagination on visible and queried data to ensure that large datasets are accessed in reasonable groups in order to maintain efficiency. The connections utilized for reporting will be assigned per-transaction capacities to ensure that the Production database is not overly taxed in such a way that could cause disruptions to the web application. For all queries regardless of reporting or any other function, KL&A will work in conjunction with DTMB to monitor database sessions and long-running queries to verify that proper data structures are in place to produce efficient and optimized queries and result output.