## Details (Hide) (hidden)
MDOT hidden tab with background work - DO NOT ALTER
Color Scheme |  | Data Validation Options and Conditional Formatting | [25 empty] | Risk Rating Guidelines | [7 empty] | Determine List of Event Driven Risks | [8 empty] | Determine List of High Impact Risks | [8 empty] | Cost and Schedule Event Driven Risk Ranges
https://www.michigan.gov/mdot/0,4616,7-151-9620_67093-197355--,00.html |  | Risk Management Plan: | Risk Register:
| Pantone PMS 301 C; RGB 0, 84, 155 | Status | Risk Category (RBS) | Project Phase | Threat/Opportunity |  | Impact Type | Probability | Consequence (Opportunity) | Consequence (Threat) | Qualitative | Impact Low Range | Impact High Range | Qualitative | Impact Qualitative |  | Impact Score Low | Impact Score High | Impact Score Qualitative |  | Likelihood on CP | Milestone | Dependency | Event Driven | Response (Opportunity) | Response (Threat) | Risk Status | Probability /Rating |  | Cost Conseq |  |  | Schedule Conseq |  |  | Risk Number | (step) | Event Driven Risks | Opp/Threat | Project Phase | Probability | Cost Conseq | Schedule Conseq | On CP | Risk Number | (step) | High Impact Risks | Impact Score |  | Rank | Risk | Severity Order | Opp/Threat | Phase | Min | Max
| Pantone PMS 347 C; RGB 0, 147, 68 | Not Started
|  | In Progress | CONSTRUCTION | IDENTIFICATION AND SELECTION | OPPORTUNITY | -1 | COST | 1 | 1 | 1 | Low | 20 | 25 | High | 25 | High | 40 | 50 | 50 | High | 10% | SCHEMATIC COMPLETE | Interdependent | YES | ACCEPT | ACCEPT | NOT ACTIVE | 1 | 10% |  | 1 | 25000 |  | 1 | 1 | 1 | 1000 | [7 empty] | 1 |  |  |  | 1 |  |  |  |  | Development | 80% | 125%
|  | Complete | DESIGN | DEVELOPMENT | THREAT | 1 | SCHEDULE | 2 | 2 | 2 | Medium-Low | 12 | 19 | Medium-High | 25 | High | 24 | 39 | 49 | High | 30% | ENVIRONMENTAL (EIS, ROD, FONSI) COMPLETE | Independent | NO | ENHANCE | MITIGATE | ACTIVE | 2 | 25% |  | 2 | 50000 |  | 2 | 3 | 2 | 1000 | [7 empty] | 2 |  |  |  | 2 |  |  |  |  | Identification and Selection | 75% | 130%
|  |  | ENVIRONMENTAL | PROCUREMENT |  |  | COST AND SCHEDULE | 3 | 3 | 3 | Medium | 6 | 11 | Medium | 24 | High | 12 | 23 | 48 | High | 60% | FUNDING COMPLETE |  |  | SHARE | TRANSFER | DORMANT | 3 | 50% |  | 3 | 250000 |  | 3 | 8 | 3 | 1000 | [7 empty] | 3 |  |  |  | 3 |  |  |  |  | Implementation | 97% | 105%
|  |  | FINANCIAL | IMPLEMENTATION |  |  |  | 4 | 4 | 4 | Medium-High | 3 | 5 | Medium-Low | 23 | High | 6 | 11 | 47 | High | 90% | ISSUE RFQ |  |  | EXPLOIT | AVOID | RETIRED | 4 | 75% |  | 4 | 500000 |  | 4 | 12 | 4 | 1000 | [7 empty] | 4 |  |  |  | 4 |  |  |  |  | Procurement | 90% | 115%
|  |  | HAZARDOUS MATERIALS |  |  |  |  | 5 | 5 | 5 | High | 1 | 2 | Low | 22 | High | 1 | 5 | 46 | High |  | QUALIFICATION STATEMENT DUE | [5 empty] | 5 | 90% |  | 5 | 1500000 |  | 5 | 20 | 5 | 1000 | [7 empty] | 5 |  |  |  | 5
|  |  | OPERATIONS AND MAINTENANCE | Identification and Selection |  |  |  |  | N/A | N/A |  | 1 | 2 | Low | 21 | High | 1 | 5 | 45 | High |  | SHORTLIST | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 6
|  |  | ORGANIZATION | Development | [7 empty] | 3 | 5 | Medium-Low | 20 | High | 6 | 11 | 44 | High |  | ISSUE DRAFT FRP | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 7
|  |  | OTHER | Procurement | [7 empty] | 6 | 11 | Medium | 19 | Medium-High | 12 | 23 | 43 | High |  | ISSUE FINAL RFP | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 8
|  |  | PARTNERS AND STAKEHOLDERS | Implementation | [7 empty] | 12 | 19 | Medium-High | 18 | Medium-High | 24 | 39 | 42 | High |  | PROPOSALS DUE | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 9
|  |  | PROCUREMENT AND CONTRACTING | [8 empty] | 20 | 25 | High | 17 | Medium-High | 40 | 50 | 41 | High |  | CONDITIONAL AWARD | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 10
|  |  | PROJECT MANAGEMENT | [8 empty] | N/A | N/A |  | 16 | Medium-High | N/A | N/A | 40 | High |  | NTP 1 | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 11
|  |  | RAILROAD | [11 empty] | 15 | Medium-High |  |  | 39 | Medium-High |  | NTP 2 | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 12
|  |  | REGULATORY / REPORTING | [11 empty] | 14 | Medium-High |  |  | 38 | Medium-High |  | SUBSTANTIAL COMPLETION | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 13
|  |  | RIGHT OF WAY | [11 empty] | 13 | Medium-High |  |  | 37 | Medium-High |  | CONSTRUCTION COMPLETION | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 14
|  |  | SAFETY | [11 empty] | 12 | Medium-High |  |  | 36 | Medium-High |  | O&M BEGIN | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 15
|  |  | SITE | [11 empty] | 11 | Medium |  |  | 35 | Medium-High |  | O&M END | [13 empty] | 0 | [8 empty] | 0 |  |  |  | 16
|  |  | THIRD PARTY | [11 empty] | 10 | Medium |  |  | 34 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 17
|  |  | UTILITIES | [11 empty] | 9 | Medium |  |  | 33 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 18
[15 empty] | 8 | Medium |  |  | 32 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 19
[15 empty] | 7 | Medium |  |  | 31 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 20
[15 empty] | 6 | Medium |  |  | 30 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 21
[15 empty] | 5 | Medium-Low |  |  | 29 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 22
[15 empty] | 4 | Medium-Low |  |  | 28 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 23
[15 empty] | 3 | Medium-Low |  |  | 27 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 24
[15 empty] | 2 | Low |  |  | 26 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 25
[15 empty] | 1 | Low |  |  | 25 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 26
[15 empty] | 1 | Low |  |  | 24 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 27
[15 empty] | 2 | Low |  |  | 23 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 28
[15 empty] | 3 | Medium-Low |  |  | 22 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 29
[15 empty] | 4 | Medium-Low |  |  | 21 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 30
[15 empty] | 5 | Medium-Low |  |  | 20 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 31
[15 empty] | 6 | Medium |  |  | 19 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 32
[15 empty] | 7 | Medium |  |  | 18 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 33
[15 empty] | 8 | Medium |  |  | 17 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 34
[15 empty] | 9 | Medium |  |  | 16 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 35
[15 empty] | 10 | Medium |  |  | 15 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 36
[15 empty] | 11 | Medium |  |  | 14 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 37
[15 empty] | 12 | Medium-High |  |  | 13 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 38
[15 empty] | 13 | Medium-High |  |  | 12 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 39
[15 empty] | 14 | Medium-High |  |  | 11 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 40
[15 empty] | 15 | Medium-High |  |  | 10 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 41
[15 empty] | 16 | Medium-High |  |  | 9 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 42
[15 empty] | 17 | Medium-High |  |  | 8 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 43
[15 empty] | 18 | Medium-High |  |  | 7 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 44
[15 empty] | 19 | Medium-High |  |  | 6 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 45
[15 empty] | 20 | High |  |  | 5 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 46
[15 empty] | 21 | High |  |  | 4 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 47
[15 empty] | 22 | High |  |  | 3 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 48
[15 empty] | 23 | High |  |  | 2 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 49
[15 empty] | 24 | High |  |  | 1 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 50
[15 empty] | 25 | High |  |  | 1 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 51
[19 empty] | 2 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 52
[19 empty] | 3 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 53
[19 empty] | 4 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 54
[19 empty] | 5 | Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 55
[19 empty] | 6 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 56
[19 empty] | 7 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 57
[19 empty] | 8 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 58
[19 empty] | 9 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 59
[19 empty] | 10 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 60
[19 empty] | 11 | Medium-Low | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 61
[19 empty] | 12 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 62
[19 empty] | 13 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 63
[19 empty] | 14 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 64
[19 empty] | 15 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 65
[19 empty] | 16 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 66
[19 empty] | 17 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 67
[19 empty] | 18 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 68
[19 empty] | 19 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 69
[19 empty] | 20 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 70
[19 empty] | 21 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 71
[19 empty] | 22 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 72
[19 empty] | 23 | Medium | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 73
[19 empty] | 24 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 74
[19 empty] | 25 | Medium-High | [15 empty] | 0 | [8 empty] | 0 |  |  |  | 75
[19 empty] | 26 | Medium-High
[19 empty] | 27 | Medium-High
[19 empty] | 28 | Medium-High
[19 empty] | 29 | Medium-High
[19 empty] | 30 | Medium-High
[19 empty] | 31 | Medium-High
[19 empty] | 32 | Medium-High
[19 empty] | 33 | Medium-High
[19 empty] | 34 | Medium-High
[19 empty] | 35 | Medium-High
[19 empty] | 36 | Medium-High
[19 empty] | 37 | Medium-High
[19 empty] | 38 | Medium-High
[19 empty] | 39 | Medium-High
[19 empty] | 40 | High
[19 empty] | 41 | High
[19 empty] | 42 | High
[19 empty] | 43 | High
[19 empty] | 44 | High
[19 empty] | 45 | High
[19 empty] | 46 | High
[19 empty] | 47 | High
[19 empty] | 48 | High
[19 empty] | 49 | High
[19 empty] | 50 | High
RS&H, 2021

## Introduction
RISK MANAGEMENT WORKBOOK INTRODUCTION
Overview
Risk management is a well-established project management process that focuses on the identification, assessment and evaluation of project risks for the primary purpose of reducing cost and schedule uncertainty on projects. Cost and schedule management are all very familiar to project managers and are key components of managing a project’s delivery.
Purpose
The purpose of this Risk Management Workbook ("Workbook") is to provide project managers with specific guidance on when and how to engage in the risk management process on MDOT innovative project delivery projects, including a concise set of risk management documents and tools that define the processes needed to manage risk.
Content
The Workbook is a risk management toolbox of guidance documents and tools for project managers. The Workbook consists of embedded links to all the documents and tools needed to perform risk management on MDOT projects. The documents and tools are organized as follows:
1.0 Risk Management Best Practices for project managers to successfully navigate and implement risk management consistently on projects
2.0 Risk Management Workflow to implement a best practice Risk Management Plan
3.0 Risk Management Plan to guide project managers through the risk management activities for each phase of project development, including:
3.1 Identification and Selection Phase
3.2 Development Phase
3.3 Procurement Phase
3.4 Implementation Phase
4.0 Risk Management Procedure to provide project managers with detailed steps of the risk management process
5.0 Risk Register Documentation and tools to document risks and outcomes when working through the Risk Management process, including:
5.1 Risk Register
5.2 Risk Categories
5.3 Rating Guidelines
5.4 Risk Contingency
6.0 Risk Reporting to facilitate reporting and monitoring of risk management activities, including:
6.1 High Priority Risks
6.2 Risk Assessment Checklist
Use
This Workbook is available on MDOT’s external facing website and also via embedded links in MDOT’s Innovative Construction Contracting Guide. Project Managers can download this Workbook for internal use on MDOT projects. The reports within Section 6.0 can be saved and printed for use at internal project meetings and to provide updates to shareholders and administration.

## 1.0 Risk Mgmt Best Practices
RISK MANAGEMENT BEST PRACTICES
Overview
The following key risk management best practices are intended to provide project managers with general best practice guidance conducting risk management activities.
Project Planning and Control
Risk Management Process
Focus on Project Team
Risk Management Culture
Flexible and Scalable Process
Risk Management as a Continuous Process
Importance of Risk Management – Guiding Principles
Enterprise Risk Management
Lessons Learned – Continuous Improvement
Use the risk management workbook as a project planning and control tool
Use proactive and reactive efforts to manage risk
Engage in risk response planning, whether informal or formal, as a part of overall project planning
Develop a risk-based contingency as part of a project’s overall budget contingency
Remember that managing risk, addressing uncertainty, and refining and validating assumptions is an integral part of a project’s planning, organization, and decision-making process
Enable and facilitate team coordination and the ability to prioritize items. This allows the team to be focused on the right tasks at the right time and work efficiently. A project team can make more informed decisions when the entire team understands the risk profiles and impacts.
Aim to establish a risk management culture and create specific guidance meeting the needs to help develop the guidelines and training. Such a culture allows the project team to clearly see the value of incorporating risk into project and program management decision-making and planning to mitigate scope, schedule and cost impacts.
The overall approach and processes in the Risk Management Toolbox are not intended to be prescriptive. Variations based on project size, procurement duration and timing, and other issues will require that the risk management effort be adjusted to fit each specific project. The requirements, limitations, and actions necessary to ensure consistent reporting and the continuous improvement of the risk program are discussed in the Risk Management Workbook.
As the project moves through the project development process, more project details are fleshed out and risk items are addressed. Risks are either no longer a problem because they did not occur or because sufficient information is available to better assess the concern. Additional risk items may also be discovered later during the development process. These should be added to the list of previously known risk items with strategies developed and worked as development continues.
Remember - the risk management process can be executed anytime for instances where project specific or unique risks could occur that are not identified and managed as stated previously.
Project Manager Focus
Foster Risk Culture
Promote awareness of key project risks
Early Risk Identification
Mitigation strategies so risks don’t become issues
Better Cost Estimates
Establish a formal, continuous risk management process
Reduce risk and uncertainty resulting in better pricing
Ensure quality of project information and RFP documents
Minimize risk to proposers resulting in better competition
A successful risk management process involves participation at various levels of an organization: from the project team and program levels to the agency and leadership level. Aim to deliver an integrated, multi-tiered, comprehensive risk management approach that communicates and addresses uncertainties of all management levels of an organization.
Using a risk management process will improve the operation of a program by improving overall visibility, facilitating communication, and providing an excellent basis for capturing lessons learned. It can be challenging to implement lessons learned and best practices consistently across a program due to a lack of a fully documented and developed formal Risk Management Program and in part to limited staff and resources. The key is to develop a feedback loop into the risk management process to incorporate lessons learned for continuous improvement.

## 2.0 Risk Mgmt Workflow
RISK MANAGEMENT WORKFLOW
Overview
The Risk Management Workflow provides an overview of the major risk management process steps of the Risk Management Plan within each of the project delivery phases:
1. Identification and Selection
2. Development
3. Procurement
4. Implementation
Instructions
Utilize the project delivery phase workflows to determine next steps within the risk management process. Use the link embedded within the Risk Management Plan icon to jump to the major process steps customized for each delivery phase.
Risk
Management
Plan
Region / TSC Initial Risk Management Meeting
Initial Qualitative Risk Assessment
Initial Risk Register Update
Identification and Selection Phase
Risk
Management
Plan
Development Phase
Transition Meeting with Region / TSC Risk Team
Workshop Outputs
Risk Reviews and Workshops
Qualitative and Quantitative Risk Assessments
Risk Register, Risk Management Plan, Risk-Based Cost Estimate
Risk
Management
Plan
Procurement Phase
Transition Meeting with Development Phase Risk Team
Workshop Outputs
Risk Reviews and Workshops
Qualitative and Quantitative Risk Assessments
Risk Register, Risk Management Plan, Risk-Based Cost Estimate
Risk
Management
Plan
Implementation Phase
Transition Meeting with Procurement Phase Risk Team
Quarterly Reporting: Risk Register Updates
Communicate and Consult with Stakeholders
Capture Feedback of Lessons Learned

## 3.0 Risk Mgmt Plan >>>
RISK MANAGEMENT PLAN
RS&H
Overview
Define risk management activities on projects customized for each phase of project development based on project size, complexity, risk attributes with links to documents and tools to perform the activities.
Instructions
Review the major process steps and risk management icons. Utilize the Delivery Phase Workflow to access content within the Risk Management Plan for each of the project delivery phases. The content of the major process steps within each of the Risk Management Plans is intended to provide Project Managers with recommended best practice guidance for performing continuous risk management on projects. The recommended guidance is intended to be flexible for Project Managers to customize for a project's specific needs. For example, quantitative assessments are included in the Risk Management Procedure, as part of the Risk Management Plan, but may not be appropriate for all projects depending on the size of the project. The ability to customize the actions within each of the process steps is left to the discretion of the Project Manager.
Major Process Steps for Each Delivery Phase
Initial Risk Meeting | Transition meeting from prior delivery phase assessing risk management needs
Risk Review and Planning | Team risk meeting and performing risk management activities
Risk Analysis and Allocation Meetings | Performing risk analysis
Risk Updates and Reporting | Monitoring and updating the risk register on a quarterly basis including quarterly reports
Icon Legend
These icons are located throughout the Risk Management Plan and subsequent Risk Management Procedure. Use the links embedded within these icons to jump to the associated item within the Workbook. The Cost Estimate and Baseline Schedule do not provide links within this Workbook.
Risk Management Plan Risk Breakdown Structure Risk Contingency
Risk Management Procedure Rating Guidelines High Priority Risks
Risk Register Event Driven Risks Assessment Checklist
Cost Estimate Baseline Schedule
(Outside of this Workbook - Links to Risk Contingency) (Outside of this Workbook - Links to Risk Contingency)
Delivery Phase Workflow for Risk Management Plan
Select one of the project delivery phases to begin the risk management activities.

## 3.1 Plan ¦ ID-Selection Phase
RISK MANAGEMENT PLAN
IDENTIFICATION AND SELECTION PHASE
Overview
Implement the major risk management process steps for the Identification and Selection Phase.
Instructions
Identify the current step within the Risk Management Plan using the Action Status. Update the Action Status after progressing through each step. Review and complete the associated actions and click on an icon associated with an action to move directly to that page in the Workbook. Utilize the References identified for each step when necessary.
Workflow
Process Step
Action
1. Collect and review available project materials to assist with a risk-based review
of candidate projects for alternative delivery selection.
2. Schedule and conduct an initial risk meeting to review the project information.
- Identify potential risks that may impact decision to select project for
alternative project delivery
- Refer to the candidate selection process described
1. Conduct initial risk management activities including a risk review to determine if
non-traditional delivery methods could be advantageous.
2. Review initial risk list and add additional items applicable to assist in the project
delivery selection process.
3. Consult with stakeholders on the characteristics of the project to identify what are
likely to be the major project risks.
4. Schedule risk-based candidate project risk review and allocation meetings.
1. Prepare a project scoping overview presentation for the meeting.
2. Conduct qualitative risk review and allocation meeting.
- Determine appropriate attendance: Project Team members including
Region/TSC, key specialty areas, and IC staff
- Prepare and distribute an agenda prior to the meeting
3. Develop/update a project risk profile with risk allocations to assist in
determination whether IC methods are advantageous for IC project delivery.
4. Evaluate whether a project is a suitable candidate for innovative contracting
delivery.
- Performance based incentives where the quality risk is shifted to the
contractor who is responsible for corrective action throughout the
performance life of the contract
- Risk allocation where risk is transferred or shared with the contractor and
where the contractor increases bid price based on the contractor's assessment
of risk; such a pricing structure could also lower MDOT costs
1. Perform a risk-based review of project information on an annual basis in
response to IC's call for innovative construction projects.
2. Review risk profile for suitability as an IC candidate project and assess whether
project information should be submitted for ICC review.
3. Provide additional information as needed to support ICC risk review before
making a final recommendation to the EOC.
MDOT Innovative Construction Contracting Guide References
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 2: Project Selection, Approval and Project Management
Appendix D: Guidelines for the Procurement of Construction Manager/General Contractor
Contracts, Chapter 2: Project Selection, Approval and Project Management
Chapter 2: Selection Information
Table 2.1 – Innovative Contracting Recommendations
Initial Risk Meeting
Risk Review and Planning
Risk Analysis and Allocation Meetings
Risk Updates and Reporting
Action Status

## 3.2 Plan ¦ Development Phase
RISK MANAGEMENT PLAN
DEVELOPMENT PHASE
Overview
Implement the major risk management process steps for the Development Phase.
Instructions
Identify the current step within the Risk Management Plan using the Action Status. Update the Action Status after progressing through each step. Review and complete the associated actions and click on an icon associated with an action to move directly to that page in the Workbook. Utilize the References identified for each step when necessary.
Workflow
Process Step
Action
1. Schedule and conduct a transition meeting with the Region/TSC.
- Review prior phase risk management activities (Backward Looking)
- Discuss key project risks and strategies for managing risk (Forward
Looking)
2. Transition ongoing risk activities and assemble prior phase risk documentation.
1. Collect and review available project materials for risk review.
2. Schedule and conduct a risk planning meeting.
- Identify risk management team responsibilities for the Development Phase
- Establish risk management goals and objectives (risk-based selection process
for preferred delivery method; develop strategies for managing risk and to
reduce project uncertainties)
- Collaborate on assessing risk management needs and requirements
- Discuss process and strategies for managing risk
- Coordinate interdisciplinary activities and risks common to multi-discipline
teams
3. Meet with key stakeholders including MDOT staff from the Region/TSC and key
specialty areas, the FHWA, if applicable, and the GEC to discuss the project, its
goals, schedule, funding constraints, and identify the initial major risks.
- Conduct initial risk surveys and/or interviews to identify potential risks
- Prepare an initial risk register to begin to prioritize risk events that may impact
decisions
4. Review the estimated project cost and schedule against the planned budgets
and schedules to identify variance.
5. Conduct initial scope verification.
6. Prepare the Risk Assessment Checklist to schedule and begin to conduct
preliminary engineering activities for risk mitigation in order to prepare for
launching the procurement and developing the RFP documents:
a. Schematic development activities
- Define project scope
- Identify geometric constraints and criteria for delivering scope
- Collaborate reviews with interdisciplinary teams during schematic
development (drainage, constructability)
b. Geotechnical investigations - Coordinate development of an investigation
plan by coordinating the work with the CFS Geotechnical engineering staff
and Region Materials Office staff
c. Utility investigations - Perform utility investigations to identify potential
conflicts and utility owners; develop preliminary conflict matrix and identify
any long lead and high risk utility adjustments
d. Survey and ROW mapping - Mapping should be adequate to support
completion of the environmental document and support preliminary
engineering activities necessary to mitigate risk
7. Use the Risk Assessment Checklist with preliminary schedule activities to track
and assess status and assign a risk rating for activities during Development
Phase.
- Coordinate development of Project Readiness Checklist with MDOT
Pre-procurement/Development Checklist and Development Schedule
8. Schedule Development Phase risk workshop/risk team meeting.
1. Prepare a project overview presentation for each risk workshop/risk team
meeting.
- Project overview and status
- Risk Management Process training, as applicable
2. Prepare for the risk workshop/risk team meeting:
- Determine scope of workshop and desired outcomes (qualitative or
quantitative; initial or update)
- Size the workshop appropriately
- Determine appropriate attendance: Project Team members including GEC,
Agency Leadership, Project Stakeholders, and local Officials; FHWA attendance
is required for PoDIs and optional for non-PoDI projects
- Prepare and distribute an agenda prior to the meeting
- Consider including a risk questionnaire to solicit feedback on risks prior to the
workshop
- Update register, if applicable, with feedback prior to the meeting
- Define Risk Response strategies and control assignments; these should be
ready to be discussed by identified parties for at least all High Priority risks
- Develop or update, as appropriate, the preliminary
project development schedule and preliminary cost estimate.
- Coordinate with the project team including stakeholders
and leadership to develop a risk rating scale for the project (Risk Workbook,
Section 5.3) to perform qualitative and quantitative assessments.
- Coordinate with leadership and stakeholders to establish an acceptable risk level
for high priority risks. Risks above the acceptable level are considered high
priority risks.
3. Conduct workshop in accordance with Risk Workbook Procedure.
4. Perform post-workshop updates to the risk register and assessments consistent
with the outcomes from the workshop.
5. Using the initial risk analysis, assess how risk will be allocated for the project.
Risks should be allocated to the party best equipped to manage the risk.
6. If the alternative delivery method has not been determined, use the analysis to
determine appropriate procurement method. Considerations include:
- DB procurements are typically projects with low risk of unforeseen
conditions
- DBF are projects that are unable to be financed due to size or specific project
risks
- DBFO or DBFOM, also known as P3 projects, are projects which transfer
specific design, construction, financial, operational, and maintenance
responsibilities to the private sector partner for a specific period of time
- CMGC is a procurement method where the A/E works with the Construction
Manager/General Contractor to mitigate risk during the design phase with
the CM at risk for delivering the project within the scope, schedule, and the
established price
1. Risk monitoring and control:
- Establish a process using the Risk Management Workbook for conducting
monthly updates
- Track and respond to changes in risk on a monthly basis
- Review and update the risk register and risk contingency monthly
2. Schedule monthly meetings with the Risk Management Team to review current
risk status:
- Assign a member of the Risk Management Team to coordinate the updates
with the Team
- Develop and implement strategies for responding to changing risks
- Use the updates from the latest workshop or monthly update as the basis for
discussions
- If a risk workshop is conducted, then the updates from the workshop replace
the monthly update
3. Review and update the High Priority list.
- Develop detailed response plans for all High Priority Risks
- Use the High Priority Risk report as a communication tool to report critical issues
4. Update the project cost estimate with changes to the cost risk contingency from
the monthly risk meeting or risk workshop.
5. Update the project development schedule with changes to the schedule risk
contingency and any changes to activity milestones.
6. Prepare the monthly report with current status:
- Use monthly risk reviews to develop documentation for reporting purposes
to leadership
- Report on High Priority risks and cost and schedule impacts
7. Evaluate whether a project is ready for procurement using readiness criteria
in the Risk Assessment Checklist and Development Milestone Schedule.
Considerations include:
- The level of preliminary design needed to launch a procurement is typically
10%-30%, although depends greatly on the allowable risk tolerance for the
project
MDOT Innovative Construction Contracting Guide References
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 5: Preliminary Project Information and Risk Assessment Meeting
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 13: Request for Proposals (RFP)
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 5: Preliminary Project Information and Risk Assessment Meeting
Section 5.1: Delivery Methods,
5.1A: Design-Build
5.1B: Design-Build-Finance
5.1C: Design-Build-Finance-Operate (or Maintain)
5.1D: Construction Manager/General Contractor
Chapter 2: Selection Information
Table 2.1 – Innovative Contracting Recommendations
Section 4.3: Payment
Appendix D: Guidelines for the Procurement of Construction Manager/General Contractor
Contracts, Chapter 3: Preliminary Project Information and Risk Assessment Meeting
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 12: Request for Qualifications (RFQ)
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Appendix 12A: Design-Build RFQ Checklist
Risk Updates and Reporting
Risk Analysis and Allocation Meetings
Risk Review and Planning
Initial Risk Meeting
Action Status

## 3.3 Plan ¦ Procurement Phase
RISK MANAGEMENT PLAN
PROCUREMENT PHASE
Overview
Implement the major risk management process steps for the Procurement Phase.
Instructions
Identify the current step within the Risk Management Plan using the Action Status. Update the Action Status after progressing through each step. Review and complete the associated actions and click on an icon associated with an action to move directly to that page in the Workbook. Utilize the References identified for each step when necessary.
Workflow
Process Step
Action
1. Prior to the initial risk meeting for the Procurement Phase, conduct a lessons
learned and best practices workshop with the Development Phase project team.
- Review lessons learned documentation from the previous phase
- Consider any Procurement Phase lessons learned and best practices from other
projects and programs.
2. Schedule and conduct a transition meeting with the Development Phase project
team.
- Review prior phase risk management activities (Backward Looking)
- Discuss key project risks and strategies for managing risk during the
procurement (Forward Looking)
3. Transition ongoing risk activities from the Development Phase and assemble
prior phase risk documentation.
4. Collaborate with the Development Phase project team to update the risk
register (retiring risks that are no longer active).
1. Collect and review available project materials from the Development Phase for
risk review.
2. Schedule and conduct a risk planning meeting.
- Identify risk management team responsibilities for the Procurement Phase
- Establish risk management goals and objectives (risk-based selection process
for preferred delivery method, develop strategies for managing risk and to
reduce project uncertainties)
- Collaborate on assessing risk management needs and requirements
- Discuss process and strategies for managing risk
- Coordinate interdisciplinary activities and risks common to multi-discipline
teams
3. Meet with key stakeholders including MDOT staff from the Regions/TSC and key
specialty areas, the FHWA, if applicable, and the GEC to discuss the project, its
goals, schedule, funding constraints, and to identify the major risks for the
procurement.
- Conduct initial risk surveys and/or interviews to identify potential
procurement risks and perform initial impact assessments
- Update the risk register based on survey feedback and begin to prioritize
risk events that may impact decisions
4. Review the estimated project cost and schedule against the planned budgets
and schedules to identify variance.
5. Verify alignment of project scope, cost and schedule assumptions.
6. Use the Risk Assessment Checklist to continue monitoring progress of
preliminary engineering activities for risk mitigation:
a. Schematic development activities
- Project scope validation and consistency with RFP requirements
- Identify geometric constraints and develop RFP criteria for delivering scope
- Collaborate reviews of the RFP documents with interdisciplinary teams
during schematic development (roadway, drainage, constructability) to
identify discrete risk events
b. Geotechnical investigations - Continue coordinating development of RFP
requirements with the CFS Geotechnical engineering staff and Region
Materials Office staff based on preliminary investigations
c. Utility investigations - Continue investigations begun during the Development
Phase to reduce RFP risk pricing by identifying and evaluating potential
conflicts, coordinating identification and adjustment solutions with utility
owners, and developing a utility conflict matrix
d. Survey and ROW mapping - Mapping should be adequate to support
completion of the environmental document and support preliminary
engineering activities necessary to mitigate risk
7. Use the Risk Assessment Checklist to track and assess status and assign a risk
rating for ongoing activities to assess the readiness for release of the RFP.
- Coordinate activities being tracked in the Risk Assessment Checklist with
MDOT Procurement Checklist and Procurement Schedule
8. Schedule Procurement Phase risk workshop/risk team meeting.
1. Prepare a project overview presentation for each workshop/team risk meeting.
- Project overview and status
- Risk Management Process training, as applicable
2. Prepare for the risk workshop/risk team meeting:
- Determine scope of workshop and desired outcomes (qualitative or
quantitative; initial or update)
- Size the workshop appropriately
- Determine appropriate attendance: Project Team members including GEC,
Agency Leadership, Project Stakeholders, and local Officials; FHWA attendance
is required for PoDIs and optional for non-PoDI projects
- Prepare and distribute an agenda prior to the meeting
- Consider including a risk questionnaire to solicit feedback on risks prior to the
workshop
- Update register, if applicable, with feedback prior to the meeting
- Define Risk Response strategies and control assignments; these should be
ready to be discussed by identified parties for at least all High Priority risks
- Develop or update, as appropriate, the preliminary
project development schedule and preliminary cost estimate.
- Coordinate with the project team including stakeholders
and leadership to develop a risk rating scale for the project (Risk Workbook,
Section 5.3) to perform qualitative and quantitative assessments.
- Coordinate with leadership and stakeholders to establish an acceptable risk level
for high priority risks. Risks above the acceptable level are considered high
priority risks.
3. Conduct workshop in accordance with Risk Workbook Procedure.
4. Use the risk analysis performed at the workshop to perform post-workshop
updates to the risk register consistent with the outcomes from the workshop.
- Finalize the risk register with decisions and responses
- Communicate response plans to team members and stakeholders
5. Update the procurement schedule and risk contingency for the project
cost estimate based on the outcomes of the workshop.
6. Use the risk analysis to develop RFP documents. Assess how risk will be
allocated for the project. Risks should be allocated to the party best equipped
to manage the risk. Determine if shared risk items are required, define the
shared risk item, and coordinate these with the development of the ITP and
RFP:
a. ITP - Prepare Form 4 - Proposal Price to include the DB lump-sum project,
shared risk items identified in Book 1 – Section 12
b. Book 1 - Review need for project- specific modifications to the Agreement to
accommodate changes in risk allocation (i.e., shared risk items)
c. Book 1, Section 6 - Access to Site; Utility Relocations; Environmental
Mitigation - Review for potential risk allocation changes for right-of-way,
utilities, and environmental compliance that may affect this chapter; risk
allocations in the RFP documents are typically applicable to address right-of-
way concerns, environmental items, geotechnical items, utility conflicts,
third party items, and railroads
d. Review Book 1, Section 12 - Shared Risk Item Work and Price Adjustments -
Risk allocation changes to shared risk items could have a significant effect on
the structure, content and details of Section 12
e. Determine if shared risk items are required for structures and define the
shared risk item
f. Verify the prices for all shared risk items
g. For CMGC contracts, determine shared risk items; MDOT may choose to own
the contractual responsibility for the risk or pass it on to the contractor and
have it included in the Guaranteed Maximum Price (GMP) portion of the
construction services cost proposal; the risks will be used to identify criteria
used to short-list or select contractors; review risk associated with item
quantities and costs for the GMP
7. Include Alternate Technical Concepts (ATC) risk analysis to assess contractor's
proposed changes to contract requirements prior to bidding to evaluate
whether the concepts provide the public with a product that is equal or better
to the base design.
8. Perform the following risk analysis activities during procurement:
a. Mitigate project specific risks during development of the RFQ and RFP
documents
b. Assess whether the RFP provides the desired blend of prescriptive vs
performance-based requirements for a DB project; overly descriptive
requirements can limit innovation and, in some cases, bring additional risk to
MDOT if designs are prescribed to the DB contractor
c. Review the contractual language in the RFP to ensure the documents clearly
define the Design-Builder’s requirements and provide a constructable design
in order to minimize MDOT's risk of claims due to plan errors and omissions
d. From the risk analysis, identify early coordination with third parties, and if
necessary obtain as many agreements as possible with third parties prior to
issuance of the RFP
1. Risk monitoring and control:
- Establish a process using the Risk Management Workbook for conducting
monthly updates during the procurement
- Track and respond to changes in risk on a monthly basis
- Review and update the risk register and risk contingency monthly
2. Schedule and participate in monthly meetings with the Risk Management
Team to review current risk status:
- Assign a member of the Risk Management Team to coordinate the updates
with the Team
- Develop and implement strategies for responding to changing risks
- Use the updates from the latest workshop or monthly update as the basis for
discussions
- If a risk workshop is conducted, then the updates from the workshop replace
the monthly update
3. Review and update the High Priority list.
- Develop detailed response plans for all high priority risks
- Use the High Priority Risk report as a communication tool to report critical issues
4. Update the project cost estimate with changes to the cost risk contingency
from the monthly risk meeting or risk workshop.
5. Update the project development schedule with changes to the schedule
risk contingency and any changes to activity milestones.
6. Prepare the monthly report with current status:
- Use monthly risk reviews to develop documentation for reporting purposes
to leadership
- Report on High Priority risks and cost and schedule impacts
7. Evaluate whether the procurement is ready to progress to the next milestone
using the Risk Assessment Checklist, procurement schedule and RFP checklist.
MDOT Innovative Construction Contracting Guide References
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 5: Preliminary Project Information and Risk Assessment Meeting
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 13: Request for Proposals (RFP)
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 13: Request for Proposals (RFP)
Appendix D: Guidelines for the Procurement of Construction Manager/General Contractor
Contracts, Chapter 3: Preliminary Project Information and Risk Assessment Meeting
Section 5.1: Delivery Methods,
5.1E: Alternative Technical Concepts
Chapter 18: Alternate Technical Concepts (ATC)
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 13: Request for Proposals (RFP)
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 5: Preliminary Project Information and Risk Assessment Meeting, Appendix 5A: Initial Schedule
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 15: RFP Package Review Meeting
Risk Updates and Reporting
Risk Analysis and Allocation Meetings
Risk Review and Planning
Initial Risk Meeting
Action Status

## 3.4 Plan ¦ Implementation Phase
RISK MANAGEMENT PLAN
IMPLEMENTATION PHASE
Overview
Implement the major risk management process steps for the Implementation Phase.
Instructions
Identify the current step within the Risk Management Plan using the Action Status. Update the Action Status after progressing through each step. Review and complete the associated actions and click on an icon associated with an action to move directly to that page in the Workbook. Utilize the References identified for each step when necessary.
Workflow
Process Step
Action
1. Prior to the initial risk meeting for the Implementation Phase, conduct a lessons
learned and best practices workshop with the Procurement Phase project team.
- Review lessons learned documentation from the previous phase
- Consider any Implementation Phase lessons learned and best practices from
other projects and programs.
2. Schedule transition meeting with Procurement Phase risk management team.
- Determine appropriate attendance: Typically MDOT staff from IC, the
Region/TSC and key specialty areas, the FHWA, key procurement team staff
and the GEC
3. Conduct transition meeting for knowledge transfer from Procurement team to
Implementation team.
- Collaborate on assessing risk management needs and requirements
- Review on-going risk management activities from Procurement Phase
- Coordinate transition activities and transition of risk management
documentation from Procurement Phase (register and associated
documentation)
- Review roles of the parties
- Discuss risk management activities
- Resolution of contract claims and disputes, and issues related to contract
interpretation
- Define DADC responsibilities through FA
- Discuss risk monitoring and reporting requirements
1. Schedule transition training.
- Schedule for shortly after contract execution and prior to design
commencement
- Attendees should include MDOT staff from IC, the Region/TSC, key
specialty areas, the FHWA, if applicable, and the GEC.
2. Conduct transition training
- Review key contract requirements negotiated during the procurement and
negotiation phases (contractual timeframes, deliverables, contractual
requirements, specifications, and commitments)
- Review risk register and risk management process related to register updates
and reporting as applicable for implementation team
- Discuss project risks allocated to MDOT and strategies developed during the
procurement for managing risk
- Review lessons learned on previous projects and strategies for mitigating
contractual risk (issues, claims, disputes) such as noncompliance and dispute
resolution procedures
1. Risk monitoring and control:
- Establish a process using the Risk Management Workbook for conducting
monthly updates
- Track and respond to changes in risk on a monthly basis
- Review and update the risk register monthly
2. Schedule and participate in monthly meetings with the Risk Management
Team to review current risk status:
- Assign a member of the Risk Management Team to coordinate the updates
with the Team
- Develop and implement strategies for responding to changing risks
- Use the updates from the latest workshop or monthly update as the basis for
discussions
3. Prepare the monthly report with current status:
- Use monthly risk reviews to develop documentation for reporting
- Report on High Priority risks, cost and schedule impacts, and status of any
issues, claims and disputes
MDOT Innovative Construction Contracting Guide References
Appendix C: Guidelines for the Procurement of Design-Build Contracts, Chapter 5: Preliminary Project Information and Risk Assessment Meeting
Guidelines for the Procurement of Design-Build Contracts, Chapter 26: Training
Risk Updates and Reporting
Transition Training
Initial Risk Meeting
Action Status

## 4.0 Risk Mgmt Procedure
RISK MANAGEMENT PROCEDURE
Overview
The Risk Management Procedure describes the formal risk management workflow to conduct the risk management process at risk workshops consisting of risk identification, risk assessment, and risk response. The Risk Management Procedure is referenced in the Risk Management Plan during the Risk Analysis and Allocation Meetings step.
Instructions
Follow the step-by-step workflow when conducting the risk management process at risk workshops. Utilize the risk register and associated tools to record risk events and risk documentation. Click on an icon associated with an action to move directly to that page in the Workbook.
Assign risk category and project phase
Identification
Provide risk name and description
Identify a risk trigger
Qualitative
Assign a probability of occurrence to each risk
Assign a consequence for each risk (cost and schedule)
Calculate severity of the impact (probability x consequence)
Assess the likelihood the schedule impact is to the Critical Path and the milestone impacted
Quantitative
For risks identified as Event Driven Risks, Section 5.4 of the Workbook calculates Cost and Schedule Risk Contingencies based on the Ratings Guidelines in Section 5.3
Response
Develop a response plan for each risk
Assign risk threat response strategies
Assign an owner (individual, role or position) for each risk
Update risk status, if applicable
Document potential project risks in the Risk Register
Identify risk as a threat or an opportunity
Review and update quantitative values based on guidance from project team, leadership and stakeholders
Accept: Not changing the project plan to deal with a risk
Mitigate: Apply controls that reduce the probability or impact
Transfer: Shift the impact of a risk to a consultant or contractor
Avoid: Change the project plan to eliminate the risk
Process Step
Risk Identification
Risk Assessment
Risk Response
Description
Identification of risk events that, if they occur, are likely to affect the overall project objectives (impacts to scope, schedule, cost, and quality)
Determination of both the probability a given risk event will occur and the consequence of the occurrence to the project scope, schedule, cost, and quality
Determination of event driven risks and calculation of project cost and schedule risk contingency (Risk Workbook, Section 5.4)
Development of an action plan including specific processes or actions in order to lessen the impact of a threatening risk or maximize risk opportunities
Assign risk opportunity response strategies
Accept: Not changing the project plan to realize the risk
Enhance: Modify the risk to improve the probability or impact
Share: Shift the ownership of a risk to a consultant or contractor
Exploit: Eliminate the uncertainty to ensure the risk occurs
Allocate risk
Select type of impact
Calculate the total impact score
Assign risk dependency
Identify if the risk is an Event Driven Risk for quantitative assessment
Assessment

## 5.0 Register Documentation >>>
RISK REGISTER DOCUMENTATION
Overview
Risk Register Documentation templates are tools to facilitate documentation of risks and outcomes when working through the Risk Management Procedure, including:
1. Risk Register
2. Risk Breakdown Structure
3. Rating Guidelines
4. Risk Contingency and Schedule Impact Calculation
Instructions
Utilize the descriptions provided below and associated risk tools to help define the inputs required for the Risk Register. User instructions and guidance for use of the register are embedded in the column headers.
Risk Register Column
Risk Number
Risk Category (RBS)
Project Phase
Risk Name
Risk Description
Risk Trigger
Threat / Opportunity
Risk Allocation
Impact Type
Probability
Cost Consequence
Cost Impact
Schedule Consequence
Schedule Impact
Likelihood is on the CP
Milestone Impacted
Impact Score
Risk Dependency
Event Driven Risk
Response Strategy
Response Plan
Risk Owner
Risk Status
Notes
Risk Register Description
Sequential numbering of identified risks. Numbers are not reused when a risk is retired to enable tracking risks throughout all development phases.
The primary category or functional area that the risk pertains to. The risk breakdown structure is a way of categorizing or grouping risks by the potential cause of the risk.
Phase of the project development process the risk is anticipated to occur in. Note that a risk may carry over from one phase to another. Update at each workshop, which will likely necessitate modifications to triggers, risk assessment and responses.
A brief and unique name given to each risk or issue.
Concise description of the risk. Sample risk descriptions: "If <uncertain event>, then <effect on objectives>." Or "Due to <definite cause>, <uncertain event> may occur, resulting in <effect on project or objectives>."
The event or condition that is a precursor to the occurrence of the risk event. Listing trigger events may not be necessary for all risks but are useful for helping to define the risk and in the monitoring of a potential risk event.
Risks can have both negative and positive impacts. Threats have negative impacts while opportunities have positive impacts.
A risk is typically allocated to the party best equipped to manage the risk, typically either MDOT or the DB Contractor, or the risk may be shared.
The type of risk impact is limited in the register to cost and/or schedule impacts. Other risk impacts should be monitored such as quality and perception risks.
A qualitative rating on a scale of 1 through 5 indicating the likelihood that a risk will occur. See Register | Rating Guide in Section 5.3.
A qualitative rating on a scale of 1 through 5 for cost risk threats and -1 through -5 for cost risk opportunities indicating the degree of impact to the project should a risk occur. See Register | Rating Guide in Section 5.3.
The product of the qualitative rankings of probability and cost consequence. The qualitative rankings and prioritization should be completed first for the purpose of ranking and determining which risks are above and which below a risk threshold.
A qualitative rating on a scale of 1 through 5 for schedule risk threats and -1 through -5 for schedule risk opportunities indicating the degree of impact to the project should a risk occur. See Register | Rating Guide in Section 5.3.
The product of the qualitative rankings of probability and schedule consequence. The qualitative rankings and prioritization should be completed first for the purpose of ranking and determining which risks are above and which below a risk threshold.
Assess whether the schedule impact is likely to be on or close to the critical path.
For risks that impact the critical path, identify the milestone that is impacted.
The sum of the cost and schedule impacts.
Select whether the risk is independent of or interdependent on other risks. For interdependent risks, document in the Notes column the other interdependent risk(s) and how the dependency may impact the risk.
Identify risks for cost and schedule quantification. See Register | Contingency in Section 5.4.
Classification of responses. Note that the strategies are mostly different for threats and opportunities. Risks response should be determined early in the development process for codification in the procurement and contract documents.
Primary plan to address the risk prior to occurrence or becoming an issue. Response plans should be specific enough to
implement and may be an action or process. Generally should respond sufficiently to reduce the risk to below the risk
threshold.
Person or people responsible for monitoring the risk and providing updates to the project manager on the status of the risk or issue.
An option to set a risk as either Not Active (not yet triggered or no anticipatory responses needed), Active (monitored and controlled), Dormant (monitored and within the triggering event or period but not active), or Retired (complete). Risks identified as Retired are not factored into contingency calculations nor are they included on the High Priority Risk report.
Contingency plans can be noted here in the event risks become issues. Utilize the notes section to provide updates on actions or owners or to note changes to the response plans. Date updates in chronological order.

## 5.1 Register ¦ Risk Register
RISK REGISTER
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Project Name:
Current Project Phase:
Date of Current Update:
Risk Identification | [8 empty] | Risk Assessment | [9 empty] | Risk Response
RISK NUMBER | RISK CATEGORY (RBS) | PROJECT PHASE | RISK NAME | RISK DESCRIPTION | RISK TRIGGER | THREAT / OPPORTUNITY | RISK ALLOCATION | IMPACT TYPE | PROBABILITY | COST |  | SCHEDULE |  |  |  | IMPACT SCORE | RISK DEPENDENCY | EVENT DRIVEN RISK | RESPONSE STRATEGY | RESPONSE PLAN | RISK OWNER | RISK STATUS | NOTES
[10 empty] | CONSEQUENCE | IMPACT | CONSEQUENCE | IMPACT | LIKLIHOOD IS ON CP | MILESTONE IMPACTED
1 | [10 empty] | 0 |  | 0 |  |  | 0
2 | [10 empty] | 0 |  | 0 |  |  | 0
3 | [10 empty] | 0 |  | 0 |  |  | 0
4 | [10 empty] | 0 |  | 0 |  |  | 0
5 | [10 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
[11 empty] | 0 |  | 0 |  |  | 0
End of register. Maximum number of risks is 75.
Overview
The Risk Register is a comprehensive tool utilized to document, track, monitor, update and report project uncertainties. The Risk Register is flexible for use during each project phase with the ability to be customized to address specific project needs.
Instructions
Enter a project name, current phase, and date of current risk update. Complete each portion of the Risk Register that has a blue header strip as you work through the Risk Management Procedure. User instructions and guidance for use of the Risk Register are embedded in the column headers and in Section 5.0 Register Documentation. Utilize the filter drop-downs to prioritize risks by impact score to determine the highest priority risks or filter by category. Risks identified as Event Driven Risks will be factored into contingency calculations. Use additional rows at the bottom to add risks or hide rows that are not in use. To maintain the functionality of the Workbook, do not insert or remove rows or columns.

## 5.2 Register ¦ Risk Structure
RISK BREAKDOWN STRUCTURE
Overview
The Risk Breakdown Structure (RBS) is split between 17 categories. A drop-down menu built into the Risk Register enables the user to select each RBS category. When used across several projects, risks within the same RBS can be directly compared across projects to see trends and areas for future focus. If particular risks are frequently occurring, system-wide responses can be developed and implemented to minimize threats and maximize opportunities.
Instructions
Utilize this hierarchical approach to organize risks within the Risk Register by subject in a consistent manner across projects, assign risks to subject matter experts from multiple disciplines ,and report the number of risks or cumulative impact score by category.
Project
Construction
Design
Environmental
Financial
Operations and Maintenance
Organization
Procurement and Contracting
Partners and Stakeholders
Regulatory / Reporting
Risk Category
(RBS)
Right of Way
Safety
Third Party
Site
Hazardous Materials
Other
Project Management
Railroad
Utilities

## 5.3 Register ¦ Rating Guide
RATING GUIDELINES
Cells below referenced
[7 empty] | Estimated Project Cost ($) | [8 empty] | Estimated Project Duration (Months)
Probability (Percentage) |  |  |  | Cost Consequence | [6 empty] | Schedule Consequence
Assessment Rating | Probability of Occurrence | Rating Value (%) |  | Assessment Rating | Percent of Project Cost | Rating Bounds |  | Rating Value ($) |  |  | Assessment Rating |  | Percent of Project Schedule |  | Rating Bounds |  | Rating Value (Weeks)
1: Low | 1-15% | 10% |  | 1: Low | 0.1% | Up to $.0K |  | 25000 |  |  | 1: Low |  | 1% |  | Up to 1 Week |  | 1
2: Medium-Low | 16-30% | 25% |  | 2: Medium-Low | 0.5% | $1.0K to $.0K |  | 50000 |  |  | 2: Medium-Low |  | 4% |  | 1 to Weeks |  | 3
3: Medium | 31-65% | 50% |  | 3: Medium | 1% | $1.0K to $.0K |  | 250000 |  |  | 3: Medium |  | 8% |  | 1 to Weeks |  | 8
4: Medium-High | 66-80% | 75% |  | 4: Medium-High | 2% | $1.0K to $.0K |  | 500000 |  |  | 4: Medium-High |  | 12% |  | 1 to Weeks |  | 12
5: High | 81-99% | 90% |  | 5: High | 6% | $1.0K to $.0K |  | 1500000 |  |  | 5: High |  | 25% |  | 1 to Weeks |  | 20
Minimum and Maximum Offsets from Most Likely Values for Event Driven Risks
|  |  |  | Phase |  | Minimum |  | Maximum
|  |  |  | Identification and Selection |  | 25% |  | 30%
|  |  |  | Development |  | 20% |  | 25%
|  |  |  | Procurement |  | 10% |  | 15%
|  |  |  | Implementation |  | 3% |  | 5%
Assessment | [7 empty] | Severity Matrix
Probability Description |  |  |  | Assessment Rating | Consequence Description |  |  | Opportunities |  |  |  |  | Threats
|  |  | Unlikely to occur, improbable | 1: Low | Very little or slight impact |  | 5 | -25 | -20 | -15 | -10 | -5 | 5 | 10 | 15 | 20 | 25
|  |  | Infrequent, occasional occurrence in past, similar projects | 2: Medium-Low | Small to mild, noticeable impact |  | 4 | -20 | -16 | -12 | -8 | -4 | 4 | 8 | 12 | 16 | 20
|  |  | Likely to occur, from possible to probable | 3: Medium | Medium, significant impact |  | 3 | -15 | -12 | -9 | -6 | -3 | 3 | 6 | 9 | 12 | 15
|  |  | Very likely, has often occurred on other projects | 4: Medium-High | Substantial, strong impact |  | 2 | -10 | -8 | -6 | -4 | -2 | 2 | 4 | 6 | 8 | 10
|  |  | Highly likely to occur, occurred on projects with similar conditions | 5: High | Critical, very high impact |  | 1 | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5
[8 empty] | -5 | -4 | -3 | -2 | -1 | 1 | 2 | 3 | 4 | 5
Overview
The Rating Guidelines are referenced during the Assessment Step of the Risk Management Procedure. The Risk Register is linked to the Ratings Guidelines and qualitative assessment ratings (low, medium-low, medium, medium-high, and high) are assigned a numeric quantity (1, 2, 3, 4, and 5) to facilitate calculating impacts. The severity of the impact is calculated by multiplying the probability by the consequence. Ratings are assigned a color, dependent upon threat or opportunity classification, and a severity matrix shows a heat map for the risk impact to cost and schedule. Default values are provided and are based on estimated project cost and schedule as guidelines. Ratings for cost and schedule are scalable to the size and duration of each project and risk thresholds may be set by the management team for each project. The Rating Guidelines are also linked to the Contingency Worksheet to derive an initial quantitative assessment from the qualitative assessment ratings for each Event Driven Risk. Minimum and Maximum Offsets from Most Likely Values may be scaled for the quantitative assessment for Event Driven Risks.
Instructions
Manual entry is required within the blue-colored boxes. Enter the Estimated Project Cost and Estimated Project Duration. These will be used with the values assigned to Percent of Project Cost and Percent of Project Schedule to set consequence thresholds for low, medium-low, medium, medium-high, and high Assessment Ratings. Set the Ratings Values for probability and consequences based upon the Ratings Bounds to be used in risk contingency calculations. Modify the offset percentages from the Most Likely value to change the minimum and maximum values in the risk contingency calculations.
Probability
Consequence

## 5.4 Register ¦ Contingency
RISK CONTINGENCY
Project Name:
Current Project Phase:
Date of Current Update:
EVENT DRIVEN RISK ITEMS
RISK NUMBER | RISK NAME | PROBABILITY OF RISK OCCURRENCE | ESTIMATED COST IMPACT | [5 empty] | ESTIMATED SCHEDULE IMPACT (WEEKS)
|  |  | MINIMUM | MOST LIKELY | MAXIMUM | EXPECTED ESTIMATED COST RISK | VARIANCE | STANDARD DEVIATION | MINIMUM | MOST LIKELY | MAXIMUM | EXPECTED ESTIMATED SCHEDULE RISK | VARIANCE | STANDARD DEVIATION
[5 empty] | Subtotals: | 0 | 0 | 0 |  |  | Subtotals: | 0 | 0 | 0
Note: Values are rounded and could create a potential for discrepancies in summed numbers.
[7 empty] | Cost Risk Contingency | [5 empty] | Schedule Risk Contingency
|  |  | Confidence Level (Percent Chance of Not Exceeding) |  |  | 50% | P50 | 0 | Confidence Level (Percent Chance of Not Exceeding) |  |  | 50% | P50 | 0
[6 empty] | 70% | P70 | 0 |  |  |  | 70% | P70 | 0
[6 empty] | 90% | P90 | 0 |  |  |  | 90% | P90 | 0
g
Overview
The Contingency Worksheet is a tool referenced during the Assessment Step of the Risk Management Procedure to capture Event Driven Risks and calculate project risk contingency and project schedule impacts. The quantitative probability of occurrence and cost and schedule consequence rating values are defined in the Rating Guidelines based on the qualitative values provided in the Register. The order of risks in the Contingency Worksheet aligns with the order of risks within the Register. The Most Likely cost and schedule impact is based on the Rating Value entered in the Rating Guidelines. The Most Likely schedule consequence will be multiplied by the likelihood the risk is on the critical path to calculate the schedule impact to the critical path. The quantitative Most Likely cost and schedule impacts are provisional assessments of the risk impacts and are subject to review and update to determine the most appropriate impact of the risk. The sum of the Expected Estimated Cost values and the Expected Estimated Schedule values results in the P50 risk contingency and project schedule impacts, respectively, where P50 represents a 50% probability that the impact will not exceed the calculated value. The sum of the variances of the individual Event Driven Risks is used to calculate the P70 and P90 risk contingency.

## 6.0 Reporting >>>
This page is intentionally left blank.

## 6.1 Report ¦ High Priority
HIGH PRIORITY RISKS
Project Name:
Current Project Phase:
Date of Current Update:
RISK NUMBER | RISK NAME | COST |  | SCHEDULE |  | IMPACT SCORE
|  | COST IMPACT | RISK IMPACT | SCHEDULE IMPACT | RISK IMPACT
Summary of High Risk Items
1
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
2
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
3
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
4
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
5
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
6
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
7
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
8
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
9
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
10
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
11
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
12
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
13
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
14
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
15
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
16
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
17
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
18
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
19
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
20
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
21
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
22
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
23
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
24
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
25
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
26
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
27
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
28
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
29
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
30
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
31
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
32
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
33
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
34
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
35
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
36
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
37
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
38
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
39
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
40
Risk Register Item
Overall Risk Rating
Category (RBS)
Risk Description
Responsible Party
Response Plan
Notes
Overview
The High Priority Risk report template is a reporting tool to highlight and prioritize active risks for the purpose of developing response plans, and report and monitor key project development activities. This report provides a list of “High Priority Risks,” that is, risks that are not retired and are qualitatively rated as “Medium-High" or "High" impact for either cost or schedule according to the Severity Matrix provided in the Rating Guidelines. This can include both Event Driven Risks and non-Event Driven Risks.
The High Priority Risk report is linked to the Risk Register and contains two reporting sections. The first section is a qualitative overview table. Opportunities and threats are color-coded according to the Rating Guidelines. The risks are sequenced in descending order by impact score, which is the combined total of the cost impact and schedule impact for a risk. The second section contains additional information in notecard format for each of the risks provided in the first section.

## 6.2 Report ¦ Assess Checklist
RISK ASSESSMENT CHECKLIST
Assessment Ratings | Risk Impact | Assessment Criteria
1 | Low | Criterion is on schedule to complete on or before the preferred milestone date.
2 | Medium-Low | Criterion has passed the preferred milestone date but is on schedule to complete by a less preferred but acceptable milestone, or the finish date has been extended one time.
3 | Medium | Criterion has extended the finish date two times.
4 | Medium-High | Criterion has extended the finish date three times.
5 | High | Criterion has missed both preferred and alternate milestone dates, or has extended the target milestone four or more times.
Project Name: |  |  |  |  | Assessment Date:
Project Readiness Criteria |  | Current Status | Begin Date | Target Completion Date | Risk Rating | Completion Date1
1 Environmental Status |  | •
Summary:
2 Schematic Development |  | •
Summary:
3 Right-of-Way (% of Parcels Acquired) |  | •
Summary:
4 Utility Investigations (SUE) |  | •
Percent Complete:
Summary:
5 Geotechnical Investigations (% Complete) |  | •
Summary:
6 Risk Assessment |  | •
7 Funding Status |  | •
Summary:
8 Additional Comments on Project Readiness That Could Affect Procurement Schedule
Summary:
Notes:
1. Actual or anticipated completion date
Overview
Impacts to the project development schedule resulting from delay in achieving project development target milestones are reported in the Risk Assessment Checklist. Project readiness criteria include activities that typically need higher scrutiny from the project team in order to be ready to advance the project. Target milestones are defined in the project schedule and the progress and percent complete are reported in the Risk Assessment Checklist as part of the routine reporting in order to make the project team aware of current status and milestones needing to be achieved.
Instructions
Complete the Risk Assessment Checklist populating values within blue columns for each of the project readiness criteria. Determine a risk rating for each criteria based on the assessment rating criteria provided in the top table.